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QUOTATION ESTIMATE
Architectural Design & Consulting Services
Atelier Architectural Méditerranée
14 Rue de la République, 13001 Marseille, France
Tel: +33 (0)4 91 00 00 00 | Email: contact@atelier-archi-marseille.fr
SIRET: 842 567 891 00012 | TVA: FR 45 842567891
Quotation Reference: QTE-2025-MA-0472
Date of Issue: 12 June 2025
Validity Period: 60 days from date of issue
Prepared By: M. Laurent Delacroix, Architecte DPLG
Order No.: ORD-2025-0318
Project Location: Marseille, Bouches-du-Rhône, France
1. Client Information
	Client Name:
	Mme. Sophie Marchand

	Address:
	27 Boulevard Longchamp, 13001 Marseille, France

	Contact:
	+33 (0)6 12 34 56 78 | s.marchand@email.fr

	Project Site:
	Parcelle cadastrale AB-1247, 8 Rue Sainte, 13007 Marseille (Le Panier district)


2. Project Description
This Quotation Estimate is issued by Atelier Architectural Méditerranée, a registered Architect firm operating in France Marseille, for the complete architectural design, planning, and regulatory compliance services for the renovation and partial extension of a historic residential property located in the Le Panier district of Marseille. The project encompasses the restoration of a 19th-century stone façade, the interior reconfiguration of approximately 185 square metres of living space, and the addition of a 42 square metre rear extension in compliance with the local Plan Local d'Urbanisme (PLU) of the Ville de Marseille. All design work will respect the heritage constraints imposed by the Service de l'Architecture et du Patrimoine of the Bouches-du-Rhône department, as the property falls within a protected urban zone.
3. Scope of Architectural Services
The Architect services included in this quotation comprise the following phases, in accordance with the French regulatory framework (Code de l'Urbanisme, Code de la Construction et de l'Habitation) and the professional standards of the Ordre des Architectes de la Région Sud:
	Phase
	Description
	Duration
	Estimated Cost (EUR)

	Phase 1 – Étude de Programmation
	Site survey, topographic analysis, heritage assessment, client brief development, feasibility study, and preliminary concept sketches for the Marseille property.
	4 weeks
	€ 4,800.00

	Phase 2 – Esquisse (Concept Design)
	Development of three design options, 3D visualisations, material palette selection appropriate to the Mediterranean climate of Marseille, and client presentation sessions.
	5 weeks
	€ 6,200.00

	Phase 3 – Avant-Projet Détaillé (Detailed Design)
	Full architectural drawings (plans, sections, elevations), structural coordination, energy performance calculations (DPE compliance), and heritage authority submission documents.
	6 weeks
	€ 8,500.00

	Phase 4 – Permis de Construire
	Preparation and submission of the building permit application (Permis de Rénovation avec Extension) to the Mairie de Marseille, response to any administrative queries, and coordination with the Architecte des Bâtiments de France (ABF).
	8 weeks
	€ 5,400.00

	Phase 5 – Projet d'Exécution (Execution Design)
	Detailed construction drawings, technical specifications (CCTP), tender documentation, and contractor coordination for the Marseille site.
	5 weeks
	€ 7,800.00

	Phase 6 – Suivi de Chantier (Site Supervision)
	Regular site visits (bi-weekly), quality control, progress reporting, and final acceptance inspection upon completion of works in Marseille.
	12 weeks
	€ 9,600.00


4. Cost Summary
	Item
	Amount (EUR)

	Phase 1 – Étude de Programmation
	€ 4,800.00

	Phase 2 – Esquisse
	€ 6,200.00

	Phase 3 – Avant-Projet Détaillé
	€ 8,500.00

	Phase 4 – Permis de Construire
	€ 5,400.00

	Phase 5 – Projet d'Exécution
	€ 7,800.00

	Phase 6 – Suivi de Chantier
	€ 9,600.00

	Subtotal (Architect Fees)
	€ 42,300.00

	VAT (TVA) at 20%
	€ 8,460.00

	TOTAL ESTIMATED COST (TTC)
	€ 50,760.00


Note: This Quotation Estimate does not include third-party costs such as structural engineer fees, geotechnical survey, ABF consultation fees, or municipal permit filing charges, which are estimated at an additional € 3,200.00 and will be billed at actual cost.
5. Payment Terms
Payment shall be made in accordance with the following schedule, aligned with the completion of each architectural phase:
· 30% upon signature of the professional engagement contract (Marche de maîtrise d'œuvre) – € 15,228.00 TTC
· 25% upon approval of the Avant-Projet Détaillé – € 12,690.00 TTC
· 25% upon grant of the Permis de Construire by the Ville de Marseille – € 12,690.00 TTC
· 20% upon completion of site supervision and final handover – € 10,152.00 TTC
All payments are due within 30 days of invoice issuance. Late payments shall incur interest at the statutory rate applicable in France (taux d'intérêt légal).
6. Terms and Conditions
1. This Quotation Estimate is valid for a period of sixty (60) calendar days from the date of issue. After this period, the Architect reserves the right to revise the pricing due to potential changes in material costs, regulatory requirements, or market conditions in France Marseille.
1. All architectural services shall be performed in strict compliance with the French Code de l'Urbanisme, the PLU of Marseille, and the specific heritage regulations applicable to the Le Panier sector.
1. The Architect shall carry out professional liability insurance (assurance responsabilité civile professionnelle) with a minimum coverage of € 5,000,000, as required by the Ordre des Architectes.
1. Any variation in the scope of work exceeding 10% of the originally estimated cost shall require a written amendment to this Quotation Estimate, signed by both parties.
1. The client acknowledges that the final building permit decision rests solely with the Mairie de Marseille and the relevant heritage authorities. The Architect shall make reasonable efforts to ensure compliance but cannot guarantee administrative approval.
1. All intellectual property rights in the architectural drawings and designs produced under this engagement shall remain with the Architect, with a non-exclusive licence granted to the client for the specific project in Marseille.
1. This Quotation Estimate is governed by French law. Any dispute shall be submitted to the jurisdiction of the Tribunal Judiciaire de Marseille.
7. Acceptance and Signatures
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms and conditions set forth herein for the architectural services to be delivered in France Marseille.
For the Architect (Atelier Architectural Méditerranée):
M. Laurent Delacroix, Architecte DPLG
Signature & Date: _________________________
For the Client:
Mme. Sophie Marchand
Signature & Date: _________________________
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