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Quotation Estimate Validity: This Quotation Estimate for Architect services in Israel Jerusalem is valid for a period of sixty (60) calendar days from the date of issue. All pricing is subject to confirmation of site conditions and municipal planning approvals by the Jerusalem Municipality.
1. Project Overview
This Quotation Estimate is issued by Levant Architectural Design Studio, a licensed Architect firm registered in Israel, to provide comprehensive Architectural Design and Planning Services for a residential and commercial mixed-use development project located in the city of Jerusalem, Israel. The project encompasses the design, planning, and regulatory submission of a four-story building situated in the central district of Jerusalem, in accordance with all applicable Israeli building codes, the Jerusalem Municipal Planning and Building Ordinance, and the national regulations set forth by the Israel Ministry of Construction and Housing.
As the designated Architect for this project, our firm will manage the entire design lifecycle from initial concept development through to final construction documentation, ensuring full compliance with the unique urban planning requirements specific to Jerusalem, including heritage preservation guidelines, setback regulations, and the Jerusalem City Council's aesthetic and structural standards.
2. Scope of Architectural Services
	No.
	Service Description
	Phase / Duration
	Unit
	Amount (ILS)

	1
	Initial site survey, feasibility study, and concept design for the Jerusalem residential-commercial project, including topographical analysis and solar orientation assessment specific to the Jerusalem landscape.
	Phase 1 / 3 weeks
	Lump Sum
	45,000

	2
	Preparation of full Architectural Design drawings (floor plans, elevations, sections, and 3D renderings) compliant with Israel Building Code (Tikun 12) and Jerusalem Municipality planning requirements.
	Phase 2 / 6 weeks
	Lump Sum
	120,000

	3
	Structural coordination and integration with licensed structural engineers for the Jerusalem project, including load calculations and foundation design documentation.
	Phase 2 / 4 weeks
	Lump Sum
	35,000

	4
	Preparation and submission of all planning and building permits to the Jerusalem Municipality Planning Department, including responses to municipal review comments and attendance at planning committee hearings.
	Phase 3 / 8 weeks
	Lump Sum
	55,000

	5
	Full construction documentation package: detailed Architectural drawings, specifications, material schedules, and technical notes for tender and construction purposes in Israel.
	Phase 4 / 5 weeks
	Lump Sum
	95,000

	6
	Site supervision and Architectural oversight during construction, including weekly site visits, progress reports, and coordination with the general contractor throughout the build in Jerusalem.
	Phase 5 / 12 months
	Monthly
	18,000

	7
	Final as-built documentation, handover certification, and compliance verification with the Israel Ministry of Construction and Housing for project completion in Jerusalem.
	Phase 6 / 3 weeks
	Lump Sum
	25,000


3. Cost Summary
	Description
	Amount (ILS)

	Phases 1 through 5 (Design, Planning, and Documentation)
	350,000

	Phase 6: Site Supervision (12 months × 18,000 ILS)
	216,000

	Phase 7: Final Documentation and Handover
	25,000

	Subtotal
	591,000

	VAT (18% — Israel Value Added Tax)
	106,380

	Total Quotation Estimate (Architect Services, Israel Jerusalem)
	697,380 ILS


4. Payment Schedule
Payment for this Quotation Estimate shall be made in accordance with the following milestone-based schedule: 20% upon contract signing, 25% upon completion of Phase 2 (design drawings), 20% upon receipt of building permits from the Jerusalem Municipality, 20% upon delivery of full construction documentation, and 15% upon final project handover and certification. Monthly site supervision fees shall be invoiced at the beginning of each calendar month.
5. Terms and Conditions
· This Quotation Estimate is issued exclusively for the Architect services described herein for the specified project in Jerusalem, Israel, and may not be transferred or applied to any other project or location without written consent.
· All Architectural work shall be performed in strict compliance with the Israeli Planning and Building Law (5725-1965), the Jerusalem Municipal Ordinance, and all relevant national and local regulations in force at the time of execution.
· The Architect firm shall carry professional indemnity insurance in the amount of no less than 2,000,000 ILS, as required by the Israel Architects Association.
· Any changes to the scope of work, additional design iterations, or unforeseen municipal requirements identified by the Jerusalem planning authorities shall be subject to a supplementary Quotation Estimate issued by the Architect firm.
· The Architect retains full intellectual property rights over all design drawings and documentation produced under this Quotation Estimate until full payment has been received.
· Disputes arising from this Quotation Estimate shall be resolved in accordance with Israeli law, with jurisdiction vested in the courts of Jerusalem, Israel.
· This Quotation Estimate does not include costs for third-party services such as geotechnical surveys, environmental impact assessments, or specialized MEP engineering, which shall be quoted separately.
6. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate for Architect services in Israel Jerusalem and agrees to the terms, conditions, and pricing outlined herein. The Architect firm confirms its availability and commitment to deliver the services described in accordance with the highest professional standards of the Israeli architectural profession.
For Levant Architectural Design Studio
(Architect of Record, Israel)
Name: _________________________
Date: _________________________
For the Client
(Project Owner, Jerusalem)
Name: _________________________
Date: _________________________
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