Quotation Estimate - Architect Services - Israel Tel Aviv
QUOTATION ESTIMATE
Architectural Design & Consulting Services
Prepared for clients in Israel Tel Aviv and surrounding metropolitan areas
Quotation Estimate No.: QTE-TLV-2025-0487
Date of Issue: 15 June 2025
Valid Until: 15 July 2025
Architect Firm: Levant Design & Build Architects Ltd.
Address: 42 Dizengoff Street, Tel Aviv-Yafo, Israel 63500
Licence No.: IL-ARCH-2019-0342
1. Client Information
	Field
	Details

	Client Name
	Mr. David Ben-Ari

	Project Address
	18 Rothschild Boulevard, Tel Aviv-Yafo, Israel 65000

	Project Type
	Residential Renovation & Extension – 4-Storey Building

	Contact Email
	d.benari@email.co.il

	Contact Phone
	+972-52-345-6789


2. Scope of Architect Services
This Quotation Estimate outlines the comprehensive architectural services to be provided by our licensed Architect team for the residential renovation and extension project located in Israel Tel Aviv. The scope encompasses all phases from initial concept design through to construction supervision, in full compliance with the Israeli Building Code (Tikun 12), the Tel Aviv-Yafo Municipality planning regulations, and the requirements of the Israel Land Authority.
The Architect of record will manage all design documentation, coordinate with structural engineers, MEP consultants, and the local planning authority in Tel Aviv, and ensure that the final design meets the aesthetic, functional, and regulatory standards expected in the Tel Aviv metropolitan area.
3. Detailed Pricing Breakdown
	Phase / Service
	Description
	Duration
	Amount (ILS)

	Phase 1 – Feasibility & Concept Design
	Site analysis in Tel Aviv, zoning verification with Tel Aviv-Yafo Municipality, concept sketches, massing studies, and preliminary budget estimation.
	4 weeks
	45,000

	Phase 2 – Schematic Design
	Detailed floor plans, elevations, sections, 3D renderings, material palettes, and coordination with structural and MEP consultants.
	6 weeks
	78,000

	Phase 3 – Design Development
	Refined architectural drawings, façade design compliant with Tel Aviv heritage guidelines, interior layout finalization, and landscape integration.
	5 weeks
	62,000

	Phase 4 – Construction Documentation
	Full set of construction drawings (A1 scale), specifications, BOQ preparation, and submission package for Tel Aviv building permit application.
	8 weeks
	95,000

	Phase 5 – Permit & Approval Support
	Representation before the Tel Aviv-Yafo Planning & Building Committee, response to municipal comments, and final permit acquisition.
	6 weeks
	38,000

	Phase 6 – Construction Supervision
	Weekly site visits in Tel Aviv, quality control, as-built documentation, and final handover inspection.
	12 months
	120,000

	Additional – Interior Design Package
	Complete interior design for all four floors including kitchen, bathrooms, and built-in storage solutions.
	4 weeks
	55,000

	Subtotal
	493,000

	VAT (18%)
	88,740

	TOTAL QUOTATION ESTIMATE (incl. VAT)
	581,740 ILS


4. Payment Schedule
Payment for the services described in this Quotation Estimate shall be made in accordance with the following milestone-based schedule, as is standard practice for Architect engagements in Israel Tel Aviv:
	Milestone
	Percentage
	Amount (ILS, incl. VAT)

	Upon signing of this Quotation Estimate
	15%
	87,261

	Upon approval of Schematic Design
	20%
	116,348

	Upon submission of Construction Documentation
	25%
	145,435

	Upon receipt of Building Permit from Tel Aviv Municipality
	20%
	116,348

	Upon completion of Construction Supervision
	20%
	116,348


5. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After this period, the Architect reserves the right to revise pricing due to market fluctuations in Israel Tel Aviv.
· All services shall be performed in accordance with the Code of Ethics of the Israel Architects Association and the provisions of the Architects and Interior Designers Law, 5726-1966.
· The Architect shall carry professional indemnity insurance with a minimum coverage of 5,000,000 ILS, valid throughout the project duration in Tel Aviv.
· Any changes to the scope of work beyond 10% of the original design will require a revised Quotation Estimate and written client approval before additional work commences.
· All intellectual property rights in the design documents produced by the Architect shall remain with the firm until full payment is received. Upon final payment, the client receives a non-exclusive licence to use the drawings for the specific project in Israel Tel Aviv.
· Disputes arising from this Quotation Estimate shall be resolved under the jurisdiction of the Tel Aviv District Court, Israel.
· The Architect is not responsible for delays caused by the Tel Aviv-Yafo Municipality planning committee, third-party contractors, or force majeure events.
Note: This Quotation Estimate does not include municipal fees, planning committee charges, surveyor fees, or any third-party consultant costs required by the Tel Aviv-Yafo Municipality. These will be billed at cost with a 5% administrative surcharge. The Architect will provide a detailed breakdown of all municipal fees upon request.
6. Acceptance and Authorization
By signing below, the client acknowledges and accepts this Quotation Estimate for Architect services in Israel Tel Aviv and agrees to all terms and conditions stated herein. This document constitutes a binding agreement upon countersignature by both parties.
For the Architect Firm
Levant Design & Build Architects Ltd.
Name: Arch. Miriam Cohen, RIBA, IAI
Date: _______________
For the Client
Mr. David Ben-Ari
ID No.: _______________
Date: _______________
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