# Quotation Estimate - Architect Services - Kuwait Kuwait City

# AL-NAKHEEL ARCHITECTURE & DESIGN FIRM

Office 12, Al-Salem Tower, Al-Salem Street, Kuwait City, State of Kuwait

Tel: +965 2244 5566 | Email: info@alnakheel-arch.com | License No: KWA-2019-04872

Quotation Estimate

### Quotation Details

Quotation No: QE-2025-0347

Date of Issue: 14 June 2025

Validity Period: 30 days from date of issue

Project Location: Kuwait Kuwait City

### Client Information

Client Name: Mr. Fahad Al-Sabah

Company: Al-Sabah Real Estate LLC

Address: Block 7, House 42, Salmiya, Kuwait

Contact: +965 9988 7766

## Project Description

This Quotation Estimate is prepared by Al-Nakheel Architecture & Design Firm in response to the request from the client for comprehensive Architect services for a residential villa project located in Kuwait Kuwait City. The project involves the design, planning, and architectural supervision of a four-storey residential villa with a total built-up area of approximately 1,850 square metres, situated on a 1,200 square metre plot in the Salmiya district of Kuwait Kuwait City. The Architect will be responsible for all phases of design development, regulatory compliance with Kuwait Municipality standards, and on-site construction supervision throughout the project duration.

## Scope of Architect Services

The following Quotation Estimate itemises the professional Architect services to be delivered. All work will be performed in accordance with the Kuwait Building Code, Kuwait Municipality regulations, and the professional standards of the Kuwait Society of Engineers. The Architect will coordinate with all necessary consultants including structural engineers, MEP engineers, and landscape architects as required for the project in Kuwait Kuwait City.

| No. | Description of Architect Service | Duration | Unit | Amount (KWD) |
| --- | --- | --- | --- | --- |
| 1 | Pre-Design Phase – Site analysis in Kuwait Kuwait City, feasibility study, zoning verification, and concept development for the residential villa | 3 weeks | Lump Sum | 4,500.000 |
| 2 | Schematic Design – Architectural floor plans, elevations, 3D massing models, and material palette presentation for client approval | 4 weeks | Lump Sum | 7,200.000 |
| 3 | Design Development – Detailed architectural drawings, interior layout plans, facade design, and coordination with structural and MEP consultants | 6 weeks | Lump Sum | 11,500.000 |
| 4 | Construction Documentation – Full set of construction drawings, specifications, and technical schedules for Kuwait Municipality submission | 8 weeks | Lump Sum | 14,800.000 |
| 5 | Permitting & Regulatory Approval – Preparation and submission of all documents to Kuwait Municipality, Fire Department, and Public Authority for Housing Welfare in Kuwait Kuwait City | 6 weeks | Lump Sum | 5,200.000 |
| 6 | Construction Administration & Site Supervision – Weekly site visits, progress monitoring, RFIs, and Architect sign-off on critical milestones | 14 months | Monthly | 3,800.000 / mo |
| 7 | As-Built Documentation & Handover – Final as-built drawings, operation manuals, and project close-out documentation | 3 weeks | Lump Sum | 3,500.000 |

## Cost Summary

| Item | Amount (KWD) |
| --- | --- |
| Pre-Design Phase (Item 1) | 4,500.000 |
| Schematic Design (Item 2) | 7,200.000 |
| Design Development (Item 3) | 11,500.000 |
| Construction Documentation (Item 4) | 14,800.000 |
| Permitting & Regulatory Approval (Item 5) | 5,200.000 |
| Construction Administration (Item 6) – 14 months × 3,800.000 | 53,200.000 |
| As-Built Documentation & Handover (Item 7) | 3,500.000 |
| Subtotal | 99,900.000 |
| VAT (5% – Kuwait) | 4,995.000 |
| Grand Total (KWD) | 104,895.000 |

## Terms and Conditions

1. This Quotation Estimate is valid for a period of thirty (30) calendar days from the date of issue. Beyond this period, the Architect reserves the right to revise fees due to market fluctuations or changes in project scope.

2. Payment shall be made in KWD (Kuwaiti Dinar) via bank transfer to the account of Al-Nakheel Architecture & Design Firm. A 25% advance payment is required upon acceptance of this Quotation Estimate to commence the Pre-Design Phase.

3. The Architect will issue monthly progress invoices for the Construction Administration phase. All other phases will be invoiced upon completion and client sign-off of deliverables.

4. The client is responsible for all third-party costs including Kuwait Municipality fees, consultant fees (structural, MEP, landscape), soil testing, and any government levies applicable in Kuwait Kuwait City. These are not included in this Quotation Estimate.

5. The Architect shall not be liable for delays caused by government approval processes, force majeure events, or client-initiated design changes. Any additional Architect time required for design revisions beyond two (2) rounds per phase will be billed at a rate of 180 KWD per hour.

6. All intellectual property, drawings, and design documents produced by the Architect remain the property of Al-Nakheel Architecture & Design Firm until full payment is received. Upon full settlement, the client receives a non-exclusive licence to use the documents for the specific project in Kuwait Kuwait City.

7. This Quotation Estimate does not constitute a binding contract until a formal Architect Services Agreement is executed by both parties. The terms herein are indicative and subject to final contractual negotiation.

8. The Architect shall maintain professional indemnity insurance with a minimum coverage of 500,000 KWD throughout the project duration.

9. Any disputes arising from this Quotation Estimate or the subsequent services shall be resolved in accordance with the laws of the State of Kuwait and under the jurisdiction of the courts of Kuwait City.

## Acceptance

By signing below, the client acknowledges receipt of this Quotation Estimate for Architect services and agrees to the terms outlined herein. The Architect confirms availability to commence work upon receipt of the advance payment and execution of the formal services agreement.

For the Client
Name: Mr. Fahad Al-Sabah
Signature: _________________________
Date: _________________________

For the Architect
Name: Eng. Layla Al-Mutawa, RIBA / KSE
Signature: _________________________
Date: _________________________

Al-Nakheel Architecture & Design Firm | Kuwait Kuwait City | This Quotation Estimate is the property of Al-Nakheel Architecture & Design Firm and may not be reproduced without written consent.

Page 1 of 1 | Document Ref: QE-2025-0347