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Quotation Estimate
Quotation Details
Quotation No: QE-2025-0347
Date of Issue: 14 June 2025
Validity Period: 30 days from date of issue
Project Location: Kuwait Kuwait City
Client Information
Client Name: Mr. Fahad Al-Sabah
Company: Al-Sabah Real Estate LLC
Address: Block 7, House 42, Salmiya, Kuwait
Contact: +965 9988 7766
Project Description
This Quotation Estimate is prepared by Al-Nakheel Architecture & Design Firm in response to the request from the client for comprehensive Architect services for a residential villa project located in Kuwait Kuwait City. The project involves the design, planning, and architectural supervision of a four-storey residential villa with a total built-up area of approximately 1,850 square metres, situated on a 1,200 square metre plot in the Salmiya district of Kuwait Kuwait City. The Architect will be responsible for all phases of design development, regulatory compliance with Kuwait Municipality standards, and on-site construction supervision throughout the project duration.
Scope of Architect Services
The following Quotation Estimate itemises the professional Architect services to be delivered. All work will be performed in accordance with the Kuwait Building Code, Kuwait Municipality regulations, and the professional standards of the Kuwait Society of Engineers. The Architect will coordinate with all necessary consultants including structural engineers, MEP engineers, and landscape architects as required for the project in Kuwait Kuwait City.
	No.
	Description of Architect Service
	Duration
	Unit
	Amount (KWD)

	1
	Pre-Design Phase – Site analysis in Kuwait Kuwait City, feasibility study, zoning verification, and concept development for the residential villa
	3 weeks
	Lump Sum
	4,500.000

	2
	Schematic Design – Architectural floor plans, elevations, 3D massing models, and material palette presentation for client approval
	4 weeks
	Lump Sum
	7,200.000

	3
	Design Development – Detailed architectural drawings, interior layout plans, facade design, and coordination with structural and MEP consultants
	6 weeks
	Lump Sum
	11,500.000

	4
	Construction Documentation – Full set of construction drawings, specifications, and technical schedules for Kuwait Municipality submission
	8 weeks
	Lump Sum
	14,800.000

	5
	Permitting & Regulatory Approval – Preparation and submission of all documents to Kuwait Municipality, Fire Department, and Public Authority for Housing Welfare in Kuwait Kuwait City
	6 weeks
	Lump Sum
	5,200.000

	6
	Construction Administration & Site Supervision – Weekly site visits, progress monitoring, RFIs, and Architect sign-off on critical milestones
	14 months
	Monthly
	3,800.000 / mo

	7
	As-Built Documentation & Handover – Final as-built drawings, operation manuals, and project close-out documentation
	3 weeks
	Lump Sum
	3,500.000


Cost Summary
	Item
	Amount (KWD)

	Pre-Design Phase (Item 1)
	4,500.000

	Schematic Design (Item 2)
	7,200.000

	Design Development (Item 3)
	11,500.000

	Construction Documentation (Item 4)
	14,800.000

	Permitting & Regulatory Approval (Item 5)
	5,200.000

	Construction Administration (Item 6) – 14 months × 3,800.000
	53,200.000

	As-Built Documentation & Handover (Item 7)
	3,500.000

	Subtotal
	99,900.000

	VAT (5% – Kuwait)
	4,995.000

	Grand Total (KWD)
	104,895.000


Terms and Conditions
1. This Quotation Estimate is valid for a period of thirty (30) calendar days from the date of issue. Beyond this period, the Architect reserves the right to revise fees due to market fluctuations or changes in project scope.
2. Payment shall be made in KWD (Kuwaiti Dinar) via bank transfer to the account of Al-Nakheel Architecture & Design Firm. A 25% advance payment is required upon acceptance of this Quotation Estimate to commence the Pre-Design Phase.
3. The Architect will issue monthly progress invoices for the Construction Administration phase. All other phases will be invoiced upon completion and client sign-off of deliverables.
4. The client is responsible for all third-party costs including Kuwait Municipality fees, consultant fees (structural, MEP, landscape), soil testing, and any government levies applicable in Kuwait Kuwait City. These are not included in this Quotation Estimate.
5. The Architect shall not be liable for delays caused by government approval processes, force majeure events, or client-initiated design changes. Any additional Architect time required for design revisions beyond two (2) rounds per phase will be billed at a rate of 180 KWD per hour.
6. All intellectual property, drawings, and design documents produced by the Architect remain the property of Al-Nakheel Architecture & Design Firm until full payment is received. Upon full settlement, the client receives a non-exclusive licence to use the documents for the specific project in Kuwait Kuwait City.
7. This Quotation Estimate does not constitute a binding contract until a formal Architect Services Agreement is executed by both parties. The terms herein are indicative and subject to final contractual negotiation.
8. The Architect shall maintain professional indemnity insurance with a minimum coverage of 500,000 KWD throughout the project duration.
9. Any disputes arising from this Quotation Estimate or the subsequent services shall be resolved in accordance with the laws of the State of Kuwait and under the jurisdiction of the courts of Kuwait City.
Acceptance
By signing below, the client acknowledges receipt of this Quotation Estimate for Architect services and agrees to the terms outlined herein. The Architect confirms availability to commence work upon receipt of the advance payment and execution of the formal services agreement.
For the Client
Name: Mr. Fahad Al-Sabah
Signature: _________________________
Date: _________________________
For the Architect
Name: Eng. Layla Al-Mutawa, RIBA / KSE
Signature: _________________________
Date: _________________________
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