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QUOTATION ESTIMATE
Quotation No: QE/2025/KL/0472
Date Issued: 15 June 2025
Valid Until: 15 July 2025
Project Ref: KL-RES-2025-089
CLIENT INFORMATION
Prepared For
Name: Tan Wei Keat
Company: Sinar Property Holdings Sdn. Bhd.
Address: Unit 21-03, The Exchange TRX, Jalan P. Ramlee, 50250 Kuala Lumpur, Malaysia
Contact: +6012-345 6789
Email: tanwk@sinarproperty.com.my
Project Details
Project Title: Sinar Residences – Mixed-Use Development
Location: Jalan Ampang, 50450 Kuala Lumpur, Malaysia
Site Area: 4,200 sqm
Gross Floor Area: 28,500 sqm
Building Type: 18-storey mixed-use (retail + residential)
SCOPE OF ARCHITECT SERVICES
This Quotation Estimate is issued by Meridian Architectural Design Sdn. Bhd. to outline the professional Architect services to be rendered for the Sinar Residences project located in Malaysia Kuala Lumpur. The scope encompasses all phases of architectural design and documentation in compliance with the Uniform Building By-Laws (UBBL), the Building Act 1984, and the Kuala Lumpur City Hall (DBKL) planning guidelines. Our Architect team, led by a Registered Architect with the Board of Architects Malaysia, will provide comprehensive design, development, and construction supervision services throughout the project lifecycle in Malaysia Kuala Lumpur.
ITEMISED COST BREAKDOWN
	No.
	Description of Architect Services
	Phase / Duration
	Unit
	Rate (RM)
	Amount (RM)

	1
	Pre-Design & Feasibility Study – Site analysis, zoning assessment, concept development, and preliminary massing studies for the Architect design in Malaysia Kuala Lumpur
	Phase 1 (4 weeks)
	Lump Sum
	—
	45,000.00

	2
	Schematic Design – Development of architectural concept, 3D visualisations, material palette, and spatial planning for all 18 storeys
	Phase 2 (6 weeks)
	Lump Sum
	—
	120,000.00

	3
	Design Development – Detailed architectural drawings, structural coordination, MEP integration, and DBKL submission preparation
	Phase 3 (8 weeks)
	Lump Sum
	—
	185,000.00

	4
	Tender Documentation – Full set of architectural tender drawings, specifications, BOQ coordination, and contractor query management
	Phase 4 (6 weeks)
	Lump Sum
	—
	95,000.00

	5
	Construction Administration & Supervision – Site inspections, progress monitoring, variation order assessment, and as-built documentation
	Phase 5 (24 months)
	Monthly
	18,500.00
	444,000.00

	6
	DBKL Planning & Building Permit Application – Preparation and submission of all statutory drawings, coordination with Malaysia Kuala Lumpur City Hall, and follow-up until approval
	As required
	Lump Sum
	—
	38,000.00

	7
	Interior Design Coordination – Architectural interface with interior design for lobby, common areas, and unit layouts
	Phase 2–4
	Lump Sum
	—
	65,000.00

	8
	Landscape & External Works Design – Garden areas, podium landscaping, and external circulation design compliant with DBKL open space requirements
	Phase 2–4
	Lump Sum
	—
	42,000.00

	9
	Post-Occupancy Evaluation & Handover – Final inspection, snag list resolution, and 12-month post-completion support
	Post-completion
	Lump Sum
	—
	28,000.00

	SUBTOTAL
	RM 1,062,000.00

	Sales & Service Tax (SST) @ 6%
	RM 63,720.00

	GRAND TOTAL (INCL. SST)
	RM 1,125,720.00


TERMS AND CONDITIONS
1. This Quotation Estimate is valid for thirty (30) days from the date of issue. Beyond this period, the Architect fees and rates may be subject to revision based on prevailing market conditions in Malaysia Kuala Lumpur.
1. Payment shall be made in accordance with the following schedule: 30% advance payment upon execution of the Professional Services Agreement; 20% upon completion of Schematic Design; 20% upon completion of Design Development; 15% upon completion of Tender Documentation; and the remaining 15% to be paid monthly during the Construction Administration phase.
1. All payments are due within fourteen (14) calendar days from the date of invoice. Late payments shall attract interest at the rate of 5% per annum, in accordance with the Late Payment of Outstanding Claims Act 2017 applicable in Malaysia Kuala Lumpur.
1. The Architect shall not be liable for delays caused by the client, statutory authorities (including DBKL), or force majeure events. Any extension of the project timeline shall be assessed on a case-by-case basis.
1. All architectural drawings, 3D models, and design documents produced under this engagement remain the intellectual property of Meridian Architectural Design Sdn. Bhd. until full payment is received. Upon full settlement, the client shall receive a non-exclusive licence to use the documents for the specific project in Malaysia Kuala Lumpur.
1. Any variations or additional scope of work beyond the original Quotation Estimate shall be subject to a separate written agreement and additional fees as determined by the Architect.
1. This Quotation Estimate does not include costs for structural engineering, geotechnical investigation, environmental impact assessment, or specialist consultancy fees, which shall be engaged separately by the client.
1. All services shall be performed in compliance with the Professional Conduct Rules of the Board of Architects Malaysia and the applicable building regulations of the Federal Territory of Kuala Lumpur.
1. Disputes arising from this engagement shall be resolved through mediation in Malaysia Kuala Lumpur in accordance with the Mediation Act 2012, failing which, the courts of Malaysia Kuala Lumpur shall have exclusive jurisdiction.
ACCEPTANCE
By signing below, the client acknowledges and accepts this Quotation Estimate for Architect services in Malaysia Kuala Lumpur as set out herein. This acceptance shall constitute a binding agreement between both parties subject to the terms and conditions stated above.
For and on behalf of Meridian Architectural Design Sdn. Bhd.
Name: Datuk Ir. Ahmad Faizal bin Hassan
Designation: Principal Architect (ABM Reg. A-2015-0892)
Date: _______________
For and on behalf of Sinar Property Holdings Sdn. Bhd.
Name: Tan Wei Keat
Designation: Managing Director
Date: _______________
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