Quotation Estimate - Architect Services - Netherlands Amsterdam
QUOTATION ESTIMATE
Architectural Design & Consultation Services
Amsterdam, Netherlands
Reference No: QTE-AMS-2025-04782 | Date: 14 June 2025
Prepared By (Architect)
Studio Van der Berg Architecten B.V.
Herengracht 412, 1017 BX Amsterdam
The Netherlands
Tel: +31 (0)20 555 0187
Email: info@vandenbergarchitecten.nl
KvK: 64281937 | BTW: NL861234567B01
Prepared For (Client)
Mr. J. de Vries
Keizersgracht 287, 1016 DS Amsterdam
The Netherlands
Tel: +31 (0)6 1234 5678
Email: j.devries@clientmail.nl
BSN: 1234.56.789
Project Description
This Quotation Estimate is issued by Studio Van der Berg Architecten B.V., a registered Architect practice operating in Netherlands Amsterdam, in response to the client's request for comprehensive architectural design services for a residential renovation and extension project located at Keizersgracht 287, Amsterdam, The Netherlands. The Architect firm has assessed the site, reviewed the existing structural condition, and prepared this detailed Quotation Estimate to outline all professional services, associated costs, and project milestones. All work will be conducted in full compliance with the Dutch Building Act (Bouwbesluit 2012), the Amsterdam Municipal Building Regulations (Bouwverordening Amsterdam), and applicable European Union directives governing architectural practice in the Netherlands Amsterdam metropolitan area.
Scope of Architect Services
The Architect engagement encompasses the following phases of professional service, each contributing to the overall Quotation Estimate presented herein:
· Phase 1 – Feasibility Study & Site Analysis: The Architect will conduct a thorough assessment of the existing property in Netherlands Amsterdam, including structural survey, soil condition review, heritage designation check (Rijksdienst voor het Cultureel Erfgoed), and zoning verification with the Amsterdam municipal planning department.
· Phase 2 – Concept Design: Development of initial architectural concepts, massing studies, and spatial planning proposals. The Architect will present three distinct design options for client review and selection.
· Phase 3 – Detailed Design & Technical Drawings: Production of full construction drawings, structural coordination, MEP (mechanical, electrical, plumbing) integration, and material specifications in accordance with Dutch NEN standards.
· Phase 4 – Permit Application (Omgevingsvergunning): The Architect will prepare and submit the complete building permit application to the Amsterdam municipality, including all required documentation, environmental impact assessments, and heritage impact statements specific to the protected canal district in Netherlands Amsterdam.
· Phase 5 – Tender & Contractor Coordination: Assistance in preparing tender documents, evaluating contractor bids, and facilitating the selection of a main contractor for construction execution.
· Phase 6 – Construction Supervision (Bouwtoezicht): The Architect will provide on-site supervision, quality control, and progress monitoring throughout the construction period to ensure compliance with the approved design and Dutch building regulations.
Itemized Quotation Estimate Breakdown
	Item No.
	Description of Architect Service
	Duration
	Rate (EUR)
	Amount (EUR)

	01
	Feasibility Study & Site Analysis (Architect)
	3 weeks
	185.00/hr
	4,440.00

	02
	Concept Design Development (3 options)
	6 weeks
	165.00/hr
	12,540.00

	03
	Detailed Design & Technical Drawings
	10 weeks
	155.00/hr
	24,800.00

	04
	Permit Application Preparation & Submission
	4 weeks
	145.00/hr
	9,280.00

	05
	Tender Documentation & Contractor Coordination
	3 weeks
	145.00/hr
	5,520.00

	06
	Construction Supervision (Bouwtoezicht)
	26 weeks
	135.00/hr
	35,100.00

	07
	3D Visualisation & VR Presentation Package
	2 weeks
	Flat fee
	3,800.00

	08
	Heritage Consultation & Municipal Liaison
	3 weeks
	175.00/hr
	4,200.00

	09
	Project Management & Client Communication
	Full term
	Flat fee
	6,500.00

	10
	Travel & Local Site Visits within Amsterdam
	Full term
	Flat fee
	1,200.00

	Subtotal (Excluding BTW/VAT)
	107,380.00

	BTW / VAT (21% – Netherlands Standard Rate)
	22,549.80

	TOTAL QUOTATION ESTIMATE (Incl. BTW)
	129,929.80


Payment Schedule
This Quotation Estimate stipulates the following payment milestones, payable within 30 days of invoice issuance by the Architect:
· 20% upon acceptance of this Quotation Estimate and signing of the Architect's engagement contract.
· 25% upon completion and approval of the Concept Design phase.
· 25% upon submission of the building permit application to the Amsterdam municipality.
· 20% upon commencement of construction works on site.
· 10% upon final handover, completion of as-built drawings, and issuance of the completion certificate (gebruiksklaarverklaring).
Terms and Conditions
1. This Quotation Estimate is valid for a period of sixty (60) calendar days from the date of issue. After this period, the Architect reserves the right to revise rates due to market fluctuations in the Netherlands Amsterdam construction sector.
1. All services rendered by the Architect are governed by the Dutch Civil Code (Burgerlijk Wetboek) Book 7, Section 9 (Aanneming van werk) and the SRA (Stichting Regeling Architecten) standard terms of engagement.
1. The Architect shall carry out all professional services with due diligence, in accordance with the standards of practice established by the Royal Dutch Association of Architects (RAI) and the professional code of conduct applicable in the Netherlands Amsterdam region.
1. Any changes to the scope of work beyond the parameters described in this Quotation Estimate will be subject to a supplementary Quotation Estimate and written client approval prior to execution.
1. The Architect maintains professional indemnity insurance with a minimum coverage of EUR 2,500,000 per claim, as required for registered architectural practices in the Netherlands.
1. All intellectual property rights in design documents, drawings, and 3D models produced by the Architect remain with Studio Van der Berg Architecten B.V. until full payment of the total Quotation Estimate amount has been received.
1. Disputes arising from this engagement shall be resolved through mediation in accordance with the SRA mediation procedure, with jurisdiction vested in the District Court of Amsterdam, The Netherlands.
1. This Quotation Estimate does not constitute a binding contract until countersigned by both parties and accompanied by the execution of the formal Architect's engagement agreement.
Acceptance and Signatures
By signing below, both parties acknowledge that this Quotation Estimate for Architect services in Netherlands Amsterdam has been reviewed, understood, and accepted in its entirety.
For and on behalf of the Architect:
Studio Van der Berg Architecten B.V.
Name: Ir. M. van der Berg, RAI
Signature: ___________________________
Date: ___________________________
For and on behalf of the Client:
Mr. J. de Vries
Name: ___________________________
Signature: ___________________________
Date: ___________________________
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