# Quotation Estimate - Architect Services - Nigeria Abuja

# Quotation Estimate

Professional Architect Services

Abuja, Nigeria

### From (Architect Firm)

Meridian Architectural Design Studio

Plot 14, Zone 6, Maitama District

Abuja, FCT, Nigeria

Tel: +234 (0) 803 555 7214

Email: enquiries@meridianarch.ng

RC No: 1284576 | ARCON Reg: ARCON/ABJ/2019/00432

### To (Client)

Mr. Chukwuma O. Adeyemi

22, Asokoro Close, Asokoro

Abuja, FCT, Nigeria

Tel: +234 (0) 812 334 9987

Email: c.adeyemi@email.com

Quotation Estimate No: MA/ABJ/2025/00387

Date of Issue: 12 June 2025

Project Location: Gwarinpa, Abuja, FCT, Nigeria

Project Type: Residential Duplex with BQ (4 Bedrooms + Self-Contained)

Validity Period: 30 days from date of issue

Currency: Nigerian Naira (NGN)

## 1. Scope of Architect Services

This Quotation Estimate is issued by Meridian Architectural Design Studio, a licensed Architect firm registered with the Architects Registration Council of Nigeria (ARCON), to provide comprehensive architectural design and consultancy services for the construction of a four-bedroom duplex with a boys' quarters (BQ) located in Gwarinpa, Nigeria Abuja. The scope of work encompasses all phases of architectural design from conceptual development through to construction supervision, in full compliance with the Abuja Capital Territory (ACT) Building Control and Planning Regulations and the Federal Capital Territory (FCT) Development Plan.

## 2. Itemized Cost Breakdown

| S/N | Description of Architect Service | Duration | Unit Cost (NGN) | Total (NGN) |
| --- | --- | --- | --- | --- |
| 1 | Site survey, topographical assessment, and feasibility study at the Gwarinpa plot, Abuja | 2 weeks | ₦450,000 | ₦450,000 |
| 2 | Conceptual design development including 3D visualisations, floor plans, and elevation sketches | 4 weeks | ₦1,200,000 | ₦1,200,000 |
| 3 | Preparation of full architectural working drawings (plans, sections, elevations, details) for submission to FCT Ministry of Works | 6 weeks | ₦1,850,000 | ₦1,850,000 |
| 4 | Structural and MEP (Mechanical, Electrical, Plumbing) coordination drawings in collaboration with allied consultants | 4 weeks | ₦950,000 | ₦950,000 |
| 5 | Bill of Quantities (BOQ) preparation and cost estimation for tendering purposes | 3 weeks | ₦750,000 | ₦750,000 |
| 6 | Permit application support and liaison with Abuja FCT Building Control Department | 4 weeks | ₦600,000 | ₦600,000 |
| 7 | Construction phase supervision and site visits (minimum 2 visits per week for 12 months) | 12 months | ₦3,500,000 | ₦3,500,000 |
| 8 | Interior design concept and furniture layout plan for all rooms | 3 weeks | ₦800,000 | ₦800,000 |
| 9 | Landscaping and external works design (garden, driveway, boundary wall) | 2 weeks | ₦550,000 | ₦550,000 |
| 10 | As-built documentation and final handover report | 2 weeks | ₦400,000 | ₦400,000 |
| SUBTOTAL |  |  |  | ₦11,050,000 |
| VAT (7.5% as applicable in Nigeria) |  |  |  | ₦828,750 |
| GRAND TOTAL (Quotation Estimate Amount) |  |  |  | ₦11,878,750 |

* All prices are quoted in Nigerian Naira (NGN). VAT is applied in accordance with the Federal Inland Revenue Service (FIRS) guidelines applicable in Nigeria Abuja.

## 3. Payment Terms

The total Quotation Estimate amount of ₦11,878,750 shall be paid in the following instalments:

| Milestone | Percentage | Amount (NGN) |
| --- | --- | --- |
| Upon signing of engagement letter | 30% | ₦3,563,625 |
| Upon approval of conceptual design | 20% | ₦2,375,750 |
| Upon submission of working drawings | 20% | ₦2,375,750 |
| Upon commencement of construction supervision | 15% | ₦1,781,813 |
| Upon project completion and handover | 15% | ₦1,781,813 |

## 4. Terms and Conditions

- This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Beyond this period, the Architect reserves the right to revise pricing due to market fluctuations in Nigeria Abuja.

- All architectural drawings and design documents remain the intellectual property of Meridian Architectural Design Studio until full payment of the Quotation Estimate amount is received.

- The Architect shall comply with all applicable building codes, the FCT Development Plan, and the Abuja Building Control and Planning Regulations throughout the project lifecycle.

- Any additional services or design revisions beyond the agreed scope shall be subject to a separate supplementary Quotation Estimate and mutual written agreement.

- Payment shall be made via bank transfer to the firm's designated account. No cash payments shall be accepted for amounts exceeding ₦500,000.

- The Architect is not liable for delays caused by the client, government agencies in Nigeria Abuja, or force majeure events including but not limited to flooding, political instability, or regulatory changes.

- This engagement is governed by the laws of the Federal Republic of Nigeria, and any disputes shall be resolved through arbitration in Abuja, FCT.

- The Architect shall maintain professional indemnity insurance with a minimum cover of ₦50,000,000 for the duration of the project.

## 5. Acceptance

By signing below, the client acknowledges and accepts this Quotation Estimate for Architect services in Nigeria Abuja and agrees to the terms and conditions outlined herein.

For: Meridian Architectural Design Studio

Name: Engr. Amina B. Yusuf, R.Arch.

Title: Principal Architect

Signature: _________________________

Date: _________________________

For: Client

Name: Mr. Chukwuma O. Adeyemi

Title: Project Owner

Signature: _________________________

Date: _________________________

Meridian Architectural Design Studio | Plot 14, Zone 6, Maitama, Abuja, FCT, Nigeria

Registered with ARCON | RC 1284576 | This Quotation Estimate is generated electronically and is valid without a physical stamp.

© 2025 Meridian Architectural Design Studio. All Rights Reserved.