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Quotation Estimate
Professional Architect Services
Abuja, Nigeria
From (Architect Firm)
Meridian Architectural Design Studio
Plot 14, Zone 6, Maitama District
Abuja, FCT, Nigeria
Tel: +234 (0) 803 555 7214
Email: enquiries@meridianarch.ng
RC No: 1284576 | ARCON Reg: ARCON/ABJ/2019/00432
To (Client)
Mr. Chukwuma O. Adeyemi
22, Asokoro Close, Asokoro
Abuja, FCT, Nigeria
Tel: +234 (0) 812 334 9987
Email: c.adeyemi@email.com
Quotation Estimate No: MA/ABJ/2025/00387
Date of Issue: 12 June 2025
Project Location: Gwarinpa, Abuja, FCT, Nigeria
Project Type: Residential Duplex with BQ (4 Bedrooms + Self-Contained)
Validity Period: 30 days from date of issue
Currency: Nigerian Naira (NGN)
1. Scope of Architect Services
This Quotation Estimate is issued by Meridian Architectural Design Studio, a licensed Architect firm registered with the Architects Registration Council of Nigeria (ARCON), to provide comprehensive architectural design and consultancy services for the construction of a four-bedroom duplex with a boys' quarters (BQ) located in Gwarinpa, Nigeria Abuja. The scope of work encompasses all phases of architectural design from conceptual development through to construction supervision, in full compliance with the Abuja Capital Territory (ACT) Building Control and Planning Regulations and the Federal Capital Territory (FCT) Development Plan.
2. Itemized Cost Breakdown
	S/N
	Description of Architect Service
	Duration
	Unit Cost (NGN)
	Total (NGN)

	1
	Site survey, topographical assessment, and feasibility study at the Gwarinpa plot, Abuja
	2 weeks
	₦450,000
	₦450,000

	2
	Conceptual design development including 3D visualisations, floor plans, and elevation sketches
	4 weeks
	₦1,200,000
	₦1,200,000

	3
	Preparation of full architectural working drawings (plans, sections, elevations, details) for submission to FCT Ministry of Works
	6 weeks
	₦1,850,000
	₦1,850,000

	4
	Structural and MEP (Mechanical, Electrical, Plumbing) coordination drawings in collaboration with allied consultants
	4 weeks
	₦950,000
	₦950,000

	5
	Bill of Quantities (BOQ) preparation and cost estimation for tendering purposes
	3 weeks
	₦750,000
	₦750,000

	6
	Permit application support and liaison with Abuja FCT Building Control Department
	4 weeks
	₦600,000
	₦600,000

	7
	Construction phase supervision and site visits (minimum 2 visits per week for 12 months)
	12 months
	₦3,500,000
	₦3,500,000

	8
	Interior design concept and furniture layout plan for all rooms
	3 weeks
	₦800,000
	₦800,000

	9
	Landscaping and external works design (garden, driveway, boundary wall)
	2 weeks
	₦550,000
	₦550,000

	10
	As-built documentation and final handover report
	2 weeks
	₦400,000
	₦400,000

	SUBTOTAL
	₦11,050,000

	VAT (7.5% as applicable in Nigeria)
	₦828,750

	GRAND TOTAL (Quotation Estimate Amount)
	₦11,878,750


* All prices are quoted in Nigerian Naira (NGN). VAT is applied in accordance with the Federal Inland Revenue Service (FIRS) guidelines applicable in Nigeria Abuja.
3. Payment Terms
The total Quotation Estimate amount of ₦11,878,750 shall be paid in the following instalments:
	Milestone
	Percentage
	Amount (NGN)

	Upon signing of engagement letter
	30%
	₦3,563,625

	Upon approval of conceptual design
	20%
	₦2,375,750

	Upon submission of working drawings
	20%
	₦2,375,750

	Upon commencement of construction supervision
	15%
	₦1,781,813

	Upon project completion and handover
	15%
	₦1,781,813


4. Terms and Conditions
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Beyond this period, the Architect reserves the right to revise pricing due to market fluctuations in Nigeria Abuja.
1. All architectural drawings and design documents remain the intellectual property of Meridian Architectural Design Studio until full payment of the Quotation Estimate amount is received.
1. The Architect shall comply with all applicable building codes, the FCT Development Plan, and the Abuja Building Control and Planning Regulations throughout the project lifecycle.
1. Any additional services or design revisions beyond the agreed scope shall be subject to a separate supplementary Quotation Estimate and mutual written agreement.
1. Payment shall be made via bank transfer to the firm's designated account. No cash payments shall be accepted for amounts exceeding ₦500,000.
1. The Architect is not liable for delays caused by the client, government agencies in Nigeria Abuja, or force majeure events including but not limited to flooding, political instability, or regulatory changes.
1. This engagement is governed by the laws of the Federal Republic of Nigeria, and any disputes shall be resolved through arbitration in Abuja, FCT.
1. The Architect shall maintain professional indemnity insurance with a minimum cover of ₦50,000,000 for the duration of the project.
5. Acceptance
By signing below, the client acknowledges and accepts this Quotation Estimate for Architect services in Nigeria Abuja and agrees to the terms and conditions outlined herein.
For: Meridian Architectural Design Studio
Name: Engr. Amina B. Yusuf, R.Arch.
Title: Principal Architect
Signature: _________________________
Date: _________________________
For: Client
Name: Mr. Chukwuma O. Adeyemi
Title: Project Owner
Signature: _________________________
Date: _________________________
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