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1. Client Information
	Field
	Details

	Client Name
	Seoul Metropolitan Development Corp.

	Representative
	Mr. Park Ji-hoon, Chief Project Officer

	Client Address
	45, Teheran-ro, Gangnam-gu, Seoul, South Korea

	Project Location
	Mapo-gu District, Seoul, South Korea

	Project Type
	Residential & Mixed-Use Complex (12 Storeys)


2. Scope of Architect Services
This Quotation Estimate is issued by Han River Architectural Studio in response to the formal request from Seoul Metropolitan Development Corp. for comprehensive Architect services for the proposed residential and mixed-use development project located in Mapo-gu, Seoul, South Korea. The scope of work encompasses all phases of architectural design, regulatory compliance, and construction documentation required under the Building Act of the Republic of Korea and the Seoul Metropolitan Government Building Standards.
The Architect team will be led by a licensed Architect registered with the Korea Institute of Architects (KIA) and will coordinate with structural engineers, MEP consultants, landscape designers, and interior specialists as required for the full delivery of the project in South Korea Seoul.
3. Itemized Cost Breakdown
	No.
	Service / Deliverable
	Duration
	Unit
	Rate (KRW)
	Amount (KRW)

	1
	Feasibility Study & Site Analysis (Seoul zoning, topography, environmental assessment)
	4 weeks
	Lump Sum
	—
	18,500,000

	2
	Concept Design & Schematic Design (3D massing, material palette, urban context study)
	8 weeks
	Lump Sum
	—
	42,000,000

	3
	Detailed Design & Construction Drawings (full set per Seoul Building Code)
	12 weeks
	Lump Sum
	—
	68,000,000

	4
	Permit Application & Regulatory Liaison (Seoul City Hall, Mapo-gu Office)
	6 weeks
	Lump Sum
	—
	22,000,000

	5
	Construction Phase Architect Supervision & Site Visits
	18 months
	Monthly
	8,500,000
	153,000,000

	6
	Interior Design Coordination & FF&E Specification
	10 weeks
	Lump Sum
	—
	35,000,000

	7
	Landscape & Exterior Environment Design (Seoul climate-responsive)
	6 weeks
	Lump Sum
	—
	28,000,000

	8
	As-Built Documentation & Handover Package
	4 weeks
	Lump Sum
	—
	12,000,000

	Subtotal (KRW)
	378,500,000

	VAT (10% — South Korea Standard Rate)
	37,850,000

	TOTAL QUOTATION ESTIMATE (KRW)
	416,350,000


* All amounts are denominated in Korean Won (KRW). Exchange rate reference at time of issue: 1 USD ≈ 1,340 KRW. Final settlement shall be in KRW via bank transfer to the account specified in Section 6.
4. Payment Schedule
	Milestone
	Percentage
	Amount (KRW)
	Trigger

	Contract Signing
	15%
	62,452,500
	Upon execution of Architect Services Agreement

	Concept Design Approval
	20%
	83,270,000
	Client written approval of Schematic Design

	Construction Drawings Issued
	25%
	104,087,500
	Submission of full drawing set to Seoul permitting authority

	Construction Phase (Monthly)
	35%
	145,722,500
	18 monthly installments during construction

	Project Handover
	5%
	20,817,500
	Final As-Built documentation delivery


5. Terms & Conditions
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiry date, all rates and conditions are subject to revision without prior notice.
1. The Architect services described herein are governed by the laws of the Republic of Korea, specifically the Architect Act (건축사법) and the Seoul Metropolitan Government regulations on building design and construction.
1. All intellectual property rights in design documents, drawings, 3D models, and specifications produced by the Architect remain the property of Han River Architectural Studio until full payment is received. Upon final settlement, the client receives a perpetual, non-exclusive license to use the documents for the specific project in South Korea Seoul.
1. Any changes to the scope of work, additional storeys, alterations to the building footprint, or changes in the project location within Seoul shall be subject to a supplementary Quotation Estimate issued by the Architect prior to commencement of the additional work.
1. The Architect shall maintain professional indemnity insurance with a minimum coverage of KRW 500,000,000 throughout the duration of the engagement.
1. Disputes arising from this Quotation Estimate or the subsequent Architect Services Agreement shall be resolved through mediation under the Korea Construction Dispute Mediation Center, and failing that, by arbitration in Seoul, South Korea.
1. The Architect reserves the right to decline or withdraw from this Quotation Estimate if the project site is found to be subject to unresolved land-use restrictions, heritage preservation orders, or environmental contamination disclosures not previously communicated by the client.
1. All communications, approvals, and change orders must be in writing (email acceptable) and signed by the authorized representative of the client.
6. Bank & Remittance Details
	Account Holder
	Han River Architectural Studio Co., Ltd.

	Bank
	Industrial Bank of Korea (IBK), Seoul Central Branch

	Account No.
	010-123-456789

	SWIFT Code
	IBKOKRSE


For and on behalf of
Han River Architectural Studio Co., Ltd.
Name: Kim Soo-yeon, Principal Architect (KIA Reg. No. 2019-04521)
Signature & Company Seal
Accepted by (Client)
Seoul Metropolitan Development Corp.
Name: Park Ji-hoon, Chief Project Officer
Signature & Company Seal
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