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P.O. Box 7832, Dar es Salaam, Tanzania
Tel: +255 22 255 8901
Email: procurement@mwamaholdings.co.tz
	Quotation Reference No.:
	SCA/QE/2025/0042

	Date of Issue:
	14 June 2025

	Project Location:
	Msasani Peninsula, Tanzania Dar es Salaam

	Project Description:
	Design and Architectural Supervision of a 6-Storey Mixed-Use Commercial and Residential Building

	Quotation Validity:
	60 days from date of issue

	Currency:
	Tanzanian Shillings (TZS)


1. Introduction and Purpose of This Quotation Estimate
This Quotation Estimate is issued by Swahili Coast Architects Ltd., a registered and licensed Architect practice operating in Tanzania Dar es Salaam, in response to the formal request for architectural design and supervision services submitted by Mwamba Holdings (T) Ltd. This document outlines the complete scope of professional Architect services to be delivered, the itemized cost breakdown, payment schedule, and all applicable terms governing the engagement. All pricing in this Quotation Estimate reflects current market rates for Architect professional services in Tanzania Dar es Salaam as of the date of issue and is subject to the validity period stated above.
2. Scope of Architect Services
The Architect team engaged under this Quotation Estimate shall provide the following comprehensive services for the proposed development in Tanzania Dar es Salaam:
· Concept Design and Feasibility Study: Preparation of initial concept drawings, massing studies, and a feasibility report aligned with the Tanzania Building Regulations and the Dar es Salaam City Council zoning requirements for the Msasani Peninsula area.
· Pre-Design and Schematic Design: Development of schematic architectural drawings including floor plans, elevations, sections, and 3D visualizations for client review and approval.
· Design Development: Detailed architectural design incorporating structural coordination, mechanical and electrical planning, and compliance with the Tanzania National Building Code and local by-laws applicable in Dar es Salaam.
· Construction Documentation: Production of full construction drawings, specifications, and bill of quantities to enable competitive tendering by the client's contractor in Tanzania Dar es Salaam.
· Tender and Procurement Support: Assistance in preparing tender documents, evaluating contractor submissions, and advising on contract selection for the construction phase.
· Construction Phase Architect Supervision: On-site architectural supervision, progress inspections, design queries resolution, and certification of completed works in accordance with Tanzanian building standards.
· Statutory Approvals and Permits: Preparation and submission of all necessary documentation to the Dar es Salaam City Council, the Tanzania Building Authority, and other relevant regulatory bodies to obtain building permits and occupancy certificates.
· As-Built Documentation: Preparation of final as-built drawings and project handover documentation upon completion of the construction works.
3. Itemized Cost Breakdown
	Item No.
	Description of Architect Service
	Duration
	Cost (TZS)

	1
	Concept Design, Feasibility Study & Site Analysis in Tanzania Dar es Salaam
	4 weeks
	18,500,000

	2
	Schematic Design & 3D Visualization Package
	6 weeks
	32,000,000

	3
	Design Development & Multi-Disciplinary Coordination
	8 weeks
	45,000,000

	4
	Construction Documentation & Specifications
	10 weeks
	58,000,000

	5
	Tender Support & Contractor Evaluation
	4 weeks
	12,500,000

	6
	Construction Phase Architect Supervision (18 months)
	18 months
	95,000,000

	7
	Statutory Approvals, Permits & Regulatory Compliance (Dar es Salaam)
	6 weeks
	8,500,000

	8
	As-Built Documentation & Project Handover
	4 weeks
	7,500,000

	9
	Travel, Site Visits & Local Transportation within Tanzania Dar es Salaam
	Entire project
	6,000,000

	10
	Contingency for Design Revisions (up to 3 major iterations)
	Entire project
	10,000,000

	Subtotal (TZS)
	293,000,000

	VAT @ 18% (Tanzania)
	52,740,000

	TOTAL QUOTATION ESTIMATE (TZS)
	345,740,000


4. Payment Schedule
Payment for the Architect services detailed in this Quotation Estimate shall be made in the following installments, invoiced upon completion of each milestone:
· 20% (TZS 69,148,000) — Upon signing of the professional services agreement and commencement of the concept design phase.
· 25% (TZS 86,435,000) — Upon approval of the schematic design and design development package.
· 25% (TZS 86,435,000) — Upon submission of complete construction documentation and tender support.
· 20% (TZS 69,148,000) — Upon completion of construction phase Architect supervision and issuance of the certificate of practical completion.
· 10% (TZS 34,574,000) — Upon delivery of as-built documentation and final project handover.
5. Terms and Conditions
1. This Quotation Estimate is valid for a period of sixty (60) calendar days from the date of issue. Beyond this period, the Architect firm reserves the right to revise pricing due to market fluctuations in Tanzania Dar es Salaam.
1. All fees stated in this Quotation Estimate are exclusive of Value Added Tax (VAT) at the prevailing Tanzanian rate of 18%, which shall be added to each invoice.
1. The Architect shall not be liable for delays caused by the client, third-party contractors, or regulatory authorities in Tanzania Dar es Salaam beyond the reasonable control of the Architect team.
1. Any additional design revisions beyond the three (3) major iterations included in this Quotation Estimate shall be charged at a rate of TZS 2,500,000 per revision day.
1. All intellectual property rights in the architectural designs, drawings, and documentation produced under this engagement shall vest in the client upon full and final payment of all fees.
1. This Quotation Estimate does not constitute a binding contract. A formal Professional Services Agreement, governed by the laws of the United Republic of Tanzania, shall be executed prior to commencement of work.
1. Disputes arising from this engagement shall be resolved through arbitration in Dar es Salaam, Tanzania, in accordance with the Arbitration Act of Tanzania.
1. The Architect firm maintains professional indemnity insurance with a coverage of not less than TZS 500,000,000, valid throughout the duration of the project.
6. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate for Architect services in Tanzania Dar es Salaam and agrees to the terms, conditions, and pricing outlined herein. This acceptance shall serve as the basis for the preparation of the formal Professional Services Agreement.
For and on behalf of Swahili Coast Architects Ltd. (Architect)
Eng. Amina J. Mwakalinga
Principal Architect, RIBA / ARB Registered
License No: TZ/ARC/LIC/2020/0112
Date: ______________________
For and on behalf of Mwamba Holdings (T) Ltd. (Client)
Mr. Joseph K. Mushi
Managing Director
Date: ______________________
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