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Quotation Estimate
Professional Architect Services — Thailand Bangkok
Ref: QTE-BKK-2025-0472
Architect Firm (Provider)
Chulalongkorn Architectural Design Studio Co., Ltd.
128 Sukhumvit Road, Khlong Toei
Bangkok 10110, Thailand
Tel: +66 (0) 2 255 8800
Email: estimates@chulaarch-bkk.co.th
Architect License No: TH-ARC-2019-004521
Client / Project Owner
Mr. Somchai Prasert
45/12 Ratchaprasong Avenue, Pathum Wan
Bangkok 10330, Thailand
Tel: +66 (0) 89 123 4567
Email: somchai.prasert@email.com
Quotation Details
Date of Issue: 15 June 2025
Quotation Valid Until: 15 July 2025 (30 days)
Currency: Thai Baht (THB)
Project Location
Site Address: 88/3 Sathorn Nuea Road
Yannawa, Sathon District
Bangkok 10120, Thailand
Plot Area: 420 sqm
1. Project Description & Scope of Architect Services
This Quotation Estimate is issued by Chulalongkorn Architectural Design Studio Co., Ltd., a licensed Architect firm registered under the Thai Ministry of Higher Education, Science, Research and Innovation, to provide comprehensive Architect services for the design and development of a mixed-use residential and commercial building located in the Sathon District of Thailand Bangkok. The proposed structure shall consist of a ground-floor retail space, four upper residential floors, and a rooftop terrace, in full compliance with the Bangkok Metropolitan Administration (BMA) building regulations and the National Building Code of Thailand.
2. Itemized Quotation Estimate Breakdown
	No.
	Description of Architect Service
	Duration
	Unit
	Amount (THB)

	1
	Pre-design consultation, site survey, and feasibility study in Thailand Bangkok
	2 weeks
	Lump Sum
	85,000

	2
	Concept design development including 3D massing studies and material palette
	4 weeks
	Lump Sum
	220,000

	3
	Schematic design package (floor plans, elevations, sections) for BMA submission
	6 weeks
	Lump Sum
	350,000

	4
	Detailed Architectural Design and construction drawing set (1:50, 1:100, 1:200 scales)
	8 weeks
	Lump Sum
	520,000

	5
	Structural, MEP, and landscape coordination drawings
	6 weeks
	Lump Sum
	280,000

	6
	Permit application support and liaison with Bangkok Metropolitan Administration
	4 weeks
	Lump Sum
	120,000

	7
	Construction-phase Architect supervision and site inspections (bi-weekly)
	12 months
	Monthly
	480,000

	8
	Interior design concept for ground-floor retail and rooftop terrace
	4 weeks
	Lump Sum
	195,000

	9
	As-built documentation and final handover package
	3 weeks
	Lump Sum
	95,000

	10
	Revisions (up to 3 rounds per design phase) and client presentation meetings
	Ongoing
	Included
	0

	Subtotal
	2,345,000

	VAT (7% as per Thai Revenue Code)
	164,150

	TOTAL QUOTATION ESTIMATE
	2,509,150


3. Payment Schedule
	Milestone
	Percentage
	Amount (THB)

	Upon signing of this Quotation Estimate and service agreement
	20%
	501,830

	Upon approval of Concept Design
	20%
	501,830

	Upon submission of full construction drawings to BMA
	25%
	627,288

	Monthly during construction supervision (12 installments)
	25%
	627,288

	Upon project completion and handover
	10%
	250,914


4. Terms and Conditions
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Any request for a revised Quotation Estimate after the expiry date shall be subject to re-evaluation of current Architect fee rates in Thailand Bangkok.
1. All Architect services described herein shall be performed in accordance with the Thai Building Control Act B.E. 2522 (1979) and all applicable Bangkok Metropolitan Administration zoning ordinances.
1. The Architect firm shall not be liable for delays caused by third-party contractors, government processing times at the BMA, or force majeure events including but not limited to flooding, which is a recognized risk in the Thailand Bangkok region.
1. Any additional design revisions beyond the three (3) included rounds per phase shall be billed at a rate of THB 3,500 per hour for the lead Architect and THB 1,800 per hour for supporting design staff.
1. Payment terms are net fifteen (15) days from the date of each invoice. Late payments shall accrue interest at 1.5% per month as stipulated under Thai commercial law.
1. All intellectual property, drawings, and design documents produced under this Quotation Estimate shall remain the property of the Architect firm until full payment has been received. Upon final settlement, the client shall receive a perpetual, non-exclusive license to use the designs for the specific project in Thailand Bangkok.
1. This Quotation Estimate does not include costs for soil testing, environmental impact assessments, or specialized engineering studies, which shall be quoted separately upon request.
1. Disputes arising from this Quotation Estimate shall be resolved through mediation under the Thai Arbitration Institute before any litigation in the Bangkok courts.
5. Acceptance and Authorization
By signing below, both parties acknowledge and agree to the terms, scope, and financial obligations outlined in this Quotation Estimate for Architect services in Thailand Bangkok. This document, once countersigned, constitutes a binding service agreement between the Architect firm and the Client.
For: Chulalongkorn Architectural Design Studio Co., Ltd.
Lead Architect & Managing Director
Arch. Nattapong Siriwat, R.A.
License No: TH-ARC-2019-004521
Date: _______________
For: Client / Project Owner
Authorized Signatory
Mr. Somchai Prasert
ID No: 7-1009-XXXXX-XX-X
Date: _______________
Important Notice: This Quotation Estimate is prepared exclusively for the project located in Thailand Bangkok as described herein. It is not transferable to any other site, jurisdiction, or project scope. All fees are quoted in Thai Baht (THB) and are subject to the prevailing VAT rate as determined by the Thai Department of Revenue. The Architect firm reserves the right to adjust rates should the project timeline extend beyond eighteen (18) months from the date of commencement. For inquiries regarding this Quotation Estimate, please contact our office at +66 (0) 2 255 8800 or estimates@chulaarch-bkk.co.th during business hours (Monday to Friday, 09:00–17:30 ICT).
