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1. Project Overview
This Quotation Estimate is issued by Al Noor Architectural Design Bureau LLC, a licensed Architect firm registered in the United Arab Emirates, to provide comprehensive architectural design and consultancy services for a residential villa project located in the Al Reem Island district, Abu Dhabi, United Arab Emirates. The proposed project encompasses a four-bedroom luxury villa with a total built-up area of approximately 4,200 square meters, including ground floor, first floor, and a rooftop terrace. The Architect will manage all phases of design from conceptual development through to construction documentation, ensuring full compliance with Abu Dhabi Municipality building codes, the Department of Municipalities and Transport (DMT) regulations, and all applicable United Arab Emirates federal standards.
2. Scope of Architect Services
The Architect services outlined in this Quotation Estimate include the following deliverables and professional engagements:
	No.
	Service Description
	Deliverables
	Duration
	Fee (AED)

	1
	Conceptual Design & Feasibility Study
	Site analysis, massing studies, 3D concept renders, preliminary floor plans
	4 weeks
	45,000.00

	2
	Schematic Design Development
	Detailed floor plans, elevations, sections, material palette, lighting concept
	5 weeks
	68,000.00

	3
	Design Development & Coordination
	Refined drawings, MEP coordination, structural input, landscape integration
	6 weeks
	82,000.00

	4
	Construction Documentation
	Full set of construction drawings, specifications, BOQ, tender documents
	8 weeks
	115,000.00

	5
	Authority Submissions & Approvals
	DMT/Abu Dhabi Municipality submissions, NOC coordination, revision management
	6 weeks
	38,000.00

	6
	Tender Support & Contractor Selection
	Tender document preparation, bid evaluation, contract administration support
	4 weeks
	32,000.00

	7
	Construction Phase Supervision
	Site inspections (bi-weekly), design queries, variation management, progress reports
	12 months
	145,000.00

	8
	As-Built Documentation & Handover
	As-built drawings, O&M manuals coordination, final compliance certificate
	4 weeks
	25,000.00

	Subtotal (AED)
	550,000.00

	VAT @ 5% (United Arab Emirates)
	27,500.00

	TOTAL AMOUNT DUE (AED)
	577,500.00


3. Payment Schedule
The total Quotation Estimate amount of AED 577,500.00 shall be disbursed according to the following milestone-based payment schedule, aligned with the Architect service phases:
	Milestone
	Percentage
	Amount (AED)
	Trigger

	Advance Payment
	20%
	115,500.00
	Upon signing of this Quotation Estimate

	Conceptual Design Approval
	15%
	86,625.00
	Client sign-off on concept

	Schematic Design Approval
	15%
	86,625.00
	Client sign-off on schematic

	Construction Docs & Approvals
	25%
	144,375.00
	DMT/Abu Dhabi Municipality approval

	Construction Supervision
	15%
	86,625.00
	Monthly pro-rata during build

	Project Handover
	10%
	57,750.00
	Final as-built submission


4. Terms and Conditions
1. This Quotation Estimate is valid for a period of thirty (30) calendar days from the date of issue. Beyond this period, the Architect reserves the right to revise fees due to market fluctuations in the United Arab Emirates construction sector.
1. All fees stated in this Quotation Estimate are exclusive of any third-party costs, including but not limited to Abu Dhabi Municipality submission fees, DMT permit charges, geotechnical survey costs, and environmental impact assessment fees, which shall be borne directly by the client.
1. The Architect shall not be liable for delays caused by authority review processes, force majeure events, or client-initiated design changes exceeding two (2) revision cycles per phase.
1. Any additional design revisions or scope changes beyond the agreed deliverables shall be subject to a separate supplementary Quotation Estimate issued by the Architect prior to commencement of additional work.
1. All intellectual property rights in the design documents, drawings, and 3D models produced by the Architect remain the property of Al Noor Architectural Design Bureau LLC until full payment of the Quotation Estimate amount is received.
1. Payment terms are Net 14 days from the date of invoice issuance. Late payments shall attract a penalty of 1.5% per month as per United Arab Emirates commercial law.
1. This Quotation Estimate is governed by the laws of the United Arab Emirates, and any disputes shall be resolved through arbitration in Abu Dhabi in accordance with the UAE Arbitration Law.
1. The Architect shall maintain professional indemnity insurance with a minimum coverage of AED 5,000,000 throughout the duration of the project.
1. All communications, submissions, and documentation shall be conducted in English, with Arabic translations provided where required by Abu Dhabi authorities.
Important Note: This Quotation Estimate assumes a standard residential villa typology. Should the project scope expand to include commercial elements, underground parking exceeding one level, or special heritage compliance requirements under Abu Dhabi's urban planning directives, the Architect will issue a revised Quotation Estimate reflecting the additional professional effort required.
5. Acceptance and Authorization
By signing below, both parties acknowledge and agree to the terms, conditions, and fee structure outlined in this Quotation Estimate for Architect services in Abu Dhabi, United Arab Emirates.
For: Al Noor Architectural Design Bureau LLC
Name: Eng. Sarah Al Falasi
Title: Principal Architect / Managing Director
Date: _________________________
For: Al Mansoori Real Estate Group
Name: Mr. Khalid Al Mansoori
Title: Director of Projects
Date: _________________________
Al Noor Architectural Design Bureau LLC — Licensed Architect Firm, Abu Dhabi, United Arab Emirates
Quotation Estimate No. QTE-2025-0347 | This document is confidential and intended solely for the named recipient.
Page 1 of 1
