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	Quotation Estimate No.
	QTE-2025-04871

	Date of Issue
	14 June 2025

	Valid Until
	14 July 2025 (30 calendar days)

	Prepared For (Client)
	Mr. Khalid Al Maktoum – Al Maktoum Development Group LLC

	Client Address
	Plot 47, Al Barsha 1, Dubai, United Arab Emirates

	Project Location
	Business Bay, Dubai, United Arab Emirates

	Project Description
	Design and Architectural Consultation for a 12-Storey Mixed-Use Commercial and Residential Tower

	Currency
	United Arab Emirates Dirham (AED)


1. Introduction and Scope of Architect Services
This Quotation Estimate is issued by Al Noor Architectural Design & Consultancy LLC (hereinafter referred to as "the Architect") in response to the formal request submitted by Al Maktoum Development Group LLC for comprehensive architectural design and consultancy services. The proposed Architect engagement covers the full lifecycle of design delivery for the aforementioned mixed-use tower located in Business Bay, United Arab Emirates Dubai, in strict compliance with the Dubai Municipality Building Regulations, the Dubai Urban Planning and Building Code, and all applicable federal and emirate-level statutory requirements of the United Arab Emirates.
The Architect team, led by a licensed Principal Architect registered with the Dubai Municipality and the UAE Council of Engineers, shall deliver concept design, schematic design, design development, construction documentation, and construction-phase architectural supervision. All deliverables shall be produced in accordance with the Royal Institute of British Architects (RIBA) Work Stages 0 through 7, adapted to the local practice standards of United Arab Emirates Dubai.
2. Itemised Cost Breakdown
	Ref.
	Description of Architect Service
	Duration
	Unit Rate (AED)
	Total (AED)

	01
	Feasibility Study & Site Analysis – Business Bay, Dubai, UAE
	3 weeks
	45,000
	45,000

	02
	Concept Design & Architectural Massing Studies (3D Visualisations)
	6 weeks
	185,000
	185,000

	03
	Schematic Design & Dubai Municipality Pre-Submission Review
	8 weeks
	275,000
	275,000

	04
	Design Development & MEP Coordination (Architect-led)
	10 weeks
	340,000
	340,000

	05
	Construction Documentation & Tender Drawings (Full Set)
	12 weeks
	420,000
	420,000

	06
	Authority Submissions – Dubai Municipality, DED, Civil Defence, RTA
	8 weeks
	95,000
	95,000

	07
	Construction Phase – Architectural Supervision & Site Visits (18 months)
	18 months
	68,000/mo
	1,224,000

	08
	As-Built Documentation & Handover Package
	4 weeks
	65,000
	65,000

	09
	Interior Design Coordination (Lobby, Amenities, 2 Sample Units)
	10 weeks
	150,000
	150,000

	10
	Project Management & Client Liaison (Architect's PM Role)
	Full duration
	35,000/mo
	630,000

	Subtotal (AED)
	3,429,000

	VAT @ 5% (United Arab Emirates)
	171,450

	GRAND TOTAL (AED)
	3,600,450


3. Payment Schedule
The Quotation Estimate payment structure is aligned with the RIBA Work Stage milestones and the standard practice for Architect engagements in United Arab Emirates Dubai:
· Milestone 1 (15%): Upon execution of the Architect's Services Agreement – AED 540,067.50
· Milestone 2 (20%): Upon approval of Schematic Design by the Client – AED 720,090.00
· Milestone 3 (25%): Upon submission of Construction Documentation to Dubai Municipality – AED 900,112.50
· Milestone 4 (25%): Upon receipt of No-Objection Certificate (NOC) from all UAE authorities – AED 900,112.50
· Milestone 5 (15%): Monthly during Construction Phase supervision – AED 540,067.50
4. Terms and Conditions
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Beyond this period, the Architect reserves the right to revise pricing due to market fluctuations in United Arab Emirates Dubai.
1. All fees are exclusive of third-party costs, including but not limited to Dubai Municipality plan-check fees, structural engineering, geotechnical surveys, and authority stamping charges, which shall be borne by the Client.
1. The Architect shall maintain professional indemnity insurance with a minimum cover of AED 10,000,000, as required by UAE regulations for registered architectural practices in Dubai.
1. Any variation in scope exceeding 10% of the original Quotation Estimate value shall be subject to a supplementary written agreement signed by both parties.
1. Intellectual property of all design documents, drawings, and 3D models produced by the Architect shall remain the property of Al Noor Architectural Design & Consultancy LLC until full payment is received.
1. This Quotation Estimate is governed by the laws of the United Arab Emirates, and any disputes shall be resolved through arbitration in Dubai under the DIFC-LCIA Arbitration Rules.
1. The Architect shall comply with all sustainability guidelines of the Dubai Green Building Regulations and the Estidama/Al Sa'fat rating system where applicable.
5. Acceptance
By signing below, the Client acknowledges and accepts this Quotation Estimate for Architect services in United Arab Emirates Dubai on the terms and conditions set forth herein.
For and on behalf of the Architect
Al Noor Architectural Design & Consultancy LLC
Name: Eng. Fatima Al Suwaidi
Title: Principal Architect / Managing Director
Date: _______________
For and on behalf of the Client
Al Maktoum Development Group LLC
Name: Mr. Khalid Al Maktoum
Title: Director of Projects
Date: _______________
This Quotation Estimate document is issued exclusively for the project referenced above in United Arab Emirates Dubai. It does not constitute a binding contract until formally executed as an Architect's Services Agreement. © 2025 Al Noor Architectural Design & Consultancy LLC. All rights reserved.
