Quotation Estimate - Biologist Services - Argentina Córdoba
Andes BioConsult S.R.L.
Professional Biological Consulting & Environmental Services
Av. Vélez Sarsfield 1245, Piso 8, Córdoba Capital, Provincia de Córdoba, Argentina
CUIT: 30-71234567-8 | Tel: +54 351 422-8890 | Email: consultas@andesbioconsult.com.ar
QUOTATION ESTIMATE
Quotation Details
Quotation No.: QE-2025-CBA-0472
Date of Issue: 14 June 2025
Valid Until: 14 July 2025 (30 calendar days)
Service Location: Argentina Córdoba Province
Currency: Argentine Peso (ARS)
Client Information
Company: Municipalidad de Córdoba – Dirección de Medio Ambiente
Contact Person: Ing. María Elena Rodríguez
Address: Av. Colón 1100, Córdoba Capital, Argentina
Email: m.rodriguez@cordoba.gob.ar
Reference: Licitación Pública N.º 2025-0387
Dear Ing. Rodríguez,
Thank you for the opportunity to submit this Quotation Estimate for the professional services of a certified Biologist to be deployed in the region of Argentina Córdoba. Andes BioConsult S.R.L. is pleased to present the following detailed proposal for your review and consideration. This Quotation Estimate has been prepared in accordance with the technical specifications outlined in your public tender and reflects our commitment to delivering high-quality biological and environmental expertise within the province of Córdoba, Argentina.
Our team of licensed Biologists specializes in ecological assessments, biodiversity monitoring, environmental impact studies, and conservation planning. The services described below are tailored specifically to the ecological conditions of Argentina Córdoba, encompassing the diverse biomes of the Sierras de Córdoba, the subtropical forests of the eastern valleys, the high-altitude ecosystems of the Calamuchita region, and the agricultural landscapes of the central plains.
Scope of Services – Biologist Professional Services in Argentina Córdoba
	Item
	Description of Service
	Duration
	Unit
	Unit Price (ARS)
	Total (ARS)

	01
	Field ecological survey and biodiversity inventory conducted by a senior Biologist across designated sites in Argentina Córdoba (Sierras Chicas, Valle de Traslasierra, and Calamuchita Valley). Includes species identification, habitat mapping, and photographic documentation.
	15 working days
	Day
	185,000
	2,775,000

	02
	Environmental Impact Assessment (EIA) preparation by a licensed Biologist for the proposed infrastructure project in the Córdoba Capital metropolitan area. Includes flora and fauna baseline data, mitigation strategies, and regulatory compliance review per Ley Nacional 25.675.
	30 working days
	Day
	210,000
	6,300,000

	03
	Water quality biological monitoring program in the Suquía River basin and tributaries within Argentina Córdoba. The Biologist will conduct macroinvertebrate sampling, algal bloom analysis, and bioindication index calculations on a monthly basis.
	6 months
	Month
	1,250,000
	7,500,000

	04
	Conservation planning and habitat restoration advisory. The Biologist will develop a 5-year action plan for the protection of native species (including the endangered Yaguareté and the Córdoba native oak) in designated protected areas of Argentina Córdoba.
	20 working days
	Day
	195,000
	3,900,000

	05
	Technical report writing, data analysis, and presentation of findings to the Dirección de Medio Ambiente. The Biologist will prepare a comprehensive final report in Spanish with English executive summary, including GIS maps, statistical analyses, and recommendations.
	10 working days
	Day
	175,000
	1,750,000

	06
	Travel, accommodation, and field equipment costs for the Biologist and support team operating across multiple sites in Argentina Córdoba. Includes vehicle rental, GPS units, sampling kits, and laboratory consumables.
	Full project
	Lump sum
	2,800,000
	2,800,000

	SUBTOTAL
	25,025,000

	IVA (21%)
	5,255,250

	GRAND TOTAL (Quotation Estimate)
	30,280,250


Professional Qualifications of the Biologist
The lead Biologist assigned to this project in Argentina Córdoba holds a Licenciatura en Biología from the Universidad Nacional de Córdoba, a Master's degree in Environmental Science from the Universidad Nacional de La Plata, and is registered with the Colegio de Biólogos de la Provincia de Córdoba (Matrícula N.º 4521). The Biologist possesses over twelve years of field experience in Argentine ecosystems, with specific expertise in the Cuyano and Pampas biomes that characterize the Córdoba province. All supporting team members are certified professionals in their respective disciplines.
Terms and Conditions of this Quotation Estimate
1. This Quotation Estimate is valid for a period of thirty (30) calendar days from the date of issue. After this period, prices may be subject to revision due to inflationary adjustments in Argentina Córdoba.
1. Payment terms: 30% advance upon contract signing, 40% upon completion of fieldwork phases, and 30% upon delivery and acceptance of the final technical report by the Biologist.
1. All services will be performed in compliance with Argentine national and provincial environmental legislation, including Ley 25.675 (Evaluación de Impacto Ambiental) and the corresponding regulations of the Provincia de Córdoba.
1. The Biologist and all support personnel will carry professional liability insurance with a minimum coverage of ARS 50,000,000, valid throughout the project duration in Argentina Córdoba.
1. Any changes to the scope of work must be agreed upon in writing by both parties. Additional services will be quoted separately as a supplementary Quotation Estimate.
1. Confidentiality: All data collected by the Biologist during fieldwork in Argentina Córdoba shall remain the exclusive property of the client. No information may be disclosed to third parties without prior written consent.
1. Force majeure events, including but not limited to severe weather conditions affecting fieldwork in the mountainous regions of Córdoba, will be addressed through mutual agreement and may result in schedule adjustments without penalty.
1. This Quotation Estimate does not constitute a binding contract until formally accepted in writing by the client and countersigned by Andes BioConsult S.R.L.
1. Disputes arising from this engagement shall be resolved through arbitration in Córdoba Capital, Argentina, in accordance with the rules of the Cámara de Comercio de Córdoba.
Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and pricing outlined herein for the Biologist services to be rendered in Argentina Córdoba. This document serves as the formal basis for the subsequent service contract.
For Andes BioConsult S.R.L.
Dr. Carlos Alberto Méndez
Director Técnico – Biólogo (Mat. N.º 3218)
Fecha: _______________
For the Client
Ing. María Elena Rodríguez
Dirección de Medio Ambiente
Municipalidad de Córdoba, Argentina
Fecha: _______________
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