# Quotation Estimate - Biologist Services - Colombia Medellín

# Quotation Estimate

Professional Biologist Services

Colombia Medellín – Antioquia Department

Document No. QTE-BIO-MDE-2025-0047

Quotation Date: June 15, 2025

Valid Until: July 15, 2025

Currency: COP (Colombian Peso)

Prepared For: Client / End User

## 1. Introduction and Purpose of This Quotation Estimate

This Quotation Estimate document has been prepared to provide a comprehensive and transparent breakdown of professional costs associated with the engagement of a certified Biologist for fieldwork, laboratory analysis, environmental impact assessment, and ecological consulting services to be conducted in Colombia Medellín and its surrounding municipalities within the Aburrá Valley. This Quotation Estimate is issued in accordance with the regulatory framework established by the Colombian Ministry of Environment, Housing, and Territorial Development (Ministerio de Ambiente, Vivienda y Desarrollo Territorial) and complies with all applicable national and departmental environmental regulations governing biological fieldwork in the Antioquia region.

The Biologist services outlined in this Quotation Estimate are specifically tailored to the unique biodiversity characteristics of Colombia Medellín, which encompasses tropical cloud forests, paramo ecosystems, riverine habitats, and urban green corridors. The professional Biologist assigned to this project holds a degree in Biological Sciences from a recognized Colombian university, possesses a valid professional registration with the Colombian Council of Biology (Consejo Profesional de Biología), and has a minimum of eight (8) years of documented field experience in the Antioquia Department.

## 2. Scope of Biologist Services in Colombia Medellín

The following scope of work defines the deliverables and professional activities for which this Quotation Estimate is issued. All services will be performed by a qualified Biologist operating within the jurisdiction of Colombia Medellín:

| Item | Description of Biologist Service | Duration / Qty | Unit Price (COP) | Subtotal (COP) |
| --- | --- | --- | --- | --- |
| 01 | Initial site assessment and ecological baseline survey in the Aburrá Valley, Colombia Medellín. Includes vegetation mapping, fauna observation, and habitat classification by the Biologist. | 5 field days | 1,250,000 | 6,250,000 |
| 02 | Environmental Impact Assessment (EIA) biological component preparation. The Biologist will draft the biological chapter of the EIA report in compliance with ANLA and CVC Antioquia requirements. | 15 working days | 980,000 | 14,700,000 |
| 03 | Water quality biological monitoring (macroinvertebrate and algal index analysis) at three (3) sampling stations along the Medellín River and its tributaries. | 3 sampling cycles | 2,400,000 | 7,200,000 |
| 04 | Species identification and taxonomic classification of collected biological specimens. Laboratory work performed by the Biologist at an accredited facility in Colombia Medellín. | 10 lab days | 850,000 | 8,500,000 |
| 05 | Preparation of the final technical report including photographic documentation, GIS-based habitat maps, and conservation recommendations for the Colombia Medellín area. | 1 report | 3,800,000 | 3,800,000 |
| 06 | Regulatory liaison and permit coordination with the Corporación Autónoma Regional del Valle de Aburrá (CVA) on behalf of the Biologist and the client. | 1 service | 1,500,000 | 1,500,000 |
| 07 | On-site supervision and quality assurance during implementation phase. The Biologist will conduct weekly inspections and provide corrective biological recommendations. | 8 weeks | 750,000 | 6,000,000 |
| 08 | Post-project ecological monitoring and follow-up report. The Biologist will assess the recovery status of affected habitats in Colombia Medellín after project completion. | 2 monitoring visits | 1,100,000 | 2,200,000 |
| TOTAL QUOTATION ESTIMATE (Before VAT / IVA) |  |  |  | 50,150,000 |
| VAT / IVA (19%) |  |  |  | 9,528,500 |
| GRAND TOTAL – QUOTATION ESTIMATE |  |  |  | 59,678,500 |

## 3. Professional Qualifications of the Biologist

The Biologist assigned to execute the services described in this Quotation Estimate meets the following professional criteria: a Bachelor's or Master's degree in Biology, Ecology, or a related life science discipline from a university accredited by the Colombian Ministry of Education; active professional registration with the Consejo Profesional de Biología; specialized training in tropical and subtropical ecosystem assessment; proficiency in Colombian environmental legislation (Ley 99 de 1993, Decreto 1076 de 2015, and applicable CVA resolutions); and demonstrated experience in at least five (5) prior biological assessment projects within the Colombia Medellín metropolitan area or the broader Antioquia Department.

## 4. Terms and Conditions of This Quotation Estimate

- This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After this period, the Biologist service rates may be subject to revision based on market conditions in Colombia Medellín.

- Payment terms: 40% advance upon acceptance of this Quotation Estimate, 40% upon delivery of the mid-project biological report, and 20% upon final acceptance of all deliverables by the client.

- All fieldwork and laboratory activities will be conducted in strict compliance with Colombian environmental regulations, CVA permits, and the ethical guidelines of the Colombian Society of Biology (Sociedad Colombiana de Biología).

- The Biologist shall maintain professional liability insurance with a minimum coverage of COP 500,000,000 for the duration of the engagement in Colombia Medellín.

- Any changes to the scope of work beyond the parameters defined in this Quotation Estimate will require a written amendment signed by both parties before additional Biologist services are rendered.

- Confidentiality: All biological data, species records, and ecological information collected by the Biologist in Colombia Medellín shall be treated as proprietary to the client and shall not be disclosed to third parties without written consent.

- Force majeure events, including but not limited to extreme weather conditions affecting the Aburrá Valley, may result in schedule adjustments to the Biologist work plan without penalty to either party.

- This Quotation Estimate does not constitute a binding contract until formally accepted in writing by the client and countersigned by the service provider.

## 5. Acceptance and Authorization

By signing below, the client acknowledges receipt of this Quotation Estimate for Biologist services in Colombia Medellín and agrees to the terms, conditions, and pricing outlined herein. The Biologist service provider confirms availability to commence work within ten (10) business days of written acceptance.

Client / End User
Name: _________________________
NIT / ID: _________________________
Date: _________________________

Biologist Service Provider
Name: _________________________
Professional Reg. No.: ___________
Date: _________________________

Quotation Estimate | Biologist Professional Services | Colombia Medellín, Antioquia, Colombia

Document Reference: QTE-BIO-MDE-2025-0047 | This Quotation Estimate is issued in duplicate. Both copies carry equal legal validity.

For inquiries regarding this Biologist service Quotation Estimate in Colombia Medellín, please contact the project coordinator at the registered office address in Medellín, Antioquia.