# Quotation Estimate - Biologist Services - DR Congo Kinshasa

# Equatorial BioSciences Consulting Ltd.

12 Avenue de la Biodiversité, Gombe, Kinshasa, DR Congo

Tel: +243 810 555 012 | Email: info@equatorialbiosciences.cd

RC: CD-KIN-2019-04478 | NIF: 0012345678

## Quotation Estimate

| Quotation Reference No.: | QBE-2025-KIN-0087 |
| --- | --- |
| Date of Issue: | 14 June 2025 |
| Validity Period: | 60 days from date of issue (expires 13 August 2025) |
| Prepared For: | Ministry of Environment, Sustainable Development & Tourism, Republic of DR Congo – Kinshasa Headquarters |
| Project Location: | Kinshasa Metropolitan Area, DR Congo (including Congo River basin, Malempa wetlands, and surrounding forest corridors) |
| Prepared By: | Dr. Amara K. Mbuyi, Lead Biologist & Principal Consultant |

### 1. Introduction and Purpose of This Quotation Estimate

This Quotation Estimate is formally issued by Equatorial BioSciences Consulting Ltd. in response to the request for professional biological assessment services in the Kinshasa metropolitan region of the Democratic Republic of Congo. The scope of work centers on the deployment of a qualified Biologist and a supporting field team to conduct comprehensive biodiversity surveys, ecological monitoring, and environmental impact assessments across designated zones within DR Congo Kinshasa. This document itemizes all anticipated costs, deliverables, timelines, and conditions governing the engagement, and it serves as the binding financial proposal upon acceptance by the client.

### 2. Scope of Services – Biologist Engagement in DR Congo Kinshasa

The Biologist engaged under this Quotation Estimate shall be a certified ecologist with a minimum of ten (10) years of field experience in Central African tropical ecosystems. The professional scope includes, but is not limited to, the following activities conducted within the Kinshasa urban and peri-urban landscape of DR Congo:

- Full-spectrum biodiversity inventory of flora and fauna across the Malempa wetland system, the Congo River shoreline (Kinshasa stretch), and the remaining gallery forest corridors in the communes of Kalamu, Ngaliema, and Limete.

- Water quality and aquatic ecology monitoring of the Congo River at six (6) designated sampling stations, including macroinvertebrate analysis, algal bloom assessment, and heavy-metal bioaccumulation testing in native fish species.

- Avian population census and migratory bird tracking using standardized point-count and transect methods, with particular attention to species listed on the IUCN Red Data List relevant to the DR Congo Kinshasa region.

- Preparation of a comprehensive Environmental Impact Assessment (EIA) report for proposed infrastructure development along the Kinshasa riverfront, in compliance with the environmental regulations of the DR Congo and the Kinshasa municipal planning code.

- Community engagement and environmental education workshops (minimum four sessions) targeting local residents, fishing cooperatives, and secondary school students in the affected communes.

- Submission of a final technical report in both French and English, accompanied by GIS-mapped habitat data, photographic documentation, and a 15-minute executive video summary.

### 3. Itemized Cost Breakdown

| Item No. | Description of Service / Deliverable | Unit | Qty | Unit Cost (USD) | Subtotal (USD) |
| --- | --- | --- | --- | --- | --- |
| 01 | Lead Biologist – Professional fees (fieldwork, analysis, reporting) | Month | 3 | 4,500.00 | 13,500.00 |
| 02 | Field Assistant / Junior Biologist (2 personnel) | Month | 6 | 1,200.00 | 7,200.00 |
| 03 | Specialized laboratory analysis (water, soil, tissue samples) – contracted lab in Kinshasa | Lot | 1 | 3,800.00 | 3,800.00 |
| 04 | Field equipment rental (boats, waders, GPS units, camera traps, specimen kits) | Month | 3 | 1,150.00 | 3,450.00 |
| 05 | Transportation and logistics within DR Congo Kinshasa (vehicle, fuel, river access) | Month | 3 | 950.00 | 2,850.00 |
| 06 | GIS mapping, remote-sensing data acquisition, and spatial analysis | Lot | 1 | 2,600.00 | 2,600.00 |
| 07 | Community workshops and environmental education materials (4 sessions) | Session | 4 | 450.00 | 1,800.00 |
| 08 | Final EIA report, executive summary, video production, and data archiving | Lot | 1 | 3,200.00 | 3,200.00 |
| 09 | Permits, regulatory filings, and local authority coordination in Kinshasa | Lot | 1 | 1,500.00 | 1,500.00 |
| 10 | Contingency and unforeseen field expenses (8%) | Lot | 1 | 3,108.00 | 3,108.00 |
| TOTAL ESTIMATED COST (USD) |  |  |  |  | 43,008.00 |

### 4. Project Timeline

The Biologist-led engagement is scheduled over a period of three (3) calendar months, commencing on 1 September 2025 and concluding on 30 November 2025. Fieldwork in the Kinshasa wetlands and river zones will be concentrated during the dry season to maximize accessibility and data reliability. The final EIA report and all deliverables shall be submitted to the client no later than 15 December 2025.

### 5. Terms and Conditions

- This Quotation Estimate is valid for sixty (60) days from the date of issue. Any acceptance beyond this period requires written reconfirmation of pricing by Equatorial BioSciences Consulting Ltd.

- Payment terms: 30% advance upon contract signature, 40% upon completion of fieldwork (end of Month 2), and 30% upon delivery and acceptance of the final report. All payments shall be made in US Dollars via bank transfer to the company account in Kinshasa, DR Congo.

- The Biologist and field team shall comply with all applicable laws and regulations of the Democratic Republic of Congo, including the Environmental Code (Loi n° 11/001 du 20 janvier 2011) and Kinshasa municipal by-laws.

- All data, specimens, and intellectual property generated under this engagement shall remain the property of the client. The Biologist retains the right to publish anonymized scientific findings in peer-reviewed journals with prior written consent from the client.

- Force majeure events, including but not limited to civil unrest, severe flooding of the Congo River, or public health emergencies in DR Congo Kinshasa, shall suspend the project timeline without penalty to either party.

- Any change in scope beyond the items listed in Section 3 shall be subject to a supplementary Quotation Estimate issued in writing before additional work commences.

- This Quotation Estimate does not constitute a contract until countersigned by both parties and the advance payment has been received.

### 6. Acceptance and Authorization

By signing below, the client acknowledges receipt of this Quotation Estimate for Biologist services in DR Congo Kinshasa and agrees to the terms, conditions, and pricing outlined herein. Equatorial BioSciences Consulting Ltd. confirms its availability to commence the engagement upon receipt of the advance payment.

For the Client

Ministry of Environment, DR Congo

Kinshasa

Name / Title / Signature / Date

For Equatorial BioSciences Consulting Ltd.

Dr. Amara K. Mbuyi

Lead Biologist & Principal Consultant

Name / Title / Signature / Date

Equatorial BioSciences Consulting Ltd. – Quotation Estimate QBE-2025-KIN-0087 – Page 1 of 1

This document is confidential and intended solely for the named recipient. Unauthorized reproduction or distribution is prohibited under the laws of the Democratic Republic of Congo.