# Quotation Estimate - Biologist Services - New Zealand Wellington

# Te Taiao Environmental Sciences Ltd.

142 Cuba Street, Te Aro, Wellington 6011, New Zealand

Phone: +64 4 472 8830 | Email: enquiries@tetaiao.co.nz

NZBN: 9429041234567 | GST No: 123-456-789

Quotation Estimate QTE-2025-WLG-0472

## 1. Quotation Estimate Details

| Quotation Estimate No.: | QTE-2025-WLG-0472 |
| --- | --- |
| Date of Issue: | 14 June 2025 |
| Valid Until: | 14 September 2025 (90 days) |
| Prepared For: | Wellington Regional Council – Environmental Planning Division |
| Project Location: | Wellington Harbour & Surrounding Catchments, New Zealand Wellington |
| Prepared By: | Dr. Aroha Ngata, Lead Biologist & Principal Consultant |

## 2. Scope of Work – Biologist Services in New Zealand Wellington

This Quotation Estimate is issued by Te Taiao Environmental Sciences Ltd. to provide the scope, schedule, and cost breakdown for the engagement of a qualified Biologist to conduct ecological assessment and biodiversity monitoring services within the New Zealand Wellington region. The Biologist will be responsible for the following deliverables:

- Terrestrial Ecological Survey: A comprehensive flora and fauna survey across 45 hectares of native bush remnant in the Hutt Valley, New Zealand Wellington, including identification of threatened species under the New Zealand Threat Classification System (NZTCS).

- Marine & Estuarine Assessment: Benthic and intertidal community sampling along 12 km of Wellington Harbour shoreline, with emphasis on kelp forest health, macroinvertebrate diversity, and the presence of the protected species Neofolliculina and native shellfish populations.

- Avian Monitoring Programme: Point-count and transect surveys for native bird species (including Morepork, Kererū, and Tūī) across three designated sites in the Wellington urban fringe, conducted over a 12-week period.

- Water Quality Biological Indicators: Collection and laboratory analysis of macroinvertebrate samples from 20 stream monitoring stations in the Rimutaka and Tararua catchments to calculate the New Zealand Macroinvertebrate Community Index (NZ-NCI).

- Reporting & Compliance: Preparation of a full ecological impact assessment report compliant with the Resource Management Act 1991 and Wellington Regional Council's Environmental Planning Policy, including recommendations for mitigation and offset strategies.

## 3. Itemised Cost Breakdown

| Item No. | Description of Biologist Service | Duration / Qty | Unit Rate (NZD) | Amount (NZD) |
| --- | --- | --- | --- | --- |
| 01 | Lead Biologist – Field Survey & Data Collection (Terrestrial) | 18 days | $1,250.00 | $22,500.00 |
| 02 | Lead Biologist – Marine & Estuarine Sampling (incl. dive support) | 10 days | $1,450.00 | $14,500.00 |
| 03 | Avian Monitoring – Biologist & Field Assistant (12-week programme) | 12 weeks | $3,800.00 | $45,600.00 |
| 04 | Water Quality Biological Indicators – Lab Analysis (20 stations) | 20 samples | $420.00 | $8,400.00 |
| 05 | Ecological Impact Assessment Report – Biologist Authorship & QA/QC | 1 report | $6,500.00 | $6,500.00 |
| 06 | Travel, Accommodation & Field Logistics (New Zealand Wellington region) | 30 days | $310.00 | $9,300.00 |
| 07 | Specialist Equipment Hire (ROV, dive gear, GPS, water samplers) | 1 lot | $4,200.00 | $4,200.00 |
| 08 | Permits, Licences & Regulatory Compliance Fees (DOC, WRC) | 1 lot | $1,850.00 | $1,850.00 |
| Subtotal (excl. GST) |  |  |  | $112,850.00 |
| GST (15%) |  |  |  | $16,927.50 |
| TOTAL Quotation Estimate (incl. GST) |  |  |  | $129,777.50 |

## 4. Terms & Conditions of This Quotation Estimate

- This Quotation Estimate is valid for a period of 90 calendar days from the date of issue. After this period, pricing may be revised to reflect changes in market rates, exchange rates, or regulatory requirements applicable in New Zealand Wellington.

- All rates quoted are in New Zealand Dollars (NZD) and are inclusive of the Biologist's professional fees, fieldwork, laboratory analysis, and reporting. Travel and accommodation within the New Zealand Wellington metropolitan area are included; travel to remote field sites beyond 80 km from central Wellington will be billed at cost.

- The Biologist engaged under this Quotation Estimate holds a Master's degree in Ecology (University of Canterbury), is a registered member of the New Zealand Ecological Society (NZES), and carries professional indemnity insurance of no less than NZD $5,000,000.

- Payment terms: 30% deposit upon acceptance of this Quotation Estimate; 40% upon completion of fieldwork; 30% upon delivery and acceptance of the final ecological report. All invoices are payable within 20 business days in accordance with the New Zealand Payment Terms in Supply Act 2013.

- Any variation to the scope of work must be agreed in writing by both parties. Additional Biologist days beyond the quoted duration will be charged at the applicable daily rate specified in Section 3.

- All data collected by the Biologist during the course of this engagement shall become the property of the Wellington Regional Council upon full payment. Te Taiao Environmental Sciences Ltd. retains the right to anonymised data for peer-reviewed publication with prior written consent.

- This Quotation Estimate is subject to the Resource Management Act 1991, the Conservation Act 1987, and all applicable Wellington Regional Council bylaws governing ecological survey work in the New Zealand Wellington region.

- Force majeure: Neither party shall be liable for delays caused by adverse weather (including Wellington's well-known wind conditions), natural disasters, or government-imposed restrictions that prevent the Biologist from accessing field sites.

## 5. Acceptance & Authorisation

By signing below, the client acknowledges and accepts this Quotation Estimate for Biologist services in New Zealand Wellington. The engagement shall commence on the date specified in the project schedule or upon written instruction from the client, whichever is later.

For and on behalf of Te Taiao Environmental Sciences Ltd.

Name: Dr. Aroha Ngata

Title: Lead Biologist & Principal Consultant

Signature: ___________________________

Date: ___________________________

For and on behalf of Wellington Regional Council

Name: ___________________________

Title: Environmental Planning Manager

Signature: ___________________________

Date: ___________________________

Te Taiao Environmental Sciences Ltd. | 142 Cuba Street, Te Aro, Wellington 6011, New Zealand Wellington

This Quotation Estimate (QTE-2025-WLG-0472) was prepared specifically for the engagement of a Biologist for ecological services in the New Zealand Wellington region. All information is confidential and intended solely for the named recipient.

© 2025 Te Taiao Environmental Sciences Ltd. All rights reserved.