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1. Introduction and Purpose of This Quotation Estimate
This Quotation Estimate is formally issued by GreenSage Biological Consulting Ltd. to the Lagos State Ministry of Environment for the engagement of a qualified Biologist to conduct comprehensive ecological assessments, biodiversity surveys, and environmental impact studies across designated zones in Nigeria Lagos. This document outlines the full scope of professional services, itemized costs, delivery timelines, and contractual terms governing the proposed engagement. All pricing is expressed in Nigerian Naira (NGN) and reflects current market rates for specialist biological consultancy work within the Lagos metropolitan area and its surrounding ecosystems.
2. Scope of Biologist Services in Nigeria Lagos
The Biologist engaged under this Quotation Estimate shall provide the following professional services within the Nigeria Lagos jurisdiction:
· Conduct a full terrestrial and aquatic biodiversity survey across the Lekki Lagoon, Lagos Lagoon, and the Epe wetland corridors.
· Perform species identification, population density mapping, and habitat condition assessment for flora and fauna in the designated study areas.
· Prepare a detailed Environmental Impact Assessment (EIA) biological component report in compliance with the Federal Ministry of Environment and Lagos State Environmental Protection Agency (LASEPA) regulations.
· Provide expert testimony and technical advisory support to the Ministry during public consultations and stakeholder engagement sessions held in Lagos.
· Deliver a final comprehensive report, including GIS-mapped data, photographic evidence, and actionable conservation recommendations tailored to the Nigeria Lagos ecological context.
3. Itemized Cost Breakdown
	Item No.
	Description of Service
	Duration / Qty
	Unit Cost (NGN)
	Total (NGN)

	01
	Senior Biologist professional fee (PhD in Tropical Ecology, 15+ years experience in Nigeria Lagos fieldwork)
	45 working days
	₦185,000
	₦8,325,000

	02
	Field survey team (2 junior biologists, 1 field technician) – Lagos Lagoon and Epe wetlands
	20 field days
	₦95,000
	₦1,900,000

	03
	Specialized laboratory analysis (water quality, soil microbiology, tissue sampling) at accredited Lagos facility
	120 samples
	₦12,500
	₦1,500,000

	04
	GIS mapping, drone aerial photography, and remote sensing data processing for habitat delineation
	1 package
	₦2,200,000
	₦2,200,000

	05
	Transportation, field equipment, PPE, and logistics within Nigeria Lagos and surrounding LGAs
	1 package
	₦850,000
	₦850,000

	06
	Report writing, peer review, and three (3) revision cycles of the final Biological Impact Report
	1 package
	₦1,100,000
	₦1,100,000

	07
	Public consultation facilitation and expert presentation at 2 stakeholder meetings in Lagos
	2 sessions
	₦350,000
	₦700,000

	08
	Contingency and unforeseen field conditions (weather delays, access restrictions in Nigeria Lagos)
	1 package
	₦1,000,000
	₦1,000,000

	SUBTOTAL
	₦17,575,000

	VAT (7.5% – Nigeria Lagos standard rate)
	₦1,318,125

	GRAND TOTAL (NGN)
	₦18,893,125


4. Project Timeline
The Biologist engagement under this Quotation Estimate is projected to span a total of fourteen (14) weeks from the date of contract execution in Nigeria Lagos:
· Weeks 1–2: Mobilization, literature review, and preliminary site reconnaissance in Lagos.
· Weeks 3–8: Active field data collection, sampling, and drone surveys across all designated zones.
· Weeks 9–11: Laboratory analysis, data processing, GIS mapping, and draft report preparation.
· Weeks 12–13: Peer review, client feedback incorporation, and final report finalization.
· Week 14: Formal presentation of findings to the Lagos State Ministry of Environment and handover of all deliverables.
5. Terms and Conditions
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Beyond this period, pricing may be subject to revision due to inflationary pressures in the Nigeria Lagos market.
1. Payment terms: 40% advance payment upon contract signing, 35% upon completion of fieldwork, and 25% upon delivery and acceptance of the final report.
1. All payments shall be made in Nigerian Naira via bank transfer to the account of GreenSage Biological Consulting Ltd., First Bank of Nigeria, Victoria Island Branch, Lagos.
1. The Biologist and supporting team shall comply with all applicable Nigerian environmental laws, including the National Environmental Standards and Regulations Enforcement Agency (NESREA) guidelines and Lagos State-specific regulations.
1. Intellectual property rights to all data, reports, and deliverables produced under this engagement shall vest with the Lagos State Ministry of Environment upon full payment.
1. Either party may terminate this agreement with fourteen (14) days written notice. In the event of early termination, the client shall be liable for all costs incurred up to the date of termination.
1. Force majeure events, including but not limited to severe weather, government-imposed restrictions, or public health emergencies affecting Nigeria Lagos, shall extend the project timeline proportionally without penalty to either party.
1. Disputes arising from this Quotation Estimate or the resulting contract shall be resolved through arbitration in Lagos, Nigeria, in accordance with the Arbitration and Conciliation Act, Cap A18, Laws of the Federation of Nigeria.
6. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, scope, and pricing outlined herein for the engagement of the Biologist and associated services in Nigeria Lagos.
For GreenSage Biological Consulting Ltd.
Name: Dr. Chinedu Eze
Title: Lead Biologist / Managing Director
Date: _______________
For Lagos State Ministry of Environment
Name: Dr. Adebayo Ogunlesi
Title: Director, Environmental Planning Division
Date: _______________
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