Quotation Estimate - Biologist Services - Venezuela Caracas
Quotation Estimate
BioConsult Venezuela C.A.
Av. Francisco de Miranda, Torre Empresarial, Piso 12, Caracas, Venezuela
RIF: J-31845672-9 | Tel: +58 (212) 555-0147 | Email: quotes@bioconsultve.com
Quotation No.: QTE-2025-0487
Date Issued: June 15, 2025
Valid Until: July 15, 2025
Location: Venezuela Caracas
1. Client Information
	Client Name: Instituto de Investigaciones Ambientales del Caribe (IIAC)
	Contact Person: Dr. María Fernanda Rojas

	Address: Av. Panteón, Edif. Científico, Chacao, Venezuela Caracas
	Phone: +58 (212) 774-3321

	Email: m.rojas@iiac.gob.ve
	RIF: G-12345678-1


2. Purpose and Scope of This Quotation Estimate
This Quotation Estimate is formally issued by BioConsult Venezuela C.A. to provide a comprehensive and transparent breakdown of professional services rendered by a certified Biologist for the execution of an ecological impact assessment and biodiversity survey in the metropolitan area of Venezuela Caracas. The Biologist engaged under this Quotation Estimate will conduct fieldwork, laboratory analysis, and reporting in accordance with the environmental regulations established by the Ministry of Environment and Water of Venezuela (MINEA) and the applicable municipal ordinances of the Caracas metropolitan region.
The scope of this Quotation Estimate encompasses a full-cycle biological assessment covering terrestrial, freshwater, and coastal ecosystems within the designated study zones of Venezuela Caracas. The Biologist will be responsible for species identification, population density estimation, habitat classification, and the preparation of a final technical report suitable for submission to regulatory authorities in Venezuela Caracas.
3. Itemized Services and Costs
	Item
	Description
	Qty
	Unit Cost (USD)
	Subtotal (USD)

	1
	Senior Biologist – Ecological Impact Assessment (fieldwork, 15 days in Venezuela Caracas)
	15
	$350.00
	$5,250.00

	2
	Biologist – Biodiversity Survey and Species Inventory (10 days)
	10
	$320.00
	$3,200.00

	3
	Biologist – Laboratory Analysis of Soil and Water Samples (8 days)
	8
	$280.00
	$2,240.00

	4
	Biologist – Technical Report Preparation and Regulatory Compliance Review (5 days)
	5
	$400.00
	$2,000.00

	5
	Field Equipment and Sampling Materials (GPS units, specimen kits, PPE)
	1
	$1,850.00
	$1,850.00

	6
	Local Transportation and Permits within Venezuela Caracas
	1
	$950.00
	$950.00

	7
	Project Management and Coordination (Biologist Supervisor, 20 days)
	20
	$250.00
	$5,000.00

	TOTAL ESTIMATED COST
	$20,490.00


4. Professional Qualifications of the Biologist
The Biologist assigned to this project holds a Master's degree in Environmental Biology from the Universidad Central de Venezuela (UCV) and a Doctorate in Tropical Ecology from the Universidad Simón Bolívar. The Biologist possesses over twelve years of professional experience conducting ecological assessments in the Venezuela Caracas metropolitan area and surrounding ecosystems, including the Ávila National Park, the Lago de Valencia watershed, and the coastal zones of La Guaira. The Biologist is registered with the Colegio de Biólogos de Venezuela and holds a valid professional license to practice in Venezuela Caracas.
5. Terms and Conditions of This Quotation Estimate
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issuance. After this period, pricing may be subject to revision due to currency fluctuations or changes in operational costs within Venezuela Caracas.
· Payment terms: 40% advance upon acceptance of this Quotation Estimate, 40% upon completion of fieldwork, and 20% upon delivery of the final technical report by the Biologist.
· All services will be performed in strict compliance with Venezuelan environmental law, including the Ley Orgánica del Ambiente and the specific regulations of the Alcaldía Metropolitana de Caracas.
· The Biologist shall provide weekly progress reports to the client throughout the duration of the project in Venezuela Caracas.
· Any additional services beyond the scope defined in this Quotation Estimate will require a written amendment signed by both parties.
· Confidentiality: All data collected by the Biologist during fieldwork in Venezuela Caracas shall remain the exclusive property of the client unless otherwise agreed in writing.
· Force majeure events, including but not limited to natural disasters, civil unrest, or government-mandated closures in Venezuela Caracas, may extend project timelines without penalty to either party.
6. Acceptance and Authorization
By signing below, the client acknowledges receipt and acceptance of this Quotation Estimate for Biologist services to be executed in Venezuela Caracas. The Biologist and the project team will commence work within five (5) business days of receiving the advance payment and written confirmation from the client.
For BioConsult Venezuela C.A.
Dr. Alejandro Mendoza, Lead Biologist
Date: _______________
For the Client (IIAC)
Dr. María Fernanda Rojas
Date: _______________
This Quotation Estimate document was prepared exclusively for the client identified above. It is not a binding contract until formally accepted in writing by both parties. All amounts are quoted in United States Dollars (USD) and are subject to applicable Venezuelan tax regulations. Document Reference: QTE-2025-0487 | BioConsult Venezuela C.A. | Venezuela Caracas
