# Quotation Estimate - Biomedical Engineer Services - Australia Brisbane

# Quotation Estimate

MedTech Solutions Pty Ltd
Level 12, 400 George Street
Brisbane, Queensland 4000
Australia
ABN: 54 123 456 789
Phone: +61 7 3100 2200
Email: quotes@medtechsolutions.com.au

Quotation Estimate No: QTE-2025-BME-0472
Date Issued: 14 June 2025
Valid Until: 14 July 2025
Prepared For: Queensland Health – Brisbane Regional Hospital

Subject: Quotation Estimate for Biomedical Engineer Professional Services – Equipment Calibration, Maintenance, and Regulatory Compliance Programme
Location of Service: Australia Brisbane, Queensland
Engagement Period: 12 months (July 2025 – June 2026)

## 1. Introduction and Purpose

This Quotation Estimate is issued by MedTech Solutions Pty Ltd to provide a comprehensive and itemised financial proposal for the engagement of a qualified Biomedical Engineer to deliver critical technical services at facilities located in Australia Brisbane. This document outlines the scope of work, associated costs, payment schedules, and contractual terms governing the professional engagement. The Biomedical Engineer services described herein are designed to ensure that all medical and diagnostic equipment within the client's Brisbane-based facilities operates in full compliance with Australian Therapeutic Goods Administration (TGA) regulations, Australian Standards (AS/NZS), and Queensland Health safety directives.

## 2. Scope of Services

The Biomedical Engineer engaged under this Quotation Estimate will be responsible for the following core service areas across all designated sites in Australia Brisbane:

### 2.1 Preventive Maintenance and Calibration

Monthly scheduled calibration and preventive maintenance of all Class IIa and Class IIb medical devices, including but not limited to patient monitors, infusion pumps, defibrillators, anaesthesia machines, and imaging equipment. The Biomedical Engineer will maintain a full digital asset register and generate calibration certificates traceable to National Measurement Institute (NMI) standards.

### 2.2 Corrective Maintenance and Troubleshooting

Responsive corrective maintenance for all biomedical equipment within a guaranteed 4-hour response window for critical life-support devices and a 24-hour response window for non-critical devices. The Biomedical Engineer will perform root-cause analysis, component-level repair, and post-repair verification testing.

### 2.3 Regulatory Compliance and Documentation

Quarterly compliance audits aligned with the Australian Medical Device Regulations 2002. The Biomedical Engineer will prepare and maintain all mandatory documentation, including risk assessments, maintenance logs, and incident reports, ensuring full traceability for Queensland Health inspections and TGA reporting obligations.

### 2.4 Equipment Procurement Advisory and Commissioning

Technical advisory support for the procurement of new biomedical equipment, including specification review, vendor evaluation, site acceptance testing, and initial commissioning. The Biomedical Engineer will provide written recommendations to the client's capital planning committee.

### 2.5 Training and Knowledge Transfer

Two (2) on-site training sessions per quarter for clinical and technical staff in Australia Brisbane, covering safe operation, basic troubleshooting, and regulatory obligations associated with biomedical equipment.

## 3. Itemised Cost Breakdown

| Item No. | Description of Service | Unit | Quantity | Unit Rate (AUD) | Amount (AUD) |
| --- | --- | --- | --- | --- | --- |
| 01 | Biomedical Engineer – Senior (Preventive Maintenance & Calibration, 12 months) | Month | 12 | 14,500.00 | 174,000.00 |
| 02 | Biomedical Engineer – Corrective Maintenance & Emergency Call-Out (estimated 40 call-outs) | Call-out | 40 | 650.00 | 26,000.00 |
| 03 | Regulatory Compliance Audits & Documentation (quarterly) | Quarter | 4 | 3,200.00 | 12,800.00 |
| 04 | Equipment Procurement Advisory & Commissioning (estimated 6 projects) | Project | 6 | 2,800.00 | 16,800.00 |
| 05 | On-Site Training & Knowledge Transfer Sessions (8 sessions in Australia Brisbane) | Session | 8 | 1,400.00 | 11,200.00 |
| 06 | Calibration Consumables, Test Equipment Hire, and Travel within Brisbane Metro | Year | 1 | 8,500.00 | 8,500.00 |
| 07 | Project Management, Reporting, and Administrative Overhead | Year | 1 | 12,000.00 | 12,000.00 |
| Subtotal (AUD) |  |  |  |  | 261,300.00 |
| GST (10%) |  |  |  |  | 26,130.00 |
| TOTAL (AUD, incl. GST) |  |  |  |  | 287,430.00 |

## 4. Payment Terms

Payment for services rendered under this Quotation Estimate shall be made in monthly instalments, invoiced in arrears on the last business day of each calendar month. The client agrees to remit payment within thirty (30) days of the invoice date via electronic funds transfer (EFT) to the bank account nominated by MedTech Solutions Pty Ltd. A late payment surcharge of 1.5% per month will apply to outstanding balances exceeding the 30-day term, in accordance with the Queensland Government Procurement Policy.

## 5. Terms and Conditions

- This Quotation Estimate is valid for thirty (30) days from the date of issue. Upon expiry, all rates and availability must be reconfirmed in writing.

- The Biomedical Engineer assigned to this engagement must hold a minimum of a Bachelor of Engineering (Biomedical) degree, be registered with Engineers Australia, and maintain current professional indemnity insurance of no less than AUD 10,000,000.

- All work performed in Australia Brisbane shall comply with the Work Health and Safety Act 2011 (Qld), the Privacy Act 1988 (Cth), and all applicable Queensland Health policies.

- MedTech Solutions Pty Ltd reserves the right to substitute the assigned Biomedical Engineer with a suitably qualified alternative, provided prior written notice of no less than five (5) business days is given to the client.

- Intellectual property, including all calibration data, compliance reports, and technical documentation generated during the engagement, shall remain the property of the client upon full payment.

- This Quotation Estimate does not constitute a binding contract until a formal Service Agreement is executed by both parties.

- Any variation to the scope of work must be documented in a written Variation Order signed by both parties before additional work commences.

- Disputes arising from this engagement shall be resolved in accordance with the Queensland Civil and Administrative Tribunal (QCAT) procedures.

## 6. Acceptance

By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and pricing outlined herein for the engagement of the Biomedical Engineer services in Australia Brisbane.

For and on behalf of MedTech Solutions Pty Ltd:

Authorised Signatory

Name: _________________________
Title: _________________________
Date: _________________________

For and on behalf of the Client:

Authorised Signatory

Name: _________________________
Title: _________________________
Date: _________________________

This Quotation Estimate was prepared by MedTech Solutions Pty Ltd, Brisbane, Queensland, Australia. All amounts are quoted in Australian Dollars (AUD) and include GST at the current rate of 10% unless otherwise stated. This document is confidential and intended solely for the named recipient.