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1. Introduction and Purpose of This Quotation Estimate
This Quotation Estimate document has been prepared to provide a comprehensive and transparent financial overview of the professional services to be rendered by a certified Biomedical Engineer operating within the jurisdiction of Israel Jerusalem. The purpose of this Quotation Estimate is to outline the scope of work, associated costs, timelines, and contractual terms governing the engagement of Biomedical Engineering expertise for the client's institutional or private healthcare facility located in Israel Jerusalem. All pricing and service descriptions contained within this Quotation Estimate are based on current market rates applicable to the Israel Jerusalem region and comply with the regulatory standards set forth by the Israeli Ministry of Health and the Israel Standards Institute (SII).
2. Scope of Biomedical Engineering Services
The Biomedical Engineer engaged under this Quotation Estimate shall provide the following professional services to the client in Israel Jerusalem:
· Comprehensive assessment and calibration of medical diagnostic equipment including MRI, CT scanners, ultrasound systems, and laboratory analyzers installed at the client's facility in Israel Jerusalem.
· Preventive maintenance scheduling and execution for all biomedical devices, ensuring compliance with Israeli medical device regulations and international ISO 13485 standards.
· Design and implementation of biomedical engineering infrastructure upgrades, including electrical safety testing, grounding verification, and electromagnetic compatibility assessments for the Israel Jerusalem facility.
· Consultation on the procurement, installation, and commissioning of new medical technology systems, with full regulatory approval coordination with Israeli health authorities.
· Training of hospital and clinic staff on the proper operation, basic troubleshooting, and safety protocols for all biomedical equipment.
· Annual safety inspections and regulatory reporting as mandated by the Israel Jerusalem municipal health department and the national Ministry of Health.
· Emergency response and on-call support for critical biomedical equipment failures, with a guaranteed response time of four hours within the Israel Jerusalem metropolitan area.
3. Detailed Cost Breakdown
The following table presents the itemized costs forming the basis of this Quotation Estimate for Biomedical Engineering services in Israel Jerusalem:
	Item No.
	Service Description
	Unit
	Quantity
	Unit Price (ILS)
	Total (ILS)

	01
	Initial facility assessment and equipment inventory audit in Israel Jerusalem
	Project
	1
	18,500
	18,500

	02
	Calibration and preventive maintenance of diagnostic imaging systems
	Device
	12
	4,200
	50,400

	03
	Electrical safety and grounding inspection of all biomedical devices
	Device
	45
	850
	38,250

	04
	Biomedical infrastructure upgrade design and implementation
	Project
	1
	72,000
	72,000

	05
	Staff training program (4 sessions, 8 hours each) in Israel Jerusalem
	Session
	4
	6,500
	26,000

	06
	Annual regulatory compliance inspection and reporting
	Year
	1
	22,000
	22,000

	07
	Emergency on-call support (24/7 coverage, Israel Jerusalem area)
	Month
	12
	3,800
	45,600

	08
	Consultation on new medical equipment procurement and installation
	Hour
	30
	1,200
	36,000

	TOTAL ESTIMATED COST (VAT 18% included)
	380,000 ILS


4. Payment Terms and Schedule
As stipulated in this Quotation Estimate, payment for the Biomedical Engineering services shall be structured as follows: an initial deposit of 30 percent (114,000 ILS) due upon acceptance of this Quotation Estimate; a second installment of 40 percent (152,000 ILS) due upon completion of the infrastructure upgrade and calibration phase; and a final payment of 30 percent (114,000 ILS) due upon successful completion of all deliverables and final regulatory sign-off in Israel Jerusalem. All payments shall be made via bank transfer to the account designated by the Biomedical Engineer's firm. Late payments shall incur a monthly interest charge of 1.5 percent in accordance with Israeli commercial law.
5. Project Timeline
The Biomedical Engineer commits to completing all services outlined in this Quotation Estimate within a period of fourteen (14) weeks from the date of contract execution. The initial assessment phase in Israel Jerusalem shall be completed within the first two weeks. Calibration and maintenance activities shall span weeks three through eight. Infrastructure upgrades and staff training shall be conducted during weeks nine through twelve. Final regulatory inspections and documentation shall be completed by the end of week fourteen.
6. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After this period, pricing may be subject to revision based on market conditions in Israel Jerusalem.
· The Biomedical Engineer shall maintain full professional liability insurance with a minimum coverage of 5,000,000 ILS throughout the duration of the engagement.
· All work performed under this Quotation Estimate shall comply with the Israeli Medical Devices Regulations, the Israel Jerusalem municipal building and safety codes, and applicable international standards.
· Any changes to the scope of work must be documented in a written amendment to this Quotation Estimate, signed by both parties, before additional work commences.
· The Biomedical Engineer guarantees all calibration and maintenance work for a period of twelve (12) months from the date of completion, provided the equipment is used in accordance with manufacturer specifications.
· Confidentiality of all patient data, facility information, and proprietary systems encountered during the engagement in Israel Jerusalem is strictly maintained under Israeli data protection law (Privacy Protection Law, 5741-1981).
· Disputes arising from this Quotation Estimate shall be resolved through mediation in Israel Jerusalem, and if unresolved, through the competent courts of Israel Jerusalem.
7. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and pricing outlined herein for the engagement of the Biomedical Engineer in Israel Jerusalem. This document, once signed by both parties, constitutes a binding agreement for the services described.
Biomedical Engineer (Service Provider)
Dr. Yael Ben-Ami, P.Eng.
Jerusalem, Israel
Signature & Date
Client / Authorized Representative
Name: ______________________
Organization: ______________________
Signature & Date
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