Quotation Estimate - Business Consultant Services - Algeria Algiers
Quotation Estimate
Professional Business Consultant Services
Prepared for Clients in Algeria Algiers
Quotation No.: QE-2025-ALG-0047
Date of Issue: 15 June 2025
Valid Until: 15 July 2025
Currency: Algerian Dinar (DZD)
1. Parties Involved
Service Provider (Business Consultant)
Company: Atlas Strategic Advisory SARL
Address: 42, Boulevard Zighout Youcef, Hydra, Algiers 16000, Algeria
RC: 16/00-1234567B25
NIF: 002516123456789
Contact: consultant@atlas-advisory.dz
Phone: +213 21 23 45 67
Client
Company: [Client Company Name] SARL
Address: [Street Address], [District], Algiers, Algeria
RC: [Registration Number]
NIF: [Tax Identification Number]
Contact: [Email Address]
Phone: [Phone Number]
2. Scope of Business Consultant Services
This Quotation Estimate is issued by Atlas Strategic Advisory SARL, a registered Business Consultant firm operating in Algeria Algiers, to provide comprehensive strategic advisory services to the client. The scope of engagement covers organizational restructuring, operational efficiency analysis, market entry strategy development, and financial performance optimization tailored specifically to the regulatory and commercial environment of Algeria Algiers. The Business Consultant will dedicate a senior team of professionals with proven expertise in the Algerian market to deliver measurable results within the agreed project timeline.
3. Detailed Quotation Estimate Breakdown
	Ref
	Service Description
	Duration
	Rate (DZD)
	Total (DZD)

	01
	Initial diagnostic assessment and organizational audit of the client's operations in Algiers
	2 weeks
	450,000
	900,000

	02
	Strategic business plan development aligned with Algerian commercial regulations
	4 weeks
	600,000
	2,400,000

	03
	Operational process optimization and supply chain restructuring
	6 weeks
	550,000
	3,300,000

	04
	Market analysis and competitive positioning study for the Algiers metropolitan region
	3 weeks
	500,000
	1,500,000

	05
	Financial modeling, budgeting framework, and cash flow projection
	3 weeks
	520,000
	1,560,000

	06
	Executive training workshops and change management facilitation (4 sessions)
	2 weeks
	350,000
	1,400,000

	07
	Regulatory compliance review and Algerian legal framework advisory
	2 weeks
	400,000
	800,000

	08
	Post-implementation monitoring and quarterly performance review (3 months)
	3 months
	300,000
	900,000

	Subtotal
	12,760,000

	TVA (19% - Algerian VAT)
	2,424,400

	Total Amount Due
	15,184,400 DZD


4. Payment Schedule
The total amount of this Quotation Estimate shall be settled according to the following milestone-based payment plan, in compliance with Algerian commercial law and banking regulations applicable in Algeria Algiers:
· 30% Advance Payment (4,555,320 DZD): Due upon signed acceptance of this Quotation Estimate and commencement of the engagement.
· 40% Progress Payment (6,073,760 DZD): Due upon delivery of the strategic business plan and operational restructuring report.
· 30% Final Payment (4,555,320 DZD): Due upon completion of all deliverables and submission of the final project report.
All payments shall be made via bank transfer to the Business Consultant's designated account at a licensed Algerian bank in Algiers. Invoices will be issued in accordance with Algerian tax authority requirements.
5. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Beyond this period, the Business Consultant reserves the right to revise pricing due to market conditions in Algeria Algiers.
· The Business Consultant shall maintain strict confidentiality regarding all client data, trade secrets, and proprietary information shared during the engagement in Algiers.
· All deliverables produced under this Quotation Estimate shall become the exclusive property of the client upon full payment.
· The Business Consultant is not liable for indirect or consequential losses arising from the implementation of recommendations. The client assumes full responsibility for decisions made based on the advisory provided.
· Any changes to the scope of work must be agreed upon in writing by both parties. Additional services will be subject to a supplementary Quotation Estimate.
· This engagement is governed by the laws of the People's Democratic Republic of Algeria. Any disputes shall be resolved through the competent commercial courts in Algiers.
· The Business Consultant shall comply with all applicable Algerian labor, tax, and commercial regulations throughout the duration of the project.
· Force majeure events, including but not limited to government-mandated closures, natural disasters, or regulatory changes in Algeria, shall suspend obligations proportionally.
6. Acceptance and Authorization
By signing below, both parties acknowledge and agree to the terms set forth in this Quotation Estimate for Business Consultant services in Algeria Algiers. This document constitutes a binding agreement upon countersignature by both parties.
For the Business Consultant
Name: ___________________________
Title: Senior Business Consultant
Company: Atlas Strategic Advisory SARL
Signature & Stamp:
Date: _______________
For the Client
Name: ___________________________
Title: ___________________________
Company: ___________________________
Signature & Stamp:
Date: _______________
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