# Quotation Estimate - Business Consultant - Chile Santiago

# Quotation Estimate

Professional Business Consultant Services

Chile Santiago — Metropolitan Region

Quotation Reference: QTE-2025-CHL-0847

### Provider

Strategic Advisory Partners SpA

Av. Apoquindo 4501, Of. 1203

Las Condes, Chile Santiago

Phone: +56 2 2345 6789

Email: quotes@strategicadvisory.cl

RUT: 77.123.456-8

### Client

Andes Manufacturing Group SpA

Calle Los Aromos 2200, Piso 8

Providencia, Chile Santiago

Phone: +56 2 2987 6543

Email: procurement@andesmanufacturing.cl

RUT: 76.543.210-9

### Quotation Details

Date of Issue: June 15, 2025

Valid Until: July 15, 2025 (30 days)

Currency: Chilean Pesos (CLP)

Project Duration: 12 weeks

### Project Reference

Project Name: Operational Excellence & Market Expansion

Location: Chile Santiago, Metropolitan Region

Lead Business Consultant: Ing. Carlos Mendoza

Engagement Type: Fixed-Fee with Milestone Deliverables

## 1. Executive Summary

This Quotation Estimate is formally issued by Strategic Advisory Partners SpA to Andes Manufacturing Group SpA for the engagement of a senior Business Consultant to deliver comprehensive operational and strategic advisory services within the Chile Santiago metropolitan area. The scope of this engagement encompasses process optimization, supply chain restructuring, market entry analysis for the Andean corridor, and organizational performance benchmarking. All services will be executed in accordance with Chilean commercial regulations and the professional standards established by the Chilean Chamber of Commerce in Chile Santiago.

## 2. Scope of Services

The Business Consultant engaged under this Quotation Estimate will provide the following deliverables and services over a twelve-week period:

- Phase 1 (Weeks 1–3): Diagnostic assessment of current operations, financial modeling review, and stakeholder interviews conducted at the client's premises in Chile Santiago. Includes a comprehensive gap analysis report.

- Phase 2 (Weeks 4–7): Development of a strategic roadmap for operational efficiency, including lean manufacturing implementation plans, vendor consolidation strategies, and digital transformation recommendations tailored to the Chile Santiago industrial landscape.

- Phase 3 (Weeks 8–10): Market expansion feasibility study targeting Peru, Bolivia, and Ecuador. The Business Consultant will conduct competitive intelligence research, regulatory compliance mapping under Chilean export regulations, and pricing strategy formulation.

- Phase 4 (Weeks 11–12): Final integration workshop, executive presentation to the board of directors, and delivery of the master action plan with KPIs and 18-month implementation timeline.

## 3. Itemized Cost Breakdown

| Item | Description | Duration | Rate (CLP) | Subtotal (CLP) |
| --- | --- | --- | --- | --- |
| 1.1 | Business Consultant — Senior Strategic Advisor (full engagement) | 12 weeks | 850,000 / week | 10,200,000 |
| 1.2 | Business Consultant — Operations Analyst (support role) | 12 weeks | 420,000 / week | 5,040,000 |
| 1.3 | Market Research & Data Acquisition (Chile Santiago & Andean markets) | One-time | — | 1,850,000 |
| 1.4 | Travel & Local Transportation within Chile Santiago Metropolitan Region | 12 weeks | 180,000 / week | 2,160,000 |
| 1.5 | Software Licenses & Analytical Tools (SAP Analytics, Tableau) | 12 weeks | 95,000 / week | 1,140,000 |
| 1.6 | Workshop Facilitation & Executive Presentation Materials | 2 sessions | 450,000 / session | 900,000 |
| 1.7 | Regulatory & Legal Compliance Review (Chilean commercial law) | One-time | — | 1,200,000 |
| Subtotal (CLP) |  |  |  | 22,490,000 |
| IVA (19% — Chilean Value Added Tax) |  |  |  | 4,273,100 |
| TOTAL AMOUNT DUE (CLP) |  |  |  | 26,763,100 |

Note: This Quotation Estimate is denominated in Chilean Pesos (CLP). All rates are inclusive of the Business Consultant's professional expertise, project management, and standard reporting. Any scope modifications beyond the defined deliverables will be subject to a supplementary Quotation Estimate issued within five (5) business days of the change request.

## 4. Payment Schedule

| Milestone | Trigger Event | Percentage | Amount (CLP) |
| --- | --- | --- | --- |
| Advance Payment | Upon signed acceptance of this Quotation Estimate | 30% | 8,028,930 |
| Phase 1 Completion | Delivery of Diagnostic Assessment Report | 25% | 6,690,775 |
| Phase 2 & 3 Completion | Delivery of Strategic Roadmap & Market Feasibility Study | 30% | 8,028,930 |
| Final Delivery | Executive Presentation & Master Action Plan handover | 15% | 4,014,465 |

## 5. Terms and Conditions

- This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiration date, the Business Consultant reserves the right to revise all rates and terms.

- All services will be performed by the designated Business Consultant and support team in Chile Santiago, with on-site visits to the client's premises no more than three (3) days per week unless otherwise agreed in writing.

- The client shall provide timely access to all relevant financial records, operational data, and personnel necessary for the Business Consultant to execute the scope of work as defined in this Quotation Estimate.

- Intellectual property of all reports, analyses, and deliverables produced under this engagement shall transfer to the client upon full payment of the total amount specified herein.

- Confidentiality: The Business Consultant and all supporting personnel shall adhere to a strict non-disclosure agreement covering all proprietary information of the client, in compliance with Chilean data protection law (Ley 19.628).

- Force Majeure: Neither party shall be liable for delays caused by events beyond reasonable control, including but not limited to natural disasters, government mandates, or public health emergencies affecting Chile Santiago.

- Disputes arising from this Quotation Estimate shall be resolved through mediation in Chile Santiago, and if unresolved, through the competent commercial courts of the Metropolitan Region of Santiago, Chile.

- Any amendments to this Quotation Estimate must be made in writing and signed by both parties to be considered binding.

## 6. Acceptance and Authorization

By signing below, both parties acknowledge and agree to the terms, scope, and financial obligations outlined in this Quotation Estimate for Business Consultant services to be delivered in Chile Santiago.

For Strategic Advisory Partners SpA

Ing. Carlos Mendoza — Lead Business Consultant

Signature & Date

For Andes Manufacturing Group SpA

Authorized Representative

Signature & Date

This Quotation Estimate (Ref: QTE-2025-CHL-0847) was prepared by Strategic Advisory Partners SpA for Business Consultant engagement in Chile Santiago. Document generated on June 15, 2025. Page 1 of 1.