# Quotation Estimate - Business Consultant Services - Egypt Cairo

# QUOTATION ESTIMATE

Professional Business Consultant Services | Egypt Cairo

### Provider

Nile Strategic Advisory Group

Business Consultant Firm

12 Tahrir Square, Downtown District

Cairo, Egypt 11511

Tel: +20 2 2578 4432

Email: info@nilestrategic.com.eg

CR: 184729 | Tax ID: 552-881-334

### Client

Al-Nileh Trading & Logistics Co.

Attn: Mr. Ahmed Hassan, CEO

45 El-Mokattam Road, Nasr City

Cairo, Egypt 11341

Tel: +20 100 556 7789

Email: ahmed.hassan@alnileh.com

| Quotation Estimate No.: | QTE-2025-04782 | Date of Issue: | 14 June 2025 |
| --- | --- | --- | --- |
| Validity Period: | 30 Calendar Days | Service Location: | Cairo, Egypt (On-site & Remote) |
| Prepared By: | Dr. Mona El-Sayed, Senior Business Consultant | Approved By: | Mr. Khaled Farouk, Managing Director |

## 1. Purpose of This Quotation Estimate

This Quotation Estimate is issued by Nile Strategic Advisory Group to formally present the scope, deliverables, and associated costs for professional Business Consultant engagement services to be delivered in Egypt Cairo. This document serves as a binding financial proposal upon client acceptance and is structured in accordance with the Egyptian Commercial Code and the regulations of the Egyptian Companies Authority. The Business Consultant engagement outlined herein is specifically tailored to the operational, strategic, and financial needs of the client within the competitive business environment of Egypt Cairo.

## 2. Scope of Business Consultant Services

The following Business Consultant services are proposed for execution in Egypt Cairo over a period of twelve (12) weeks, commencing upon written acceptance of this Quotation Estimate:

| # | Service Description | Deliverable | Duration | Unit | Amount (EGP) |
| --- | --- | --- | --- | --- | --- |
| 1 | Comprehensive Business Strategy Assessment & Market Analysis for the Cairo metropolitan commercial sector | Strategic Report (40+ pages) | Weeks 1–2 | Fixed Fee | 85,000 |
| 2 | Operational Process Optimization & Supply Chain Restructuring (on-site in Cairo offices) | Process Manual & SOPs | Weeks 3–5 | Fixed Fee | 120,000 |
| 3 | Financial Modeling, Cash Flow Forecasting & Investment Readiness Assessment | Financial Model (Excel) & Advisory Memo | Weeks 5–7 | Fixed Fee | 95,000 |
| 4 | Human Capital & Organizational Development Consulting (workshops in Cairo) | Training Materials & Org Chart | Weeks 7–9 | Fixed Fee | 72,000 |
| 5 | Digital Transformation Roadmap & Technology Integration Advisory | Roadmap Document & Vendor Shortlist | Weeks 9–11 | Fixed Fee | 68,000 |
| 6 | Final Executive Presentation, Implementation Plan & 30-Day Post-Engagement Support | Board Deck & Implementation Gantt | Weeks 11–12 | Fixed Fee | 40,000 |
| 7 | Travel, Local Transportation & Accommodation within Cairo & Giza (Business Consultant on-site visits) | Itemized Expense Report | 12 Weeks | Per Diem | 25,000 |
| TOTAL ESTIMATED COST (EGP) |  |  |  |  | 505,000 |
| VAT (14% – Egyptian Tax Authority) |  |  |  |  | 70,700 |
| GRAND TOTAL (EGP, VAT Inclusive) |  |  |  |  | 575,700 |

Note: All amounts in this Quotation Estimate are denominated in Egyptian Pounds (EGP) and are subject to the prevailing exchange rate at the time of invoicing. The Business Consultant fees are exclusive of any third-party licensing, software procurement, or regulatory filing fees that may arise during the engagement in Egypt Cairo.

## 3. Terms and Conditions

- Acceptance: This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Acceptance must be communicated in writing via signed copy of this document or a formal purchase order referencing Quotation Estimate No. QTE-2025-04782.

- Payment Schedule: 30% advance payment upon contract signing; 40% upon completion of Week 6 deliverables; 30% upon final delivery and acceptance. All payments shall be made via bank transfer to the provider's account at CIB, Cairo Branch, Egypt.

- Confidentiality: The Business Consultant and all supporting team members shall adhere to a strict Non-Disclosure Agreement (NDA) covering all proprietary information of the client obtained during the engagement in Egypt Cairo.

- Intellectual Property: All reports, models, and deliverables produced under this Quotation Estimate shall become the sole property of the client upon full payment. The Business Consultant retains the right to reference the engagement in anonymized case studies.

- Force Majeure: Neither party shall be liable for delays caused by events beyond reasonable control, including but not limited to government-mandated closures, civil unrest, or natural disasters affecting Egypt Cairo.

- Governing Law: This Quotation Estimate and any resulting contract shall be governed by the laws of the Arab Republic of Egypt. Disputes shall be resolved through arbitration at the Egyptian Arbitration Center in Cairo.

- Revisions: Up to two (2) rounds of revisions per deliverable are included. Additional revision cycles will be billed at the Business Consultant's standard hourly rate of EGP 2,500 per hour.

- Termination: Either party may terminate the engagement with fourteen (14) days' written notice. In such case, the client shall pay for all services rendered up to the termination date as outlined in this Quotation Estimate.

## 4. Business Consultant Team & Qualifications

The Business Consultant engagement will be led by Dr. Mona El-Sayed (PhD, Business Administration, Cairo University; 18 years of consulting experience in the Egyptian and MENA markets) and supported by a team of four (4) senior analysts specializing in operations, finance, HR, and digital strategy. All team members are based in or regularly operate within Egypt Cairo, ensuring cultural fluency, regulatory awareness, and immediate on-site availability.

## 5. Acceptance & Authorization

By signing below, the client acknowledges and accepts all terms, conditions, pricing, and scope of work detailed in this Quotation Estimate for Business Consultant services to be performed in Egypt Cairo.

For Nile Strategic Advisory Group
Name: Khaled Farouk
Title: Managing Director
Date: _______________

For Al-Nileh Trading & Logistics Co.
Name: Ahmed Hassan
Title: Chief Executive Officer
Date: _______________

Nile Strategic Advisory Group | Business Consultant Services | Cairo, Egypt

Quotation Estimate No. QTE-2025-04782 | Page 1 of 1

This document is confidential and intended solely for the named recipient. Unauthorized distribution is prohibited under Egyptian law.