# Quotation Estimate - Business Consultant - New Zealand Wellington

# QUOTATION ESTIMATE

Apex Strategic Advisory Ltd

Level 4, 128 Lambton Quay, Wellington, New Zealand

Phone: +64 4 382 5500 | Email: enquiries@apexstrategic.co.nz

NZBN: 9429041234567 | GST No: 123-456-789

| Quotation Estimate No. | QTE-2025-WLG-0047 |
| --- | --- |
| Date of Issue | 14 June 2025 |
| Valid Until | 14 July 2025 (30 calendar days) |
| Prepared For | Harbourview Logistics Group Ltd, 22 Featherston Street, Wellington, New Zealand |
| Prepared By | Dr. Margaret Chen, Senior Business Consultant, Apex Strategic Advisory Ltd |
| Project Reference | Operational Restructuring & Market Expansion Advisory – FY2025/26 |

## 1. Introduction and Purpose of This Quotation Estimate

Thank you for engaging Apex Strategic Advisory Ltd to prepare this Quotation Estimate for professional advisory services. This document outlines the scope, deliverables, timeline, and associated costs for the engagement of our Business Consultant team to support Harbourview Logistics Group Ltd in its operational restructuring and market expansion initiatives. All services described herein will be delivered in accordance with the professional standards expected of a Business Consultant operating within the New Zealand Wellington commercial landscape, and in full compliance with the New Zealand Code of Ethics for Professional Consultants.

This Quotation Estimate has been prepared specifically for use in New Zealand Wellington and reflects current market rates, local regulatory requirements, and the specific economic conditions of the Wellington region as of June 2025. All monetary values are expressed in New Zealand Dollars (NZD) and are inclusive of Goods and Services Tax (GST) at the prevailing rate of 15%.

## 2. Scope of Services – Business Consultant Engagement

Our Business Consultant, Dr. Margaret Chen, together with a dedicated team of two associate consultants, will provide the following services to Harbourview Logistics Group Ltd:

- Operational Audit and Diagnostic Review: A comprehensive assessment of current logistics workflows, supply chain bottlenecks, and resource allocation across all Wellington-based facilities. This phase includes on-site visits to the client's distribution centre in Lower Hutt and the central Wellington warehouse.

- Strategic Market Expansion Planning: Development of a detailed market entry strategy for the Tasman and Marlborough regions, including competitive analysis, regulatory compliance mapping under New Zealand trade law, and projected revenue modelling.

- Organisational Restructuring Advisory: Recommendations for role realignment, performance management frameworks, and leadership development pathways tailored to the client's workforce of approximately 120 employees in the New Zealand Wellington area.

- Financial Modelling and Forecasting: Construction of a five-year financial projection incorporating capital expenditure, working capital requirements, and sensitivity analyses for key operational variables.

- Stakeholder Communication and Board Reporting: Preparation of executive summaries, board presentation materials, and progress reports delivered on a fortnightly basis throughout the engagement period.

## 3. Itemised Cost Breakdown

| Ref | Description of Service | Duration | Rate (NZD) | Hours | Amount (NZD incl. GST) |
| --- | --- | --- | --- | --- | --- |
| 01 | Operational Audit and Diagnostic Review – Business Consultant on-site and desk research | Weeks 1–3 | $285/hr | 96 | $41,232.00 |
| 02 | Strategic Market Expansion Planning – Tasman and Marlborough regions | Weeks 4–7 | $285/hr | 120 | $51,540.00 |
| 03 | Organisational Restructuring Advisory and workforce planning | Weeks 8–10 | $285/hr | 72 | $30,924.00 |
| 04 | Financial Modelling, Forecasting, and sensitivity analysis | Weeks 11–13 | $310/hr | 64 | $23,040.00 |
| 05 | Stakeholder Communication, Board Reporting, and final deliverable compilation | Weeks 14–16 | $285/hr | 48 | $19,872.00 |
| 06 | Travel and accommodation within the New Zealand Wellington metropolitan area | Full engagement | Actuals | — | $3,500.00 (est.) |
| Subtotal (incl. 15% GST) |  |  |  |  | $170,108.00 |
| Quotation Estimate Total – Business Consultant Services, New Zealand Wellington |  |  |  |  | $170,108.00 |

## 4. Payment Terms

Payment for this Quotation Estimate shall be made in three instalments: 30% upon execution of the engagement letter, 40% upon completion of Week 8 (mid-project milestone), and the remaining 30% upon delivery of the final report and all supporting deliverables. Invoices will be issued to the accounts payable department of Harbourview Logistics Group Ltd and are payable within 20 business days of the invoice date in accordance with standard commercial practice in New Zealand Wellington. Late payments will attract interest at the rate prescribed under the New Zealand Late Payment of Commercial Debts (Interest) Act 2002.

## 5. Terms and Conditions

- This Quotation Estimate is valid for 30 calendar days from the date of issue. Should the client wish to proceed after the expiry date, the Business Consultant team reserves the right to revise rates to reflect any changes in market conditions or resource availability in the New Zealand Wellington region.

- All intellectual property, reports, models, and strategic documents produced under this engagement shall become the sole property of Harbourview Logistics Group Ltd upon full and final payment.

- The Business Consultant and all team members are bound by strict confidentiality obligations in accordance with the New Zealand Privacy Act 2020. No client data, financial information, or strategic plans will be disclosed to third parties without written consent.

- Any variation to the scope of work must be agreed in writing by both parties prior to commencement of additional services. Variations exceeding 10% of the total Quotation Estimate value will require a formal amendment to this document.

- This engagement is governed by the laws of New Zealand. Any disputes arising from this Quotation Estimate or the services rendered shall be resolved through mediation in New Zealand Wellington before any litigation is commenced in the District Court of Wellington.

- Apex Strategic Advisory Ltd carries professional indemnity insurance with a coverage limit of NZD $10,000,000, as is standard for a Business Consultant operating in the New Zealand Wellington professional services sector.

## 6. Assumptions and Exclusions

This Quotation Estimate assumes that the client will provide timely access to all relevant financial records, operational data, and key personnel. It does not include legal advice, tax advisory services, or implementation of the recommended strategies. Should the client require a Business Consultant to remain on a retainer basis post-engagement for ongoing advisory support, a separate Quotation Estimate will be prepared at that time.

## 7. Acceptance of Quotation Estimate

By signing below, the client acknowledges that it has read, understood, and accepts the terms, conditions, scope of work, and pricing set out in this Quotation Estimate for Business Consultant services to be delivered in New Zealand Wellington.

For and on behalf of Harbourview Logistics Group Ltd:

Name: _________________________    Title: _________________________

Signature: _________________________    Date: _________________________

For and on behalf of Apex Strategic Advisory Ltd:

Name: Dr. Margaret Chen    Title: Senior Business Consultant

Signature: _________________________    Date: _________________________

Apex Strategic Advisory Ltd | Level 4, 128 Lambton Quay, Wellington, New Zealand | +64 4 382 5500 | enquiries@apexstrategic.co.nz

This Quotation Estimate was prepared for use in New Zealand Wellington and is subject to the terms and conditions stated herein. Document Ref: QTE-2025-WLG-0047