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Quotation Estimate
Quotation Estimate
Carpenter Services – Residential & Commercial Woodwork – Brazil Brasília
Quotation Details
Quotation No.: QE-2025-0847
Date of Issue: 15 June 2025
Valid Until: 15 July 2025 (30 days)
Service Location: Brazil Brasília, Federal District
Client Information
Client Name: Sr. Ricardo Almeida Santos
Address: SHIS QI 05, Lote 12, Lago Sul, Brasília – DF
CPF: ***.456.789-**
Contact: +55 (61) 99876-5432
1. Scope of Work – Carpenter Services in Brazil Brasília
This Quotation Estimate is issued by Brasília Carpentry & Woodworks Ltda. to provide comprehensive Carpenter services for the residential property located in the Lago Sul neighborhood of Brazil Brasília. Our team of licensed and experienced carpenters will execute all woodwork, cabinetry, structural timber, and finishing tasks as detailed below. All materials and labor comply with the municipal building regulations of the Federal District and the national standards established by ABNT (Associação Brasileira de Normas Técnicas).
2. Itemized Quotation Estimate Breakdown
	Item
	Description of Carpenter Work
	Quantity
	Unit
	Unit Price (BRL)
	Subtotal (BRL)

	01
	Custom kitchen cabinetry in solid Brazilian cherry wood (jacarandá-da-bahia), including upper and lower cabinets, countertop installation, and hardware fitting
	1
	Set
	R$ 18,500.00
	R$ 18,500.00

	02
	Master bedroom wardrobe system with sliding doors, internal shelving, and LED strip lighting integration
	1
	Set
	R$ 9,800.00
	R$ 9,800.00

	03
	Structural timber reinforcement and repair of existing wooden beams in the living room ceiling (approximately 12 linear meters)
	12
	Linear m
	R$ 320.00
	R$ 3,840.00

	04
	Installation of solid wood flooring (ipe hardwood) in the main living area, including subfloor preparation, sanding, and three-coat polyurethane finish
	45
	m²
	R$ 285.00
	R$ 12,825.00

	05
	Custom built-in bookshelf and home office desk unit in engineered oak veneer, with cable management and integrated storage drawers
	1
	Set
	R$ 7,200.00
	R$ 7,200.00

	06
	Exterior wooden pergola construction (12 m²) using treated eucalyptus timber, including foundation posts, roofing slats, and anti-termite treatment
	1
	Set
	R$ 11,400.00
	R$ 11,400.00

	07
	Interior door replacement (4 doors) – solid core, pre-hung, with matching trim, hinges, and handles
	4
	Doors
	R$ 1,150.00
	R$ 4,600.00

	08
	General carpenter labor supervision, site cleanup, and final quality inspection across all work areas in Brazil Brasília
	1
	Lump sum
	R$ 3,500.00
	R$ 3,500.00

	TOTAL QUOTATION ESTIMATE (BRL)
	R$ 71,665.00


3. Materials and Specifications
All timber and wood products used in this Quotation Estimate shall be sourced from certified sustainable forestry operations in compliance with IBAMA regulations. The Carpenter team will utilize only materials with valid FSC or equivalent certification. Hardware, adhesives, and finishes will be of premium grade, suitable for the tropical climate conditions prevalent in Brazil Brasília, where humidity levels and intense solar exposure demand durable, weather-resistant wood treatments.
4. Project Timeline
The estimated duration for full completion of all Carpenter works outlined in this Quotation Estimate is 45 business days from the date of contract signing and receipt of the initial payment. The project will be executed in phases: structural and framing work (Weeks 1–2), cabinetry and built-in fabrication (Weeks 3–5), flooring and finishing (Weeks 6–7), and final inspection and handover (Week 8). The schedule is subject to weather conditions and material availability in the Brasília metropolitan area.
5. Payment Terms
Payment for this Quotation Estimate shall be made in the following installments via bank transfer (TED/PIX) to the account of Brasília Carpentry & Woodworks Ltda.:
1. 40% advance payment (R$ 28,666.00) upon signing of the service contract and approval of this Quotation Estimate.
1. 35% progress payment (R$ 25,082.75) upon completion of structural carpentry and cabinetry installation (end of Week 5).
1. 25% final payment (R$ 17,916.25) upon final inspection, client sign-off, and delivery of the completed project in Brazil Brasília.
6. Terms and Conditions
1. This Quotation Estimate is valid for 30 calendar days from the date of issue. After this period, prices may be adjusted to reflect changes in material costs, labor rates, or exchange rates applicable in Brazil Brasília.
1. All Carpenter services are guaranteed for a period of 12 months from the date of final acceptance, covering workmanship defects. Material warranties are governed by the respective manufacturers' terms.
1. The client is responsible for obtaining all necessary permits and approvals from the Brasília municipal building authority (Secretaria de Urbanismo e Habitação) prior to the commencement of structural carpentry work.
1. Any additional work or changes requested by the client beyond the scope defined in this Quotation Estimate will be subject to a separate written amendment and additional cost estimate.
1. The Carpenter team will observe all occupational health and safety standards (NR-18, NR-35) and will maintain the work site in Brazil Brasília in a clean and orderly condition at all times.
1. Disputes arising from this Quotation Estimate shall be resolved through the Consumer Protection Agency (PROCON-DF) or the competent courts of the Federal District, Brazil Brasília.
1. This Quotation Estimate does not constitute a binding contract until both parties have signed the formal service agreement.
7. Acceptance and Signatures
By signing below, both parties acknowledge and accept the terms, scope, and pricing set forth in this Quotation Estimate for Carpenter services to be performed in Brazil Brasília.
Brasília Carpentry & Woodworks Ltda.
Authorized Representative – Carpenter Services
Date: _______________
Client – Sr. Ricardo Almeida Santos
CPF: ***.456.789-**
Date: _______________
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