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QUOTATION ESTIMATE
Carpenter Services & Woodwork Solutions
Medellín, Antioquia, Colombia
Quotation No.: QTE-MDE-2025-04782
Date of Issue: June 12, 2025
Valid Until: July 12, 2025
Carpenter Services – Colombia Medellín
1. PARTIES INVOLVED
Service Provider (Carpenter)
Company: Taller de Carpintería Los Robles S.A.S.
Lead Carpenter: Ing. Carlos Alberto Restrepo M.
NIT: 901.234.567-8
Address: Calle 43 # 52A-18, Barrio El Poblado, Medellín, Antioquia, Colombia
Phone: +57 (604) 444 5566
Email: cotizaciones@carpinterialosrobles.co
Client
Company: Hotel Andino Suites S.A.S.
Contact Person: Lic. María Fernanda Ospina
NIT: 830.987.654-1
Address: Cra. 43A # 6-55, Barrio La Candelaria, Medellín, Antioquia, Colombia
Phone: +57 (604) 333 2211
Email: compras@hotelandinousuites.co
2. SCOPE OF WORK – CARPENTER PROJECT DESCRIPTION
This Quotation Estimate is issued by our certified Carpenter team to provide comprehensive woodwork and carpentry services for the renovation of the lobby, reception area, and twelve (12) guest rooms at Hotel Andino Suites, located in the heart of Colombia Medellín. The project encompasses custom furniture fabrication, interior wood paneling, built-in storage solutions, and finishing work using premium hardwoods sourced from certified sustainable forestry operations in the Antioquia region.
The Carpenter assigned to this project, Ing. Carlos Alberto Restrepo M., holds over twenty-two years of professional experience in residential and commercial carpentry within the Medellín metropolitan area. All work will comply with the Colombian National Technical Standards (NTC) for woodwork and construction, as well as the municipal building regulations established by the Alcaldía de Medellín.
3. ITEMIZED COST BREAKDOWN
	No.
	Description of Carpenter Service
	Unit
	Quantity
	Unit Price (COP)
	Subtotal (COP)

	1
	Custom walnut wood reception desk (3.2m x 1.1m x 1.05m) with integrated LED lighting and cable management
	Unit
	1
	8,500,000
	8,500,000

	2
	Interior wood paneling in natural oak – lobby walls (approx. 185 sq. meters)
	sq. m
	185
	145,000
	26,825,000

	3
	Built-in wardrobe systems per guest room (2.4m x 1.8m x 0.65m) with sliding doors and interior shelving
	Unit
	12
	3,200,000
	38,400,000

	4
	Custom bedside tables and writing desks per guest room (cedar wood, hand-finished)
	Set
	12
	1,850,000
	22,200,000

	5
	Wooden staircase railing and balustrade replacement (18 steps, mahogany)
	Unit
	1
	12,750,000
	12,750,000

	6
	Custom bar counter and back-bar shelving for the hotel lounge (teak wood, 4.5m linear)
	Unit
	1
	9,800,000
	9,800,000

	7
	Doors and door frames – solid wood (12 guest rooms + 4 service areas), including hardware installation
	Unit
	16
	1,450,000
	23,200,000

	8
	Finishing, sanding, and application of three coats of water-based polyurethane varnish on all woodwork
	Global
	1
	7,500,000
	7,500,000

	9
	On-site supervision, project management, and final quality inspection by lead Carpenter
	Global
	1
	4,200,000
	4,200,000

	10
	Waste removal, site cleanup, and disposal in compliance with Medellín municipal environmental regulations
	Global
	1
	1,800,000
	1,800,000

	SUBTOTAL (COP)
	155,175,000

	VAT – IVA (19%)
	29,483,250

	TOTAL ESTIMATED COST (COP)
	184,658,250


* All prices are expressed in Colombian Pesos (COP). Exchange rate reference at time of quotation: 1 USD ≈ 3,950 COP. Total in USD equivalent: approximately USD 46,749.
4. PROJECT TIMELINE
	Phase
	Activity
	Duration
	Estimated Start

	Phase 1
	Site measurement, material procurement, and workshop fabrication
	15 working days
	July 1, 2025

	Phase 2
	On-site installation of paneling, doors, and structural woodwork
	20 working days
	July 16, 2025

	Phase 3
	Installation of custom furniture, wardrobes, and bar counter
	12 working days
	August 11, 2025

	Phase 4
	Finishing, varnishing, quality inspection, and handover
	8 working days
	August 25, 2025


Total estimated project duration: 55 working days (approximately 11 calendar weeks).
5. TERMS AND CONDITIONS
· Validity: This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After this period, prices may be adjusted due to fluctuations in raw material costs in the Colombia Medellín market.
· Payment Terms: 40% advance payment upon contract signing; 35% upon completion of Phase 2; 25% upon final delivery and client sign-off. All payments to be made via bank transfer to the account specified in the commercial contract.
· Warranty: The Carpenter service includes a twelve (12) month warranty on all workmanship and structural integrity. Material defects are covered under the manufacturer's warranty terms.
· Materials: All wood species used (walnut, oak, cedar, mahogany, teak) are sourced from legally harvested, FSC-certified suppliers in the Antioquia and Chocó regions of Colombia. No illegally logged timber will be used under any circumstance.
· Change Orders: Any modifications to the scope of work requested by the client after contract execution will be subject to a written change order with updated pricing and timeline adjustments.
· Regulatory Compliance: All work performed in Colombia Medellín will adhere to the applicable regulations of the Secretaría de Planeación de Medellín, the Colombian Ministry of Environment (Ministerio de Ambiente), and the NTC technical standards for carpentry and woodwork.
· Insurance: The service provider maintains comprehensive liability insurance and workers' compensation coverage (Arla) for all personnel on site.
· Dispute Resolution: Any disputes arising from this Quotation Estimate or the subsequent contract shall be resolved through mediation in the city of Medellín, Antioquia, Colombia, in accordance with Colombian civil law.
6. ACCEPTANCE AND SIGNATURES
By signing below, both parties acknowledge that this Quotation Estimate accurately reflects the scope, cost, and terms of the Carpenter services to be rendered in Colombia Medellín. This document serves as the basis for the formal commercial contract to be executed within five (5) business days of mutual acceptance.
Ing. Carlos Alberto Restrepo M.
Lead Carpenter / Project Director
Taller de Carpintería Los Robles S.A.S.
Date: _______________
Lic. María Fernanda Ospina
Procurement Manager
Hotel Andino Suites S.A.S.
Date: _______________
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