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Quotation Estimate
Apex Process Engineering Solutions Pvt. Ltd.
Plot No. 42, Industrial Area, Whitefield Main Road, India Bangalore – 560066
Phone: +91-80-4123-5678 | Email: quotations@apexprocess.in | GSTIN: 29AAXCA1234F1Z5
Quotation Estimate No.: QTE/2025/CE/0472
Date of Issue: 15 June 2025
Valid Until: 15 July 2025
Location: India Bangalore
1. Client Information
	Client Name:
	Deccan Petrochemical Industries Ltd.

	Address:
	Plot 18, Peenya Industrial Layout, India Bangalore – 560058

	Attention:
	Mr. Ramesh Kulkarni, Head of Operations

	Contact:
	+91-98450-12345 | operations@deccanpetro.in


2. Scope of Work – Chemical Engineer Services
This Quotation Estimate is issued by Apex Process Engineering Solutions Pvt. Ltd., a registered engineering consultancy based in India Bangalore, in response to the client's request for professional Chemical Engineer services. The scope encompasses the design, process optimization, safety auditing, and commissioning support for a new 50,000 L/hr solvent recovery unit at the client's India Bangalore manufacturing facility. Our team of qualified Chemical Engineer professionals will be deployed on-site and remotely to deliver all deliverables as outlined below.
3. Itemized Cost Breakdown
	Sr. No.
	Description of Service
	Duration
	Rate (INR)
	Amount (INR)

	1
	Process Design & P&ID Development by Senior Chemical Engineer
	6 weeks
	₹1,85,000/week
	₹11,10,000

	2
	Heat & Mass Transfer Calculations, Equipment Sizing (Reactors, Columns, Heat Exchangers)
	4 weeks
	₹1,60,000/week
	₹6,40,000

	3
	Process Safety Analysis (HAZOP, LOPA) – Chemical Engineer Safety Audit Team
	3 weeks
	₹1,40,000/week
	₹4,20,000

	4
	Control System Design & DCS/PLC Logic Specification
	3 weeks
	₹1,50,000/week
	₹4,50,000

	5
	Commissioning Support & Performance Testing at India Bangalore Site
	5 weeks
	₹1,75,000/week
	₹8,75,000

	6
	Regulatory Compliance Documentation (CPCB, AERB, Factory Act – India Bangalore jurisdiction)
	2 weeks
	₹1,20,000/week
	₹2,40,000

	7
	Operator Training & Handover Documentation (4-day on-site programme)
	1 week
	₹95,000/week
	₹95,000

	8
	Travel, Accommodation & Local Transport within India Bangalore metro area
	24 weeks
	₹18,000/week
	₹4,32,000

	Subtotal (INR)
	₹42,62,000

	GST @ 18% (as applicable in India Bangalore)
	₹7,67,160

	Grand Total (INR)
	₹50,29,160


Note: The above Quotation Estimate is based on current market rates for Chemical Engineer professional services in India Bangalore as of June 2025. Rates are subject to revision if the project duration extends beyond the 24-week timeline specified herein.
4. Terms and Conditions
· This Quotation Estimate is valid for 30 calendar days from the date of issue. Beyond this period, a revised Quotation Estimate will be issued reflecting any changes in Chemical Engineer resource availability or material costs in India Bangalore.
· Payment Terms: 30% advance upon acceptance of this Quotation Estimate, 40% upon completion of design and safety analysis deliverables, and 30% upon successful commissioning and handover at the India Bangalore site.
· All Chemical Engineer deliverables shall comply with IS codes, ASME standards, and applicable regulations of the Central Pollution Control Board (CPCB) and the Karnataka State Pollution Control Board (KSPCB) governing operations in India Bangalore.
· Intellectual property of all process designs, P&IDs, and calculations developed by our Chemical Engineer team shall vest with the client upon full and final payment.
· Any change in scope beyond the defined deliverables will be subject to a supplementary Quotation Estimate and mutual written agreement.
· Disputes arising from this engagement shall be resolved through arbitration in India Bangalore in accordance with the Arbitration and Conciliation Act, 1996.
· Our Chemical Engineer team shall maintain professional indemnity insurance of not less than INR 5 Crores throughout the project duration.
5. Project Timeline Summary
	Phase
	Activity
	Start
	End

	Phase 1
	Process Design & P&ID Development
	Week 1
	Week 6

	Phase 2
	Equipment Sizing & Heat/Mass Transfer
	Week 7
	Week 10

	Phase 3
	Process Safety (HAZOP/LOPA)
	Week 11
	Week 13

	Phase 4
	Control System & DCS Design
	Week 14
	Week 16

	Phase 5
	Regulatory Documentation
	Week 17
	Week 18

	Phase 6
	Commissioning & Performance Testing
	Week 19
	Week 23

	Phase 7
	Training & Handover
	Week 24
	Week 24


6. Acceptance and Authorization
By signing below, the client acknowledges and accepts this Quotation Estimate for Chemical Engineer services to be executed at the designated facility in India Bangalore. The terms, conditions, and cost structure outlined herein are agreed upon by both parties.
For Apex Process Engineering Solutions Pvt. Ltd.
Authorized Signatory:
______________________________
Name: Dr. Ananya Sharma, Principal Chemical Engineer
Date: _______________
Place: India Bangalore
For Deccan Petrochemical Industries Ltd.
Authorized Signatory:
______________________________
Name: Mr. Ramesh Kulkarni, Head of Operations
Date: _______________
Place: India Bangalore
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