# Quotation Estimate - Chemical Engineer Services - India Bangalore

# Quotation Estimate

Apex Process Engineering Solutions Pvt. Ltd.

Plot No. 42, Industrial Area, Whitefield Main Road, India Bangalore – 560066

Phone: +91-80-4123-5678 | Email: quotations@apexprocess.in | GSTIN: 29AAXCA1234F1Z5

Quotation Estimate No.: QTE/2025/CE/0472

Date of Issue: 15 June 2025

Valid Until: 15 July 2025

Location: India Bangalore

## 1. Client Information

| Client Name: | Deccan Petrochemical Industries Ltd. |
| --- | --- |
| Address: | Plot 18, Peenya Industrial Layout, India Bangalore – 560058 |
| Attention: | Mr. Ramesh Kulkarni, Head of Operations |
| Contact: | +91-98450-12345 ¦ operations@deccanpetro.in |

## 2. Scope of Work – Chemical Engineer Services

This Quotation Estimate is issued by Apex Process Engineering Solutions Pvt. Ltd., a registered engineering consultancy based in India Bangalore, in response to the client's request for professional Chemical Engineer services. The scope encompasses the design, process optimization, safety auditing, and commissioning support for a new 50,000 L/hr solvent recovery unit at the client's India Bangalore manufacturing facility. Our team of qualified Chemical Engineer professionals will be deployed on-site and remotely to deliver all deliverables as outlined below.

## 3. Itemized Cost Breakdown

| Sr. No. | Description of Service | Duration | Rate (INR) | Amount (INR) |
| --- | --- | --- | --- | --- |
| 1 | Process Design & P&ID Development by Senior Chemical Engineer | 6 weeks | ₹1,85,000/week | ₹11,10,000 |
| 2 | Heat & Mass Transfer Calculations, Equipment Sizing (Reactors, Columns, Heat Exchangers) | 4 weeks | ₹1,60,000/week | ₹6,40,000 |
| 3 | Process Safety Analysis (HAZOP, LOPA) – Chemical Engineer Safety Audit Team | 3 weeks | ₹1,40,000/week | ₹4,20,000 |
| 4 | Control System Design & DCS/PLC Logic Specification | 3 weeks | ₹1,50,000/week | ₹4,50,000 |
| 5 | Commissioning Support & Performance Testing at India Bangalore Site | 5 weeks | ₹1,75,000/week | ₹8,75,000 |
| 6 | Regulatory Compliance Documentation (CPCB, AERB, Factory Act – India Bangalore jurisdiction) | 2 weeks | ₹1,20,000/week | ₹2,40,000 |
| 7 | Operator Training & Handover Documentation (4-day on-site programme) | 1 week | ₹95,000/week | ₹95,000 |
| 8 | Travel, Accommodation & Local Transport within India Bangalore metro area | 24 weeks | ₹18,000/week | ₹4,32,000 |
| Subtotal (INR) |  |  |  | ₹42,62,000 |
| GST @ 18% (as applicable in India Bangalore) |  |  |  | ₹7,67,160 |
| Grand Total (INR) |  |  |  | ₹50,29,160 |

Note: The above Quotation Estimate is based on current market rates for Chemical Engineer professional services in India Bangalore as of June 2025. Rates are subject to revision if the project duration extends beyond the 24-week timeline specified herein.

## 4. Terms and Conditions

- This Quotation Estimate is valid for 30 calendar days from the date of issue. Beyond this period, a revised Quotation Estimate will be issued reflecting any changes in Chemical Engineer resource availability or material costs in India Bangalore.

- Payment Terms: 30% advance upon acceptance of this Quotation Estimate, 40% upon completion of design and safety analysis deliverables, and 30% upon successful commissioning and handover at the India Bangalore site.

- All Chemical Engineer deliverables shall comply with IS codes, ASME standards, and applicable regulations of the Central Pollution Control Board (CPCB) and the Karnataka State Pollution Control Board (KSPCB) governing operations in India Bangalore.

- Intellectual property of all process designs, P&IDs, and calculations developed by our Chemical Engineer team shall vest with the client upon full and final payment.

- Any change in scope beyond the defined deliverables will be subject to a supplementary Quotation Estimate and mutual written agreement.

- Disputes arising from this engagement shall be resolved through arbitration in India Bangalore in accordance with the Arbitration and Conciliation Act, 1996.

- Our Chemical Engineer team shall maintain professional indemnity insurance of not less than INR 5 Crores throughout the project duration.

## 5. Project Timeline Summary

| Phase | Activity | Start | End |
| --- | --- | --- | --- |
| Phase 1 | Process Design & P&ID Development | Week 1 | Week 6 |
| Phase 2 | Equipment Sizing & Heat/Mass Transfer | Week 7 | Week 10 |
| Phase 3 | Process Safety (HAZOP/LOPA) | Week 11 | Week 13 |
| Phase 4 | Control System & DCS Design | Week 14 | Week 16 |
| Phase 5 | Regulatory Documentation | Week 17 | Week 18 |
| Phase 6 | Commissioning & Performance Testing | Week 19 | Week 23 |
| Phase 7 | Training & Handover | Week 24 | Week 24 |

## 6. Acceptance and Authorization

By signing below, the client acknowledges and accepts this Quotation Estimate for Chemical Engineer services to be executed at the designated facility in India Bangalore. The terms, conditions, and cost structure outlined herein are agreed upon by both parties.

### For Apex Process Engineering Solutions Pvt. Ltd.

Authorized Signatory:

______________________________

Name: Dr. Ananya Sharma, Principal Chemical Engineer

Date: _______________

Place: India Bangalore

### For Deccan Petrochemical Industries Ltd.

Authorized Signatory:

______________________________

Name: Mr. Ramesh Kulkarni, Head of Operations

Date: _______________

Place: India Bangalore

This Quotation Estimate document is generated electronically and is valid without a physical stamp. | Apex Process Engineering Solutions Pvt. Ltd., India Bangalore

Page 1 of 1 | Document Ref: QTE/2025/CE/0472 | Confidential – For Client Use Only