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1. Client Information
	Client Name:
	Zimbabwe National Industrial Development Corporation (ZINIDC)

	Project Site:
	Chitungwiza Industrial Area, Zimbabwe Harare Metropolitan Region

	Contact Person:
	Mr. T. Moyo – Head of Procurement

	Email:
	t.moyo@zinidc.co.zw


2. Scope of Work – Chemical Engineer Services
This Quotation Estimate is issued by Apex Chemical Engineering Solutions (Pvt) Ltd in response to the request for professional Chemical Engineer consultancy services for the design, commissioning, and operational optimisation of a 5,000 L/hour water treatment and chemical dosing plant located in the Chitungwiza Industrial Area, Zimbabwe Harare. The scope encompasses all engineering deliverables, site supervision, regulatory compliance, and post-commissioning support as detailed below.
3. Itemised Cost Breakdown
	Ref
	Description of Service
	Duration / Qty
	Unit Rate (USD)
	Amount (USD)

	3.1
	Initial site survey, process audit, and feasibility assessment by a senior Chemical Engineer at the Zimbabwe Harare project site
	5 working days
	450.00
	2,250.00

	3.2
	Development of process flow diagrams (PFDs), piping and instrumentation diagrams (P&IDs), and equipment specifications for the water treatment plant
	15 working days
	380.00
	5,700.00

	3.3
	Chemical dosing system design, reactor sizing, and mass/energy balance calculations performed by the assigned Chemical Engineer
	10 working days
	420.00
	4,200.00

	3.4
	Regulatory compliance review with the Zimbabwe National Environment Management Agency (NEMA) and the Harare City Council environmental health department
	7 working days
	350.00
	2,450.00

	3.5
	On-site supervision of mechanical and electrical installation, including coordination with local contractors in Zimbabwe Harare
	20 working days
	500.00
	10,000.00

	3.6
	Commissioning, performance testing, and handover documentation prepared by the lead Chemical Engineer
	10 working days
	480.00
	4,800.00

	3.7
	Operator training programme (4 sessions) for ZINIDC plant staff on safe chemical handling, process control, and troubleshooting
	4 days
	600.00
	2,400.00

	3.8
	Post-commissioning warranty support and remote technical advisory for a period of 90 days
	90 days
	150.00
	1,350.00

	Subtotal (USD)
	33,150.00

	VAT @ 15% (Zimbabwe)
	4,972.50

	TOTAL AMOUNT DUE (USD)
	38,122.50


4. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Beyond this period, pricing may be subject to revision due to fluctuations in the USD/ZWL exchange rate or changes in material costs within Zimbabwe Harare.
· All services shall be rendered by a qualified and registered Chemical Engineer holding a valid practising certificate issued by the Engineering Council of Zimbabwe (ECZ). The lead engineer for this project is Eng. R. Chikafu, MSc (Chemical Engineering), ECZ Reg. No. CE-2014-0891.
· Payment terms: 30% advance payment upon acceptance of this quotation, 40% upon completion of design deliverables (Ref 3.2 and 3.3), and 30% upon successful commissioning and handover. All payments shall be made in United States Dollars (USD) to the company bank account in Harare.
· The Chemical Engineer and Apex Chemical Engineering Solutions (Pvt) Ltd shall comply with all applicable Zimbabwean legislation, including the Environmental Management Act [Chapter 20:27], the Factories and Works Act, and the Occupational Safety and Health Act.
· Any variation in scope beyond the items listed in Section 3 shall be subject to a supplementary Quotation Estimate issued in writing and accepted by both parties before additional work commences.
· All intellectual property, design documents, and process data generated under this engagement shall become the property of the client upon full payment.
· Disputes arising from this agreement shall be resolved through arbitration in Zimbabwe Harare in accordance with the Arbitration Act [Chapter 7:15] of the Laws of Zimbabwe.
· The contractor shall maintain adequate professional indemnity and public liability insurance throughout the duration of the project.
5. Assumptions and Exclusions
This Quotation Estimate assumes that the client will provide safe access to the project site in Zimbabwe Harare, existing utility connections (water, electricity, drainage), and all necessary permits for construction activity. The following are excluded from this estimate: procurement of major process equipment (pumps, reactors, tanks), civil and structural works, electrical switchgear supply, and any third-party laboratory testing fees. Should the Chemical Engineer identify additional requirements during the site survey, a revised quotation will be issued within five (5) working days.
6. Acceptance and Authorisation
By signing below, the client acknowledges and accepts this Quotation Estimate for Chemical Engineer services in Zimbabwe Harare in full, including all terms and conditions set out herein.
For and on behalf of the Client:
Name: ______________________________
Title: ______________________________
Signature: ______________________________
Date: ______________________________
For and on behalf of Apex Chemical Engineering Solutions (Pvt) Ltd:
Name: Eng. R. Chikafu
Title: Lead Chemical Engineer / Director
Signature: ______________________________
Date: ______________________________
Apex Chemical Engineering Solutions (Pvt) Ltd | 142 Samora Machel Avenue, Harare, Zimbabwe
This Quotation Estimate is the property of Apex Chemical Engineering Solutions (Pvt) Ltd and is issued solely for the client named herein.
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