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Service Provider
Meridian Civil Engineering Consultants Ltd.
House 42, Road 11, Banani, Dhaka-1213
Bangladesh Dhaka, Metropolitan Area
Tel: +880-2-9887654 | Email: info@meridiancivil.com.bd
Trade License No: DL-2019-45821
Client / Recipient
Mr. Abdul Karim Chowdhury
Plot 7, Sector 10, Uttara, Dhaka-1230
Bangladesh Dhaka
Tel: +880-1711-234567
Email: a.k.chowdhury@email.com
	Quotation Estimate No.:
	MCE/QE/2025/0347

	Date of Issue:
	15 June 2025

	Valid Until:
	15 July 2025 (30 calendar days)

	Project Location:
	Uttara, Bangladesh Dhaka

	Project Type:
	Residential Building Construction (G+3 Floors)

	Currency:
	Bangladeshi Taka (BDT / ৳)


1. Scope of Work – Civil Engineer Services
This Quotation Estimate is issued by Meridian Civil Engineering Consultants Ltd. to provide comprehensive Civil Engineer professional services for the design, supervision, and project management of a G+3 residential building located in Uttara, Bangladesh Dhaka. The scope encompasses all structural, architectural, and geotechnical engineering deliverables required under the Bangladesh National Building Code (BNBC 2020) and the local regulations of the Dhaka North City Corporation (DNCC).
2. Itemized Cost Breakdown
	Sr.
	Description of Civil Engineer Service
	Unit
	Qty
	Rate (BDT)
	Amount (BDT)

	1
	Site survey, topographic mapping, and geotechnical soil investigation for the plot in Bangladesh Dhaka
	Lot
	1
	85,000
	85,000

	2
	Architectural design and 3D rendering (G+3, 2,400 sq. ft. per floor) by licensed Civil Engineer
	Lot
	1
	320,000
	320,000

	3
	Structural design including RCC frame, foundation design, and seismic analysis per BNBC 2020 Zone-2 criteria for Bangladesh Dhaka
	Lot
	1
	275,000
	275,000

	4
	MEP (Mechanical, Electrical, Plumbing) coordination drawings and load calculations
	Lot
	1
	145,000
	145,000

	5
	DNCC building permit application preparation, submission, and follow-up in Bangladesh Dhaka
	Lot
	1
	65,000
	65,000

	6
	Construction supervision by resident Civil Engineer (full duration, approx. 14 months)
	Month
	14
	48,000
	672,000

	7
	Material quality testing (concrete cube, steel tensile, soil compaction) – 120 tests
	Test
	120
	2,800
	336,000

	8
	As-built drawings, final compliance certificate, and handover documentation
	Lot
	1
	95,000
	95,000

	9
	Project management, contractor coordination, and weekly progress reporting
	Month
	14
	22,000
	308,000

	10
	Contingency and miscellaneous (travel within Bangladesh Dhaka, printing, software licenses)
	Lot
	1
	55,000
	55,000

	Subtotal
	2,056,000

	VAT (5% as applicable in Bangladesh)
	102,800

	Grand Total (Quotation Estimate)
	2,158,800


3. Payment Schedule
The total Quotation Estimate amount of BDT 2,158,800 shall be disbursed in the following milestones, subject to satisfactory completion of each phase by the Civil Engineer team:
1. Advance (20%): BDT 431,760 – upon signing of the service agreement and receipt of this Quotation Estimate acceptance.
1. Design Completion (25%): BDT 539,700 – upon delivery and approval of all architectural, structural, and MEP drawings.
1. Permit Approval (10%): BDT 215,880 – upon successful issuance of the DNCC building permit for the Bangladesh Dhaka site.
1. Construction Supervision (35%): BDT 755,580 – payable in 14 equal monthly installments of BDT 53,970 during the active construction phase.
1. Final Handover (10%): BDT 215,880 – upon submission of as-built drawings, compliance certificate, and final site inspection.
4. Terms and Conditions
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiry date, rates may be revised due to market fluctuations in Bangladesh Dhaka.
1. All services shall be rendered by a licensed and registered Civil Engineer holding a valid license from the Bangladesh Council of Architects (BCA) and the Institution of Engineers, Bangladesh (IEB).
1. The project shall strictly comply with the Bangladesh National Building Code (BNBC 2020), DNCC by-laws, and all applicable environmental regulations of the Dhaka Metropolitan area.
1. Any variation or change order beyond the original scope must be approved in writing by both parties before execution. Additional costs will be itemized in a supplementary Quotation Estimate.
1. The Civil Engineer shall provide weekly progress reports and monthly site meeting minutes to the client throughout the project duration.
1. Payment delays exceeding fifteen (15) days shall attract a penalty of 1.5% per month on the outstanding balance.
1. This Quotation Estimate does not include the cost of construction materials, labor, or third-party statutory fees (e.g., utility connection charges, road tax) payable directly to relevant Bangladesh Dhaka authorities.
1. Disputes arising from this agreement shall be resolved through arbitration in Dhaka, Bangladesh, in accordance with the Arbitration Act, 2001 of Bangladesh.
1. The Civil Engineer team shall maintain professional indemnity insurance of not less than BDT 5,000,000 for the duration of the project.
5. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, scope, and pricing outlined herein for the engagement of the Civil Engineer services in Bangladesh Dhaka.
For Meridian Civil Engineering Consultants Ltd.
Authorized Signatory / Lead Civil Engineer
Name: Engr. Rafiqul Islam, MIEB
Date: _______________
For the Client
Name: Mr. Abdul Karim Chowdhury
Date: _______________
Note: This Quotation Estimate document is generated for the specific project referenced above and is non-transferable. All rates are quoted in Bangladeshi Taka (BDT). For any clarification regarding the Civil Engineer scope of work or the Bangladesh Dhaka regulatory requirements, please contact our project office at +880-2-9887654 or info@meridiancivil.com.bd. This document is confidential and intended solely for the named recipient.
