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QUOTATION ESTIMATE
Civil Engineer Professional Services
China Guangzhou | 广州市
	Quotation No.: QE-CIV-GZ-2025-0472
	Date of Issue: 15 June 2025

	Valid Until: 15 July 2025 (30 days)
	Currency: Chinese Yuan (CNY / RMB)

	Prepared By: Mr. Liang Wei, P.Eng. (Registered Civil Engineer, Guangdong Province)
	Project Location: Tianhe District, China Guangzhou


Client / Project Owner
Company: Guangzhou Pearl River Commercial Development Co., Ltd.
Address: No. 388, Tianhe Road, Tianhe District, Guangzhou, Guangdong Province, China
Contact Person: Ms. Zhang Yumei, Project Director
Telephone: +86-20-8876-XXXX
Email: yumei.zhang@pearlriverdev.cn
Service Provider
Firm: Guangzhou Structural & Civil Engineering Consultants Ltd.
Address: 12th Floor, International Finance Center, Zhujiang New Town, Tianhe District, Guangzhou, China
License No.: GD-CIV-2019-00847 (Guangdong Provincial Construction Engineering Survey & Design Qualification)
Lead Civil Engineer: Mr. Liang Wei, P.Eng. (Registration No. GDC-2012-44521)
Telephone: +86-20-3881-XXXX
1. Project Description and Scope of Work
This Quotation Estimate is issued by Guangzhou Structural & Civil Engineering Consultants Ltd. to provide comprehensive Civil Engineer services for the design review, structural assessment, and construction supervision of the Pearl River Commercial Tower, a 28-storey mixed-use building located in the Tianhe District of China Guangzhou. The Civil Engineer team engaged under this Quotation Estimate shall be responsible for ensuring full compliance with the National Standard of the People's Republic of China (GB 50010-2010 for concrete structures, GB 50011-2010 for seismic design, and GB 50009-2012 for wind and snow loads applicable in the Guangzhou region).
The scope of Civil Engineer work covered by this Quotation Estimate includes, but is not limited to: preliminary structural feasibility analysis; detailed structural design verification of the reinforced concrete frame-core system; geotechnical investigation review of the alluvial soil conditions typical of the Pearl River Delta in Guangzhou; foundation design assessment (bored pile foundation, approximately 420 piles at 1.2 m diameter); seismic performance evaluation per the 0.10 g design basic acceleration zone applicable to China Guangzhou; construction-stage structural monitoring and inspection; and final as-built documentation and handover certification.
All Civil Engineer deliverables shall be produced in accordance with the latest edition of the Chinese National Standards (GB) and the local Guangzhou Municipal Construction Engineering Quality Supervision requirements. The Civil Engineer shall coordinate with the architectural, mechanical, and electrical design teams to ensure integrated structural solutions throughout the project lifecycle.
2. Quotation Estimate – Itemised Cost Breakdown
	Item No.
	Description of Civil Engineer Service
	Duration
	Amount (CNY)

	01
	Preliminary structural feasibility study and site reconnaissance in China Guangzhou (Tianhe District)
	3 weeks
	185,000

	02
	Geotechnical investigation review and foundation design (bored pile system, 420 piles)
	5 weeks
	420,000

	03
	Detailed structural design verification – reinforced concrete frame-core, 28 storeys
	10 weeks
	680,000

	04
	Seismic performance analysis and wind load assessment per GB 50011 and GB 50009 for Guangzhou
	4 weeks
	295,000

	05
	Construction-stage structural supervision and monthly inspection reports (Civil Engineer on-site)
	18 months
	1,250,000

	06
	Structural health monitoring system design and commissioning (accelerometers, strain gauges)
	6 weeks
	340,000

	07
	As-built documentation, final structural certification, and handover to Guangzhou Municipal Authority
	4 weeks
	165,000

	08
	Coordination meetings, regulatory submissions, and liaison with Guangzhou Urban Planning Bureau
	Ongoing
	95,000

	Subtotal (Excluding VAT):
	3,430,000

	VAT (6% – Professional Services, PRC):
	205,800

	TOTAL QUOTATION ESTIMATE AMOUNT:
	3,635,800 CNY


3. Payment Schedule
	Milestone
	Trigger Event
	Percentage
	Amount (CNY)

	Advance Payment
	Upon contract execution
	20%
	727,160

	Design Phase Completion
	Approval of structural drawings by Guangzhou review authority
	30%
	1,090,740

	Construction Supervision (Monthly)
	Monthly progress certification by Civil Engineer
	40%
	1,454,320

	Final Handover
	Issuance of final structural certificate
	10%
	363,580


4. Terms and Conditions
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Any acceptance beyond this period requires written reconfirmation of pricing.
1. All Civil Engineer services shall be performed in strict compliance with the Construction Law of the People's Republic of China, the Regulations on the Quality Management of Construction Projects, and the applicable local ordinances of Guangzhou Municipality.
1. The Civil Engineer shall maintain professional indemnity insurance with a minimum coverage of CNY 10,000,000 per occurrence throughout the project duration.
1. Any variation in scope exceeding 10% of the total Quotation Estimate value shall be subject to a supplementary written agreement signed by both parties.
1. Payment terms are net thirty (30) days from the date of invoice issuance. Late payments shall attract interest at the rate of 0.05% per day as stipulated under PRC contract law.
1. All intellectual property rights in the structural design documents, calculation reports, and monitoring data produced by the Civil Engineer shall vest in the Client upon full payment.
1. Disputes arising from this Quotation Estimate shall be resolved through arbitration at the China International Economic and Trade Arbitration Commission (CIETAC), Guangzhou Sub-Commission.
1. The Civil Engineer reserves the right to suspend services if payment is overdue by more than fifteen (15) days, subject to seven (7) days' written notice.
5. Acceptance and Authorisation
By signing below, the Client acknowledges and accepts this Quotation Estimate for Civil Engineer services in China Guangzhou. This document, once countersigned, constitutes a binding agreement between the parties for the scope of work described herein.
	For the Service Provider:
Mr. Liang Wei, P.Eng.
Lead Civil Engineer, Guangzhou Structural & Civil Engineering Consultants Ltd.
Date: ____________________
	For the Client:
Ms. Zhang Yumei
Project Director, Guangzhou Pearl River Commercial Development Co., Ltd.
Date: ____________________
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