# Quotation Estimate - Civil Engineer Services - Egypt Cairo

# QUOTATION ESTIMATE

## Civil Engineer Professional Services

Ref: QE-CAIRO-2025-0472

Date of Issue: 15 June 2025  |  Valid Until: 15 July 2025

Location: Egypt Cairo, New Administrative Capital District

#### Prepared By (Civil Engineer Firm)

Nile Delta Civil Engineering Consultants

License No.: EGY-CE-2019-4482

Address: 142 El Tahrir Street, Downtown, Egypt Cairo

Tel: +20 2 2578 4431

Email: projects@niledelta-ce.com.eg

#### Prepared For (Client)

Al-Nile Real Estate Development Co.

Commercial Reg. No.: 882341

Address: 77 Corniche El Nil, Zamalek, Egypt Cairo

Tel: +20 2 2735 9910

Email: procurement@alnile-re.com

1. Project Overview

This Quotation Estimate is issued by Nile Delta Civil Engineering Consultants in response to the formal request for professional Civil Engineer services for the design, structural analysis, and construction supervision of a mixed-use residential and commercial complex located in the New Administrative Capital area of Egypt Cairo. The project encompasses a 12-story building with a basement parking level, ground-floor retail spaces, and residential units spanning floors two through twelve. The total built-up area is approximately 18,500 square meters, and the structure will be designed in full compliance with the Egyptian Building Code (EBC 2021), the Egyptian Seismic Design Code, and all applicable municipal regulations enforced by the Cairo Governorate and the New Capital Authority.

2. Scope of Civil Engineer Services

The following scope of work defines the complete set of professional services that our team of licensed Civil Engineer specialists will deliver under this Quotation Estimate:

| Item No. | Service Description | Duration | Unit | Unit Price (EGP) | Total (EGP) |
| --- | --- | --- | --- | --- | --- |
| 01 | Geotechnical site investigation coordination and soil report review for the Egypt Cairo project site | 3 weeks | Lump Sum | 185,000 | 185,000 |
| 02 | Architectural and structural design drawings (foundation, columns, beams, slabs, stairs, and retaining walls) | 10 weeks | Lump Sum | 1,250,000 | 1,250,000 |
| 03 | Structural analysis and finite element modeling using ETABS and SAP2000 software | 6 weeks | Lump Sum | 420,000 | 420,000 |
| 04 | MEP (Mechanical, Electrical, Plumbing) coordination with structural elements | 5 weeks | Lump Sum | 310,000 | 310,000 |
| 05 | Construction supervision and site inspection (full-time Civil Engineer resident on site) | 24 months | Monthly | 95,000 | 2,280,000 |
| 06 | Material testing coordination (concrete, rebar, soil compaction) per Egyptian standards | 24 months | Monthly | 38,000 | 912,000 |
| 07 | As-built documentation and final handover report preparation | 4 weeks | Lump Sum | 175,000 | 175,000 |
| 08 | Regulatory approvals and permit submissions to Egypt Cairo municipal authorities | 8 weeks | Lump Sum | 260,000 | 260,000 |
| Subtotal |  |  |  |  | 5,792,000 |
| VAT (14% – Egyptian Tax Authority) |  |  |  |  | 810,880 |
| GRAND TOTAL (EGP) |  |  |  |  | 6,602,880 |

3. Payment Schedule

Payment for the services outlined in this Quotation Estimate shall be made in the following installments, subject to satisfactory completion of each milestone as verified by the client's project manager:

- Advance Payment (20%): EGP 1,320,576 – payable within 10 business days of contract signing.

- Design Phase Completion (25%): EGP 1,650,720 – payable upon submission and approval of all structural drawings.

- Construction Supervision (45%): EGP 2,971,296 – payable in equal monthly installments of EGP 123,804 over 24 months.

- Final Handover (10%): EGP 660,288 – payable upon delivery of as-built documents and final inspection clearance.

4. Terms and Conditions

- This Quotation Estimate is valid for a period of thirty (30) calendar days from the date of issue. Any request for services beyond this validity period will require a revised Quotation Estimate reflecting current market rates in Egypt Cairo.

- All Civil Engineer services shall be performed by licensed professionals registered with the Egyptian Engineers Syndicate and holding valid practice permits for the Cairo Governorate.

- The client is responsible for providing timely access to the project site in Egypt Cairo, including all necessary safety equipment and site logistics for the resident Civil Engineer team.

- Any changes to the project scope, design modifications, or additional structural requirements beyond the original Quotation Estimate will be subject to a supplementary cost assessment and written change order.

- All deliverables, including drawings, reports, and digital files, shall be provided in both Arabic and English to satisfy Egypt Cairo regulatory and client requirements.

- Disputes arising from this Quotation Estimate shall be resolved through arbitration in accordance with the Egyptian Arbitration Law No. 27 of 1994, with the seat of arbitration in Cairo, Egypt.

- The Civil Engineer firm shall maintain professional indemnity insurance with a minimum coverage of EGP 10,000,000 for the duration of the project.

5. Acceptance and Authorization

By signing below, both parties acknowledge and agree to the terms, scope, and pricing set forth in this Quotation Estimate for the Civil Engineer services to be rendered in Egypt Cairo.

For Nile Delta Civil Engineering Consultants

Eng. Mahmoud El-Sayed Hassan

Principal Civil Engineer & Managing Director

License No.: EGY-CE-2003-1187

For Al-Nile Real Estate Development Co.

Mr. Khaled Farouk Abdel-Rahman

Director of Procurement & Projects

Authorized Signatory

Nile Delta Civil Engineering Consultants — 142 El Tahrir Street, Downtown, Egypt Cairo — License No. EGY-CE-2019-4482

This Quotation Estimate document is confidential and intended solely for the named recipient. Unauthorized reproduction or distribution is prohibited.

Page 1 of 1 — Generated: 15 June 2025