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Quotation Estimate
Quotation Details
Quotation No.: ACE/QE/2025/0047
Date Issued: 12 June 2025
Valid Until: 12 July 2025 (30 days)
Project Location: Nigeria Abuja, FCT
Client Information
Client Name: Federal Capital Development Authority (FCDA)
Attention: Engr. Adebayo Okafor, Project Director
Address: FCDA Headquarters, Garki, Abuja, Nigeria
Contact: +234 (0) 909 221 4456
1. Introduction and Scope of Work
This Quotation Estimate is formally submitted by Apex Civil Engineering & Infrastructure Ltd. to the Federal Capital Development Authority for the provision of professional Civil Engineer services in the planning, design, supervision, and quality assurance of the proposed 4.2-kilometre dual-carriageway road improvement project along the Abuja–Kaduna Expressway corridor in Nigeria Abuja. This Quotation Estimate covers all engineering consultancy deliverables required from the initial site investigation phase through to the final handover and defect liability period.
The Civil Engineer team assigned to this project in Nigeria Abuja shall comprise a Lead Structural and Geotechnical Engineer (COREN-registered), two Senior Civil Engineers, one Quantity Surveyor, one Environmental Impact Assessment Specialist, and a dedicated site supervision crew of four technicians. All personnel shall be physically stationed at the project site in Nigeria Abuja for the duration of the engagement.
2. Itemized Cost Breakdown
S/N
Description of Service
Duration
Unit Rate (NGN)
Total Amount (NGN)
1
Site reconnaissance, topographic survey, and geotechnical investigation for the 4.2 km corridor in Nigeria Abuja
4 weeks
—
4,850,000
2
Preliminary and detailed design of road alignment, drainage, and retaining structures by the Civil Engineer team
8 weeks
—
12,400,000
3
Environmental Impact Assessment (EIA) and community engagement in Nigeria Abuja
6 weeks
—
3,750,000
4
Preparation of tender documents, bill of quantities, and technical specifications
4 weeks
—
2,900,000
5
Construction supervision, quality control, and progress monitoring (Civil Engineer on-site)
26 weeks
—
28,600,000
6
As-built documentation, final inspection, and defect liability supervision
12 weeks
—
5,200,000
7
Project management, reporting, and client liaison in Nigeria Abuja
Full duration
—
4,100,000
8
Contingency and unforeseen site conditions (5% of subtotal)
—
—
3,140,000
Subtotal (NGN)
65,940,000
VAT @ 7.5% (NGN)
4,945,500
GRAND TOTAL (NGN)
70,885,500
3. Payment Schedule
This Quotation Estimate proposes the following milestone-based payment structure, subject to satisfactory acceptance of deliverables by the client in Nigeria Abuja:
· Milestone 1 (20%): Upon contract execution and mobilization of the Civil Engineer team to the Nigeria Abuja site — NGN 14,177,100
· Milestone 2 (25%): Upon submission and approval of detailed design drawings and EIA report — NGN 17,721,375
· Milestone 3 (35%): Upon completion of 50% of construction supervision period — NGN 24,809,925
· Milestone 4 (20%): Upon project completion, final inspection, and handover — NGN 14,177,100
4. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Beyond this period, prices may be revised to reflect market conditions in Nigeria Abuja.
· All payments shall be made in Nigerian Naira (NGN) via bank transfer to the account designated by Apex Civil Engineering & Infrastructure Ltd. within fourteen (14) days of invoice issuance.
· The Civil Engineer services described herein are governed by the Nigerian Engineering Council (COREN) Code of Professional Conduct and the Federal Capital Territory (FCT) Building and Development Control Regulations.
· Any variation in scope exceeding ten percent (10%) of the total Quotation Estimate value shall require a written amendment signed by both parties before additional work commences.
· The client shall provide reasonable access to the project site in Nigeria Abuja, including security clearance, logistics support, and any permits required for fieldwork.
· Intellectual property rights to all design documents, reports, and data produced under this engagement shall vest in the client upon full payment.
· Disputes arising from this Quotation Estimate or the resulting contract shall be resolved through arbitration in Abuja, FCT, Nigeria, in accordance with the Arbitration and Conciliation Act, Cap A18, Laws of the Federation of Nigeria 2004.
· This Quotation Estimate does not constitute a binding contract until a formal agreement is executed by both parties.
5. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, scope, and pricing outlined for the Civil Engineer services to be delivered in Nigeria Abuja.
For: Apex Civil Engineering & Infrastructure Ltd.
Name: Engr. Chukwuma Eze, MSc, MICE, COREN/ENG/12847
Title: Managing Director / Lead Civil Engineer
Date: _______________
For: Federal Capital Development Authority
Name: Engr. Adebayo Okafor
Title: Project Director
Date: _______________
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