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Quotation Details
Quotation Estimate No.: QE-2025-VAL-0047
Date Issued: 14 June 2025
Valid Until: 14 July 2025 (30 days)
Currency: EUR (€)
Project Location: Spain Valencia
Prepared For
Client Name: [Client Company Name]
Contact Person: [Name and Title]
Address: [Street, City, Postal Code]
Spain Valencia Region
Email: [client@email.com]
Project Reference
Project Title: IT Infrastructure & Systems Engineering
Scope Region: Spain Valencia
Estimated Duration: 12 weeks
Start Date: 01 September 2025
1. Executive Summary
This Quotation Estimate is issued by Valencia Tech Solutions S.L. to provide a comprehensive and itemised cost breakdown for the engagement of a senior Computer Engineer to deliver end-to-end IT infrastructure design, implementation, and maintenance services within the Spain Valencia metropolitan area. This document serves as a formal commercial proposal and is intended to give the client full transparency regarding all professional fees, material costs, and ancillary charges associated with the project. The Computer Engineer assigned to this engagement holds a recognised degree in Computer Engineering from a Spanish university and possesses over fifteen years of hands-on experience in enterprise systems, network architecture, and cloud migration projects specifically tailored to the industrial and commercial landscape of Spain Valencia.
2. Scope of Work
The Computer Engineer will be responsible for the following deliverables, all to be executed at the client's premises located in Spain Valencia and at the Valencia Tech Solutions S.L. engineering facility:
· Full audit and assessment of the existing IT infrastructure, including server rooms, network topology, and endpoint devices.
· Design and delivery of a scalable network architecture compliant with Spanish and EU data protection regulations (RGPD / GDPR).
· Migration of legacy on-premise systems to a hybrid cloud environment (AWS / Microsoft Azure) with full redundancy.
· Implementation of a cybersecurity framework including firewalls, intrusion detection systems, and endpoint protection.
· Development of a 24-month preventive maintenance and support plan for all installed systems.
· Training sessions for up to twenty (20) end-users at the client's Spain Valencia office.
· Delivery of complete technical documentation, as-built drawings, and a final acceptance report.
3. Itemised Cost Breakdown
	Ref
	Description of Service / Item
	Quantity
	Unit Rate (€)
	Total (€)
	Duration

	01
	Senior Computer Engineer — Project Management & Architecture Design (on-site, Spain Valencia)
	120 hrs
	65.00
	7,800.00
	Weeks 1–3

	02
	Computer Engineer — Network Implementation & Configuration
	160 hrs
	58.00
	9,280.00
	Weeks 3–6

	03
	Cloud Migration Services (hybrid architecture, data transfer, validation)
	1 lot
	12,500.00
	12,500.00
	Weeks 5–8

	04
	Cybersecurity Framework Deployment (hardware + software licences)
	1 lot
	8,400.00
	8,400.00
	Weeks 7–9

	05
	End-User Training Sessions (Computer Engineer-led, max 20 participants)
	4 sessions
	650.00
	2,600.00
	Weeks 10–11

	06
	Technical Documentation & Final Acceptance Report
	1 lot
	1,800.00
	1,800.00
	Week 12

	07
	24-Month Preventive Maintenance & Support Contract (Computer Engineer on-call)
	24 months
	1,200.00
	28,800.00
	Post-delivery

	08
	Travel & Accommodation (Computer Engineer, Spain Valencia area)
	1 lot
	1,500.00
	1,500.00
	Full project

	Subtotal (excl. VAT)
	72,680.00
	

	VAT — 21% (Spanish IVA)
	15,262.80
	

	TOTAL (incl. VAT)
	87,942.80
	


4. Payment Schedule
This Quotation Estimate proposes the following milestone-based payment structure. All payments are due within thirty (30) calendar days of invoice issuance and are payable by bank transfer to the account of Valencia Tech Solutions S.L. in Spain Valencia:
	Milestone
	Percentage
	Amount (€ incl. VAT)
	Trigger

	Advance Payment
	25%
	21,985.70
	Upon contract signature

	Design & Architecture Approval
	20%
	17,588.56
	Week 3 milestone sign-off

	Implementation & Migration Complete
	30%
	26,382.84
	Week 9 milestone sign-off

	Training & Final Acceptance
	15%
	13,191.42
	Week 12 final report

	Maintenance Contract (monthly)
	10%
	1,199.53 / month
	Monthly, 24 months


5. Terms and Conditions
1. This Quotation Estimate is valid for a period of thirty (30) calendar days from the date of issue. After this period, all prices and availability of the Computer Engineer must be reconfirmed in writing.
1. All work will be performed in accordance with the applicable Spanish legislation, including the Ley de Servicios de la Sociedad de la Información (LSSI), the Spanish Data Protection Act (LOPDGDD), and EU Regulation 2016/679 (GDPR).
1. The Computer Engineer assigned to this project will operate under a professional services contract governed by the Spanish Civil Code and the applicable provisions of the Spanish Commercial Code.
1. Any changes to the scope of work must be agreed upon in writing via a formal Variation Order. Additional costs will be calculated at the hourly rates specified in this Quotation Estimate.
1. Intellectual property rights in all deliverables, including design documents, configurations, and code, shall transfer to the client upon full payment of the applicable milestone.
1. The Computer Engineer shall maintain professional indemnity insurance with a minimum coverage of €1,000,000, valid throughout the project duration in Spain Valencia.
1. Disputes arising from this agreement shall be resolved by the competent courts of Spain Valencia, in accordance with Spanish law.
1. This Quotation Estimate does not constitute a binding contract until both parties have signed and returned the acceptance copy. A formal Service Agreement will be executed prior to the commencement of work.
1. All hardware and software licences procured under this estimate are subject to the standard warranty terms of the respective manufacturers and vendors.
1. Force majeure events, including but not limited to natural disasters, pandemics, or government-mandated shutdowns in the Spain Valencia region, shall suspend project timelines without penalty to either party.
6. Acceptance and Signatures
By signing below, both parties acknowledge that they have read, understood, and agree to the terms set forth in this Quotation Estimate for the engagement of a Computer Engineer to deliver the specified services in Spain Valencia.
For Valencia Tech Solutions S.L.
Name: ___________________________
Title: Director / Lead Computer Engineer
Date: ___________________________
For the Client
Name: ___________________________
Title: ___________________________
Date: ___________________________
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