Quotation Estimate - Curriculum Developer Services - Chile Santiago
QUOTATION ESTIMATE
EduCurriculum Pro Solutions SpA
Av. Apoquindo 4501, Piso 12, Las Condes, Santiago, Chile
RUT: 77.123.456-8 | Phone: +56 2 2345 6789 | Email: quotes@educurriculumpro.cl
Quotation Estimate No.: QE-2025-0847
Date of Issue: June 12, 2025
Valid Until: July 12, 2025
Client: Colegio San Martín de Porres
Address: Calle Los Aromos 1250, Providencia, Santiago, Chile
Contact: Director Académico, Sr. Roberto Fuentes
RUT: 80.234.567-1
Dear Sir/Madam,
Thank you for the opportunity to present this Quotation Estimate for professional Curriculum Developer services tailored to the educational needs of your institution in Chile Santiago. Our team at EduCurriculum Pro Solutions SpA specializes in designing, implementing, and evaluating comprehensive curricular frameworks that align with the Chilean Ministry of Education (MINEDUC) standards and the National Curriculum Base (Base Curricular Nacional). This Quotation Estimate outlines the full scope of work, deliverables, timelines, and associated costs for engaging our senior Curriculum Developer to support your academic transformation initiative in the Santiago metropolitan area.
Scope of Services – Curriculum Developer Engagement
The following Quotation Estimate covers a comprehensive engagement of a certified Curriculum Developer who will work on-site and remotely to deliver the following services for your institution located in Chile Santiago:
	#
	Service Description
	Duration
	Quantity
	Unit Price (CLP)

	1
	Curriculum Audit & Diagnostic Assessment – Full review of existing curricular materials, learning outcomes, and alignment with MINEDUC standards for all grade levels (Pre-K through 4th Medio).
	3 weeks
	1
	$1,850,000

	2
	Curriculum Design & Development – Creation of a structured, competency-based curriculum framework including learning objectives, content sequencing, assessment strategies, and pedagogical methodologies for all subject areas.
	8 weeks
	1
	$6,200,000

	3
	Teacher Training & Professional Development Workshops – On-site workshops in Santiago for 45 teaching staff on curriculum implementation, differentiated instruction, and formative assessment techniques.
	4 weeks
	6 sessions
	$480,000

	4
	Assessment Framework Development – Design of standardized evaluation instruments, rubrics, and continuous assessment protocols aligned with the Chilean educational evaluation system.
	4 weeks
	1
	$2,400,000

	5
	Technology Integration Plan – Development of a digital curriculum integration roadmap including LMS configuration, e-learning module design, and blended learning strategies for the Santiago campus.
	3 weeks
	1
	$1,950,000

	6
	Ongoing Consultancy & Curriculum Review – Monthly on-site visits to Chile Santiago for curriculum monitoring, iterative improvements, and stakeholder feedback sessions over a 6-month period.
	6 months
	6 visits
	$350,000

	7
	Documentation & Final Reporting – Comprehensive curriculum manual, implementation guide, and final project report in Spanish and English for institutional and MINEDUC compliance filing.
	2 weeks
	1
	$780,000


Cost Summary
	Description
	Amount (CLP)

	Subtotal – All Curriculum Developer Services
	$19,660,000

	IVA (19% – Chilean Value Added Tax)
	$3,735,400

	TOTAL ESTIMATED COST
	$23,395,400


Terms and Conditions
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After this period, pricing may be subject to revision based on market conditions in Chile Santiago.
1. Payment terms: 40% upon contract signing, 30% upon completion of Curriculum Design & Development (Item 2), and 30% upon final delivery and acceptance of all deliverables.
1. All payments shall be made in Chilean Pesos (CLP) via bank transfer to the account specified in the formal service contract.
1. The Curriculum Developer assigned to this project will be a certified professional with a minimum of 12 years of experience in Chilean K-12 curriculum design and at least 5 years of direct MINEDUC compliance work.
1. Travel and accommodation expenses for on-site visits within the Santiago Metropolitan Region are included in the quoted prices. Any travel outside this region will be billed separately at cost.
1. Intellectual property of all developed curriculum materials, frameworks, and documentation shall transfer to the client upon full payment of the total amount stated in this Quotation Estimate.
1. Confidentiality: All institutional data, student records, and proprietary information accessed during the engagement in Chile Santiago shall be treated as strictly confidential and protected under Chilean Law 19.628 on Data Protection.
1. Any changes to the scope of work must be agreed upon in writing by both parties and may result in a revised Quotation Estimate.
1. This Quotation Estimate does not constitute a binding contract. A formal service agreement will be executed upon mutual acceptance of these terms.
Acceptance
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms outlined above for the engagement of the Curriculum Developer services in Chile Santiago.
For EduCurriculum Pro Solutions SpA
Name: Dra. Carolina Méndez Rojas
Title: Director General
Date: _______________
For Colegio San Martín de Porres
Name: Sr. Roberto Fuentes
Title: Director Académico
Date: _______________
This Quotation Estimate document was prepared by EduCurriculum Pro Solutions SpA, a Chilean company registered under the Commercial Registry of Santiago. All services are subject to the Chilean Labor Code and applicable MINEDUC regulations. For inquiries regarding this Quotation Estimate or to request a revised estimate for Curriculum Developer services in Chile Santiago, please contact our office at +56 2 2345 6789 or quotes@educurriculumpro.cl.
