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1. Purpose of This Quotation Estimate
This Quotation Estimate document has been prepared specifically to outline the scope, deliverables, timeline, and associated costs for professional Curriculum Developer services tailored to educational institutions, corporate training departments, and government agencies operating within Colombia Bogotá. This estimate reflects current market rates for specialized curriculum design and development work in the Bogotá metropolitan area and adheres to the regulatory frameworks established by the Colombian Ministry of Education (Ministerio de Educación Nacional) and the District Secretariat of Education of Bogotá (Secretaría Distrital de Educación).
The Curriculum Developer engagement described herein encompasses the full lifecycle of curriculum creation, from initial needs assessment and stakeholder consultation through to final documentation, pilot implementation, and post-implementation review. All services are designed to meet the specific pedagogical, cultural, and linguistic requirements of the Colombia Bogotá educational context, including compliance with the national curriculum standards (Lineamientos Curriculares) and the Basic Learning Rights (Estándares Básicos de Competencias).
2. Scope of Services – Curriculum Developer Engagement
The Curriculum Developer will provide the following comprehensive services as part of this Quotation Estimate:
	Service Component
	Description
	Estimated Hours
	Unit Rate (COP)
	Subtotal (COP)

	Needs Assessment & Stakeholder Analysis
	On-site visits to Bogotá institutions, interviews with educators, parents, and students; alignment with MEN standards
	40
	180,000
	7,200,000

	Curriculum Framework Design
	Development of learning objectives, competency matrices, and pedagogical strategies for the target program
	80
	200,000
	16,000,000

	Learning Materials & Resource Development
	Creation of lesson plans, assessment instruments, digital resources, and teacher guides in Spanish with optional English modules
	120
	175,000
	21,000,000

	Teacher Training & Professional Development
	Workshops and coaching sessions for faculty in Bogotá on curriculum implementation and pedagogical methodology
	60
	220,000
	13,200,000

	Pilot Implementation & Evaluation
	Supervised pilot phase in selected Bogotá classrooms, data collection, and iterative refinement of the curriculum
	50
	210,000
	10,500,000

	Final Documentation & Handover
	Complete curriculum package, implementation manual, and administrative documentation for institutional records
	30
	190,000
	5,700,000

	TOTAL ESTIMATED COST
	73,600,000 COP

	VAT (IVA) 19% – Applicable per Colombian tax regulations
	13,984,000 COP

	GRAND TOTAL (Tax Inclusive)
	87,584,000 COP


3. Project Timeline
The Curriculum Developer engagement is projected to span a total of 16 weeks from the date of contract execution. The timeline has been structured to accommodate the academic calendar of institutions in Colombia Bogotá, ensuring that pilot implementation coincides with the appropriate semester. Key milestones include: Needs Assessment (Weeks 1–3), Framework Design (Weeks 4–7), Materials Development (Weeks 8–12), Teacher Training (Weeks 13–14), Pilot & Evaluation (Weeks 15–16), and Final Handover (Week 16).
4. Terms and Conditions of This Quotation Estimate
This Quotation Estimate is valid for thirty (30) calendar days from the date of issuance. All pricing is quoted in Colombian Pesos (COP) and is subject to adjustment should the scope of the Curriculum Developer services be modified by mutual written agreement. Payment terms are structured as follows: 30% upon contract signing, 40% upon completion of the curriculum framework and materials development phase, and 30% upon final delivery and acceptance of all deliverables. The Curriculum Developer shall maintain full intellectual property rights over proprietary methodologies, while all customized curriculum materials developed specifically for the client in Colombia Bogotá shall transfer to the client upon full payment.
Note: This Quotation Estimate does not include costs for printing, digital platform licensing, or third-party software subscriptions. Travel expenses within the Bogotá metropolitan area are included; travel to other Colombian departments will be billed separately at cost.
5. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms outlined for the Curriculum Developer services in Colombia Bogotá. A formal service agreement will be executed within five (5) business days of acceptance.
	Role
	Name
	Signature
	Date

	Client Representative
	_________________________
	_________________________
	___________

	Curriculum Developer / Service Provider
	_________________________
	_________________________
	___________
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