# Quotation Estimate - Curriculum Developer Services - DR Congo Kinshasa

# Quotation Estimate

EduBridge Consulting & Training Solutions

12 Avenue de la Paix, Gombe, Kinshasa, DR Congo

Tel: +243 810 000 000 | Email: info@edubridge-cd.com

RC: CD-KIN-2024-004521

Quotation No.: QTE-2025-CD-0087

Date Issued: 15 June 2025

Valid Until: 15 July 2025

Prepared For: Ministry of National Education, DR Congo

Project Location: Kinshasa, DR Congo

Reference: MNE-EDU-2025-034

## 1. Introduction and Purpose

This Quotation Estimate is formally submitted by EduBridge Consulting & Training Solutions to the Ministry of National Education of the Democratic Republic of Congo for the professional engagement of a qualified Curriculum Developer to design, review, and implement updated educational curricula across primary and secondary school levels in DR Congo Kinshasa. This document outlines the full scope of services, associated costs, delivery timelines, and contractual terms governing the proposed engagement.

The Curriculum Developer engagement is specifically tailored to address the evolving educational needs of the Kinshasa metropolitan region, ensuring that learning materials, pedagogical frameworks, and assessment strategies align with both national educational standards and international best practices. The proposed work will be conducted entirely within DR Congo Kinshasa, with all deliverables localized in French and Lingala to serve the diverse student population of the capital region.

## 2. Scope of Services – Curriculum Developer

The Curriculum Developer will be responsible for the following deliverables and activities:

- Conduct a comprehensive needs assessment across 45 public primary and secondary schools in the Kinshasa urban and peri-urban zones.

- Design and develop updated curriculum frameworks for Mathematics, Natural Sciences, French Language, and Social Studies for grades 1 through 12.

- Author and localize all accompanying teacher guides, student workbooks, and standardized assessment instruments in French and Lingala.

- Organize and facilitate a minimum of six (6) professional development workshops for 300+ teachers across DR Congo Kinshasa.

- Establish a continuous curriculum review and feedback mechanism in coordination with the Directorate of Education for the Kinshasa region.

- Provide ongoing technical advisory support for a period of twelve (12) months following initial curriculum deployment.

## 3. Itemized Cost Breakdown

| Item No. | Description of Service | Duration | Unit Cost (USD) | Quantity | Total (USD) |
| --- | --- | --- | --- | --- | --- |
| 01 | Curriculum Developer – Senior Consultant (Needs Assessment & Framework Design) | 3 months | $4,500 | 3 | $13,500 |
| 02 | Curriculum Developer – Senior Consultant (Material Authoring & Localization) | 4 months | $4,500 | 4 | $18,000 |
| 03 | Curriculum Developer – Senior Consultant (Teacher Training & Workshop Facilitation) | 2 months | $4,500 | 2 | $9,000 |
| 04 | Curriculum Developer – Senior Consultant (Ongoing Technical Advisory Support) | 12 months | $2,800 | 12 | $33,600 |
| 05 | Field Research & School Visits within Kinshasa (transport, logistics, per diem) | 9 months | $1,200 | 9 | $10,800 |
| 06 | Printing, Binding & Distribution of Curriculum Materials (5,000 copies) | One-time | $12,500 | 1 | $12,500 |
| 07 | Project Management, Reporting & Quality Assurance | 20 months | $1,800 | 20 | $36,000 |
| 08 | Applicable Taxes, Permits & Regulatory Compliance (DR Congo Kinshasa) | One-time | $4,200 | 1 | $4,200 |
| GRAND TOTAL (USD) |  |  |  |  | $137,600 |

Note: All costs are quoted in United States Dollars (USD). Payment will be processed via bank transfer to the account of EduBridge Consulting & Training Solutions, Banques Africaines du Congo, Kinshasa branch. A 10% mobilization advance is required upon contract signature. The Quotation Estimate does not include costs for additional curriculum subjects beyond those specified in Section 2.

## 4. Payment Schedule

| Milestone | Percentage | Amount (USD) | Trigger |
| --- | --- | --- | --- |
| Contract Signature | 10% | $13,760 | Upon execution of agreement |
| Needs Assessment Complete | 15% | $20,640 | Submission of assessment report |
| Curriculum Framework Approved | 20% | $27,520 | Ministry sign-off on framework |
| Materials Printed & Distributed | 25% | $34,400 | Delivery to all 45 schools |
| Teacher Training Completed | 15% | $20,640 | Workshop completion certificates |
| Final Advisory Period Concluded | 15% | $20,640 | Final project report accepted |

## 5. Terms and Conditions

5.1 This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Beyond this period, pricing and availability of the Curriculum Developer may be subject to revision.

5.2 All intellectual property rights to curriculum materials developed under this engagement shall vest with the Ministry of National Education, DR Congo, upon full payment.

5.3 The Curriculum Developer shall comply with all applicable laws and regulations of the Democratic Republic of Congo, including but not limited to labor, tax, and educational licensing requirements specific to DR Congo Kinshasa.

5.4 Any changes to the scope of work must be documented in a formal change order signed by both parties before implementation.

5.5 Disputes arising from this engagement shall be resolved through amicable negotiation, failing which they shall be submitted to the competent courts of Kinshasa, DR Congo.

5.6 The Curriculum Developer shall maintain professional liability insurance throughout the duration of the project.

## 6. Acceptance and Authorization

By signing below, the client acknowledges receipt of this Quotation Estimate and authorizes EduBridge Consulting & Training Solutions to proceed with the engagement of the Curriculum Developer for the project located in DR Congo Kinshasa under the terms and conditions outlined herein.

For EduBridge Consulting & Training Solutions

Name: Jean-Pierre Mbuyi
Title: Managing Director
Date: _______________

For the Ministry of National Education, DR Congo

Name: _________________________
Title: _________________________
Date: _______________

This Quotation Estimate was prepared exclusively for the Ministry of National Education, DR Congo, Kinshasa. It is non-transferable and non-negotiable in its current form. For inquiries, contact info@edubridge-cd.com or visit our office at 12 Avenue de la Paix, Gombe, Kinshasa, DR Congo.

© 2025 EduBridge Consulting & Training Solutions. All rights reserved.