Quotation Estimate - Curriculum Developer Services - Egypt Cairo
Quotation Estimate
Professional Curriculum Developer Services
Serving the Educational Sector in Egypt Cairo
Ref: QE-EGY-CAI-2025-0472
Prepared By:
Nile Delta Educational Consulting Ltd.
142 El Tahrir Street, Downtown District
Cairo, Egypt 11511
Tel: +20 2 2574 8890
Email: quotes@niledelta-edu.com.eg
Quotation Details:
Date Issued: 15 June 2025
Valid Until: 15 July 2025
Currency: Egyptian Pound (EGP)
Prepared For: [Client Name / Institution]
Location: Cairo, Egypt
1. Scope of Work – Curriculum Developer Engagement in Egypt Cairo
This Quotation Estimate is issued by Nile Delta Educational Consulting Ltd. to provide comprehensive Curriculum Developer services tailored to the educational landscape of Egypt Cairo. Our team of certified Curriculum Developers will design, develop, review, and implement structured learning curricula aligned with the Egyptian Ministry of Education and Technical Education (MoETE) national standards, the Cairo Governorate's local educational directives, and international best practices in instructional design.
The Curriculum Developer engagement will cover the full lifecycle of curriculum creation, including needs assessment, learning objective formulation, content architecture, assessment strategy design, teacher training materials, and ongoing iterative refinement. All deliverables will be produced in both Arabic and English to accommodate the bilingual educational environment prevalent in Cairo's private and international schools, universities, and vocational training centers.
2. Itemized Services and Cost Breakdown
	#
	Service Description
	Duration
	Quantity
	Unit Rate (EGP)
	Total (EGP)

	1
	Initial Needs Assessment & Stakeholder Consultation in Cairo educational institutions
	2 weeks
	1
	45,000
	45,000

	2
	Curriculum Framework Design (aligned with MoETE standards and Cairo local requirements)
	4 weeks
	1
	120,000
	120,000

	3
	Development of Learning Modules, Lesson Plans & Pedagogical Content (Arabic & English)
	8 weeks
	12 modules
	18,500
	222,000

	4
	Assessment & Evaluation Strategy Design (formative, summative, and competency-based)
	3 weeks
	1
	65,000
	65,000

	5
	Teacher Training Workshops & Professional Development Sessions (held in Cairo)
	2 weeks
	4 sessions
	22,000
	88,000

	6
	Digital Curriculum Platform Integration & E-Learning Content Development
	6 weeks
	1
	95,000
	95,000

	7
	Quality Assurance Review, Peer Validation & MoETE Compliance Audit
	2 weeks
	1
	38,000
	38,000

	8
	Ongoing Curriculum Maintenance & Annual Revision Support (12 months)
	12 months
	1
	150,000
	150,000

	Subtotal
	823,000

	VAT (14% – Egyptian Tax Authority)
	115,220

	Grand Total (EGP)
	938,220


3. Project Timeline
The total estimated duration for the Curriculum Developer project in Egypt Cairo is approximately 28 weeks (7 months) from the date of contract signing, followed by a 12-month maintenance and support period. The timeline accounts for the Egyptian academic calendar, including the summer break period (July–August) and the winter holiday (January). All on-site activities in Cairo will be scheduled to minimize disruption to ongoing academic operations.
4. Terms and Conditions
· This Quotation Estimate is valid for 30 calendar days from the date of issue. After the expiry date, pricing may be subject to revision based on market conditions in Egypt Cairo.
· Payment terms: 30% advance upon contract signing, 40% upon completion of curriculum development phase, and 30% upon final delivery and acceptance.
· All payments shall be made in Egyptian Pounds (EGP) via bank transfer to the account of Nile Delta Educational Consulting Ltd., registered with the Egyptian Companies Registration Authority.
· The Curriculum Developer team will operate in compliance with all applicable Egyptian labor laws, data protection regulations, and the Egyptian Ministry of Education's guidelines for educational content development.
· Intellectual property of all developed curriculum materials shall transfer to the client upon full payment. The Curriculum Developer retains the right to reference the project in professional portfolios with client written consent.
· Any scope changes or additional modules beyond the 12 specified in this Quotation Estimate will be subject to a separate written amendment and additional cost assessment.
· Force majeure events, including but not limited to government-mandated closures in Cairo, shall extend the project timeline proportionally without penalty to either party.
· This Quotation Estimate does not constitute a binding contract until both parties have executed the formal Service Agreement.
5. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate for Curriculum Developer services in Egypt Cairo and agrees to the terms, conditions, and pricing outlined herein. This document serves as the formal basis for the subsequent Service Agreement between the parties.
For Nile Delta Educational Consulting Ltd.
Authorized Signatory
Name: _________________________
Title: Managing Director
Date: _________________________
For the Client / Institution
Authorized Representative
Name: _________________________
Title: _________________________
Date: _________________________
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