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1. Purpose of This Quotation Estimate
This Quotation Estimate is formally issued to provide a comprehensive and transparent breakdown of costs associated with the engagement of a qualified Curriculum Developer to design, review, and implement educational curricula within the Ethiopia Addis Ababa educational framework. This document serves as a binding financial proposal for the services described herein and is intended to support procurement and budgeting processes in accordance with the Federal Democratic Republic of Ethiopia's public sector procurement directives.
2. Scope of Services – Curriculum Developer Engagement
The Curriculum Developer engaged under this quotation will deliver the following professional services tailored to the educational needs of institutions operating in Ethiopia Addis Ababa:
· Needs Assessment and Stakeholder Consultation: Conduct comprehensive baseline surveys across primary, secondary, and tertiary institutions in the Addis Ababa Sub-City Education Offices to identify gaps, learning outcomes, and community expectations for curriculum content.
· Curriculum Design and Development: Develop a full-cycle curriculum framework aligned with the Ethiopian National Education Policy (2019) and the Competency-Based Curriculum (CBC) guidelines, including learning objectives, content standards, assessment strategies, and instructional sequencing for Grades 1 through 12.
· Localization and Cultural Adaptation: Adapt all curriculum materials to reflect the linguistic diversity of Addis Ababa, incorporating Amharic, Afaan Oromo, Tigrinya, and English as appropriate, while embedding Ethiopian cultural values, history, and civic education content.
· Teacher Training and Capacity Building: Design and deliver a 10-day intensive professional development workshop for 200 teachers across 40 schools in Addis Ababa, focusing on the effective implementation of the newly developed curriculum.
· Pilot Implementation and Evaluation: Supervise a 12-week pilot phase in 10 selected schools within Addis Ababa, collect formative and summative assessment data, and produce a detailed evaluation report with recommendations for full-scale rollout.
· Documentation and Reporting: Deliver all curriculum documents in both printed and digital formats, including teacher guides, student workbooks, assessment banks, and a comprehensive project report in Amharic and English.
· Ongoing Technical Support: Provide 6 months of post-implementation advisory support, including quarterly review meetings with the Addis Ababa Education Bureau and on-site consultations as needed.
3. Itemized Cost Breakdown
	Item No.
	Description of Service
	Duration / Quantity
	Unit Cost (ETB)
	Total Cost (ETB)

	01
	Needs Assessment & Stakeholder Consultation (fieldwork across 5 sub-cities)
	3 weeks
	185,000
	185,000

	02
	Curriculum Design & Development (Grades 1–12, all core subjects)
	12 weeks
	1,250,000
	1,250,000

	03
	Localization, Translation & Cultural Adaptation of Materials
	4 weeks
	420,000
	420,000

	04
	Teacher Training Workshop (200 teachers, 10 days, 40 schools)
	10 days
	680,000
	680,000

	05
	Pilot Implementation Supervision & Evaluation (10 schools, 12 weeks)
	12 weeks
	540,000
	540,000

	06
	Documentation, Printing & Digital Distribution of All Materials
	1 batch
	310,000
	310,000

	07
	Post-Implementation Technical Support & Advisory (6 months)
	6 months
	460,000
	460,000

	08
	Travel, Logistics & Local Transportation within Addis Ababa
	Full project
	125,000
	125,000

	09
	Project Management, Coordination & Administrative Overhead
	Full project
	280,000
	280,000

	SUBTOTAL (ETB)
	4,250,000

	VAT (15% as per Ethiopian Tax Law)
	637,500

	GRAND TOTAL (ETB)
	4,887,500

	GRAND TOTAL (USD, approx. at 1 USD = 57 ETB)
	≈ 85,746


Note: All costs are quoted in Ethiopian Birr (ETB) and are subject to the prevailing exchange rate at the time of contract execution. The Quotation Estimate assumes standard working conditions in Ethiopia Addis Ababa and does not include costs for international travel, accommodation for external consultants, or any force majeure events.
4. Payment Schedule
Payment for the Curriculum Developer services outlined in this Quotation Estimate shall be made in four installments, disbursed upon verified completion of each milestone:
· Installment 1 (25% – ETB 1,221,875): Due upon signing of the service agreement and submission of the approved project work plan.
· Installment 2 (35% – ETB 1,710,625): Due upon delivery of the complete curriculum design documents and completion of the teacher training workshop.
· Installment 3 (25% – ETB 1,221,875): Due upon successful completion of the 12-week pilot phase and submission of the evaluation report.
· Installment 4 (15% – ETB 733,125): Due upon conclusion of the 6-month post-implementation support period and final project close-out report.
5. Terms and Conditions
5.1 This Quotation Estimate is valid for a period of ninety (90) calendar days from the date of issue. Beyond this period, all prices are subject to revision based on prevailing economic conditions in Ethiopia Addis Ababa.
5.2 The Curriculum Developer shall comply with all applicable laws and regulations of the Federal Democratic Republic of Ethiopia, including the Ethiopian Education and Research Proclamation (No. 816/2013) and the Addis Ababa City Administration Education Bureau directives.
5.3 All intellectual property rights in the curriculum materials developed under this engagement shall vest with the client (the Addis Ababa Education Bureau) upon full payment. The Curriculum Developer retains the right to reference the project in professional portfolios and academic publications with prior written consent.
5.4 Any changes to the scope of work must be documented in a formal change order signed by both parties. No additional costs shall be incurred without prior written approval.
5.5 Disputes arising from this Quotation Estimate or the resulting contract shall be resolved through amicable negotiation. If unresolved within thirty (30) days, the matter shall be referred to the competent courts of Addis Ababa, Ethiopia.
5.6 The Curriculum Developer shall maintain professional liability insurance throughout the duration of the engagement and shall provide proof of coverage upon request.
6. Acceptance and Authorization
By signing below, both parties acknowledge that this Quotation Estimate for Curriculum Developer services in Ethiopia Addis Ababa has been reviewed, understood, and accepted in full. This document, once countersigned, constitutes a binding financial proposal and may be converted into a formal service contract upon mutual agreement.
For the Provider
Dr. Selamawit Tadesse
Lead Curriculum Developer
EthioCurriculum Development & Training Institute
Addis Ababa, Ethiopia
Signature & Date: _________________________
For the Client
Authorized Representative
Addis Ababa City Education Bureau
Ministry of Education, Ethiopia
Signature & Date: _________________________
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