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1. Introduction and Scope of Work
This Quotation Estimate is issued by EduBridge Learning Solutions Ltd. in response to the request for professional Curriculum Developer services to be delivered within the Ghana Accra metropolitan area. The purpose of this document is to provide a comprehensive, itemized breakdown of all costs associated with the design, development, review, and implementation support of a revised secondary school curriculum framework aligned with the Ghana Education Service (GES) standards and the National Council for Curriculum and Assessment (NaCCA) guidelines.
Our team of certified Curriculum Developer professionals, based in Ghana Accra, will undertake a full-cycle curriculum development engagement spanning approximately sixteen (16) weeks. The scope encompasses needs assessment, stakeholder consultation, learning outcome mapping, content structuring, assessment design, teacher training materials, and a final quality assurance review. All deliverables will be produced in English, with optional Twi and Ewe language summaries for community engagement sessions conducted in the Accra and Greater Accra Region.
2. Itemized Cost Breakdown
	No.
	Description of Service
	Duration
	Unit Rate (GHS)
	Total (GHS)

	1
	Curriculum Developer – Lead Consultant: Senior-level curriculum architect responsible for overall framework design, pedagogical alignment, and NaCCA compliance review. Based in Ghana Accra with 15+ years of experience in Ghanaian education systems.
	16 weeks
	4,500.00 / week
	72,000.00

	2
	Curriculum Developer – Subject Specialists (x4): Four subject-matter experts (Mathematics, Science, English Language, Social Studies) to develop unit-level content, learning objectives, and differentiated activity plans.
	12 weeks
	2,800.00 / week each
	134,400.00

	3
	Stakeholder Consultation & Needs Assessment: Facilitation of focus group discussions with teachers, school heads, parents, and community leaders across 6 districts in Ghana Accra. Includes venue, transport, and documentation.
	3 weeks
	18,500.00 / week
	55,500.00

	4
	Assessment & Evaluation Design: Development of formative and summative assessment instruments, rubrics, and standardized test blueprints aligned with the Ghanaian national examination framework (BECE/WASSCE).
	4 weeks
	12,000.00 / week
	48,000.00

	5
	Teacher Training & Capacity Building Workshops: Design and delivery of 8 in-service training workshops for 200+ teachers in Ghana Accra schools. Includes training manuals, digital resources, and post-training follow-up.
	4 weeks
	22,000.00 / week
	88,000.00

	6
	Quality Assurance & Final Review: Independent peer review of all curriculum documents, compliance audit against GES and NaCCA standards, and production of the final bound curriculum package (digital and print).
	2 weeks
	15,000.00 / week
	30,000.00

	7
	Project Management & Coordination: Dedicated project manager to oversee timelines, reporting, communication with the client, and administrative logistics throughout the engagement in Ghana Accra.
	16 weeks
	3,200.00 / week
	51,200.00

	8
	Travel, Accommodation & Local Logistics: All internal travel within the Greater Accra Region, accommodation for visiting specialists, printing, stationery, and miscellaneous operational costs.
	16 weeks
	4,800.00 / week
	76,800.00

	Subtotal (GHS)
	555,900.00

	VAT (15%)
	83,385.00

	GRAND TOTAL (GHS)
	639,285.00


3. Payment Terms
Payment for this Quotation Estimate shall be made in four (4) milestones as follows:
· Milestone 1 (30%): GHS 191,785.50 – Due upon signing of the service agreement and commencement of the project in Ghana Accra.
· Milestone 2 (30%): GHS 191,785.50 – Due upon completion of the curriculum framework draft and stakeholder consultation phase (Week 8).
· Milestone 3 (25%): GHS 159,821.25 – Due upon delivery of all subject-specific content, assessment instruments, and training materials (Week 14).
· Milestone 4 (15%): GHS 95,892.75 – Due upon final quality assurance sign-off and handover of the complete curriculum package (Week 16).
4. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Any acceptance beyond this period is subject to re-evaluation of rates.
· All Curriculum Developer personnel assigned to this project are fully qualified, insured, and vetted in accordance with Ghanaian labour and professional standards.
· The client agrees to provide timely access to relevant schools, data, and institutional records within Ghana Accra to facilitate the work of the Curriculum Developer team.
· Intellectual property of all developed curriculum materials shall vest in the client upon full payment. EduBridge Learning Solutions Ltd. retains the right to reference the project in professional portfolios.
· Any scope changes or additional services beyond the original Quotation Estimate will be subject to a written change order and supplementary quotation.
· Disputes arising from this engagement shall be resolved through mediation in Ghana Accra, in accordance with the laws of the Republic of Ghana.
· Confidentiality: All data, student records, and internal documents shared during the project shall be treated as strictly confidential and shall not be disclosed to third parties without written consent.
5. Acceptance
By signing below, the client acknowledges and accepts this Quotation Estimate for Curriculum Developer services to be rendered in Ghana Accra, and agrees to the terms, conditions, and payment schedule outlined herein.
For and on behalf of EduBridge Learning Solutions Ltd.
Name: ______________________________
Title: Managing Director
Signature: ______________________________
Date: ______________________________
For and on behalf of the Client
Name: ______________________________
Title: ______________________________
Signature: ______________________________
Date: ______________________________
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