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Quotation Estimate
Quotation Details
Quotation No: QTE-YGN-2025-00847
Date Issued: 15 June 2025
Valid Until: 15 July 2025
Prepared For: Myanmar Yangon Regional Education Board
Project Location: Yangon, Myanmar
Client Information
Client Name: Myanmar Yangon Regional Education Board
Address: No. 12, Anawrahta Road, Yangon, Myanmar
Contact Person: U Aung Kyaw Min
Position: Director of Curriculum Affairs
Email: aung.kyaw@myanmaredboard.gov.mm
This Quotation Estimate is formally submitted by Yangon Educational Solutions Co., Ltd. to the Myanmar Yangon Regional Education Board for the engagement of a professional Curriculum Developer to design, develop, and implement comprehensive educational curricula tailored to the academic needs of institutions operating within the Myanmar Yangon metropolitan area. This document outlines the full scope of services, associated costs, timelines, and terms governing the proposed engagement.
Scope of Work – Curriculum Developer Services
The Curriculum Developer engaged under this Quotation Estimate will be responsible for the following deliverables and activities, all conducted within the Myanmar Yangon region:
	No.
	Service Description
	Duration
	Unit
	Amount (MMK)

	1
	Needs Assessment & Stakeholder Consultation – The Curriculum Developer will conduct a comprehensive needs analysis across 12 partner schools in Myanmar Yangon, including interviews with teachers, administrators, and students to identify gaps in existing curricula.
	3 weeks
	Lump Sum
	4,500,000

	2
	Curriculum Framework Design – Development of a structured curriculum framework aligned with Myanmar national education standards, incorporating competency-based learning outcomes for primary and secondary levels in the Yangon region.
	6 weeks
	Lump Sum
	12,000,000

	3
	Learning Material Development – The Curriculum Developer will author and produce 8 subject-specific teaching modules (Mathematics, Science, English, Myanmar Language, Social Studies, ICT, Arts, and Physical Education) with accompanying assessment rubrics.
	10 weeks
	Per Module
	15,200,000

	4
	Teacher Training & Professional Development – Delivery of 4 intensive training workshops (2 days each) for 200 teachers across Myanmar Yangon schools to ensure effective implementation of the newly developed curriculum.
	4 weeks
	Per Workshop
	8,000,000

	5
	Pilot Implementation & Feedback Collection – The Curriculum Developer will oversee a 6-week pilot program in 3 selected schools within Myanmar Yangon, collecting structured feedback from all stakeholders for iterative refinement.
	6 weeks
	Lump Sum
	6,500,000

	6
	Final Curriculum Documentation & Handover – Compilation of the complete curriculum package, including teacher guides, student workbooks, assessment tools, and a digital repository, delivered to the Myanmar Yangon Regional Education Board.
	3 weeks
	Lump Sum
	5,000,000

	7
	Ongoing Advisory & Revision Support – 6 months of post-implementation advisory support where the Curriculum Developer remains available for curriculum adjustments, Q&A sessions, and minor revisions as required by the Myanmar Yangon education authorities.
	6 months
	Monthly
	3,600,000

	TOTAL ESTIMATED COST (MMK)
	54,800,000


Grand Total: 54,800,000 MMK (Fifty-Four Million Eight Hundred Thousand Myanmar Kyat)
Equivalent to approximately USD 34,250 at the prevailing exchange rate as of the date of this Quotation Estimate.
Payment Schedule
Payment for the Curriculum Developer services outlined in this Quotation Estimate shall be made according to the following milestone-based schedule:
	Milestone
	Percentage
	Amount (MMK)
	Due Date

	Contract Signing & Mobilization
	20%
	10,960,000
	Upon contract execution

	Completion of Curriculum Framework Design
	25%
	13,700,000
	Week 12

	Delivery of All Learning Materials
	25%
	13,700,000
	Week 22

	Completion of Pilot & Final Handover
	20%
	10,960,000
	Week 31

	End of Advisory Period
	10%
	5,480,000
	Month 10


Terms and Conditions
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Beyond this period, pricing for the Curriculum Developer services may be subject to revision based on market conditions in Myanmar Yangon.
1. All services described herein shall be performed by a qualified and experienced Curriculum Developer with a minimum of ten (10) years of experience in educational design, specifically familiar with the Myanmar national education framework and the unique linguistic and cultural context of the Myanmar Yangon region.
1. The Curriculum Developer shall maintain full confidentiality regarding all proprietary information, student data, and institutional records encountered during the course of this engagement in Myanmar Yangon.
1. Any changes to the scope of work beyond what is specified in this Quotation Estimate must be agreed upon in writing by both parties prior to implementation. Additional costs will be itemized in a supplementary Quotation Estimate.
1. All deliverables, including curriculum documents, teaching materials, and digital assets, shall become the exclusive property of the Myanmar Yangon Regional Education Board upon full payment.
1. The Curriculum Developer is responsible for all travel, accommodation, and local transportation costs within Myanmar Yangon as part of the quoted amounts. No additional travel expenses shall be billed separately.
1. Disputes arising from this Quotation Estimate and the subsequent contract shall be resolved through amicable negotiation. If unresolved, matters shall be referred to the Myanmar Yangon District Court for adjudication.
1. This Quotation Estimate does not constitute a binding contract until formally accepted and countersigned by both parties. A separate Service Agreement will be executed upon acceptance.
1. The Curriculum Developer shall comply with all applicable laws and regulations of the Republic of the Union of Myanmar, including those pertaining to education, employment, and intellectual property within the Yangon Region.
1. Force majeure events, including but not limited to natural disasters, government-mandated closures, or public health emergencies affecting Myanmar Yangon, shall extend project timelines proportionally without penalty to either party.
Acceptance and Authorization
By signing below, both parties acknowledge and agree to the terms, conditions, and pricing outlined in this Quotation Estimate for the engagement of a Curriculum Developer to serve the educational institutions of Myanmar Yangon.
For: Yangon Educational Solutions Co., Ltd.
Name: ___________________________
Designation: Managing Director
Signature: ___________________________
Date: ___________________________
For: Myanmar Yangon Regional Education Board
Name: ___________________________
Designation: Director of Curriculum Affairs
Signature: ___________________________
Date: ___________________________
This Quotation Estimate was prepared exclusively for the Myanmar Yangon Regional Education Board and is not transferable to any third party.
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