# Quotation Estimate - Curriculum Developer Services - Russia Saint Petersburg

# Quotation Estimate

Professional Curriculum Developer Services — Russia Saint Petersburg

| Quotation No.: | QTE-RSP-2025-0472 | Date of Issue: | 15 June 2025 |
| --- | --- | --- | --- |
| Valid Until: | 15 July 2025 | Currency: | Russian Ruble (RUB) / US Dollar (USD) |
| Prepared By: | Dr. Elena V. Sokolova, Lead Curriculum Developer | Company: | PetroEdu Consulting LLC, Saint Petersburg, Russia |
| Client: | Northwestern Federal Educational Consortium | Client Address: | 12 Nevsky Prospekt, Saint Petersburg, 191011, Russia |
| Contact Person: | Mr. Dmitry A. Volkov, Director of Academic Affairs | Email: | d.volkov@nwfec.ru |

## 1. Purpose of This Quotation Estimate

This Quotation Estimate is formally issued by PetroEdu Consulting LLC to the Northwestern Federal Educational Consortium, located in Russia Saint Petersburg, to provide a comprehensive and transparent breakdown of costs associated with the engagement of a senior Curriculum Developer for the redesign and modernization of the consortium's academic programmes. This document serves as a binding financial proposal and outlines the full scope of deliverables, timelines, and associated fees for the proposed engagement. All pricing in this Quotation Estimate reflects current market rates applicable to the Russia Saint Petersburg educational sector as of the date of issue.

## 2. Scope of Work — Curriculum Developer Services

The Curriculum Developer engaged under this Quotation Estimate will be responsible for the following deliverables, tailored specifically to the academic requirements and regulatory standards of institutions operating in Russia Saint Petersburg:

| # | Deliverable / Service Item | Duration | Unit Cost (RUB) | Total Cost (RUB) |
| --- | --- | --- | --- | --- |
| 1 | Comprehensive needs assessment and audit of existing curriculum frameworks across all three consortium campuses in Saint Petersburg | 3 weeks | 185,000 | 555,000 |
| 2 | Design and development of a new integrated curriculum architecture aligned with the Federal State Educational Standards (FSES) of the Russian Federation | 8 weeks | 220,000 | 1,760,000 |
| 3 | Authoring of detailed course syllabi, learning outcomes, and assessment rubrics for 24 undergraduate modules | 10 weeks | 195,000 | 1,950,000 |
| 4 | Development of digital learning resources, interactive modules, and e-learning content compatible with the consortium's LMS platform | 6 weeks | 210,000 | 1,260,000 |
| 5 | Faculty training workshops (4 sessions) to onboard teaching staff on the new curriculum framework and pedagogical methodologies | 4 weeks | 160,000 | 640,000 |
| 6 | Quality assurance review, peer validation, and regulatory compliance check with the Ministry of Education and Science of the Russian Federation | 3 weeks | 175,000 | 525,000 |
| 7 | Post-implementation support, curriculum iteration, and annual review cycle (12-month period) | 12 months | 95,000 | 1,140,000 |
| Subtotal: |  |  |  | 7,830,000 |
| VAT (20%): |  |  |  | 1,566,000 |
| Grand Total: |  |  |  | 9,396,000 RUB |

## 3. Curriculum Developer Qualifications and Methodology

The Curriculum Developer assigned to this project holds a Doctorate in Educational Sciences from Saint Petersburg State University and possesses over fifteen years of experience in academic programme design within the Russia Saint Petersburg higher education landscape. The methodology employed will follow a constructivist, competency-based approach, ensuring that all developed curricula meet both the national FSES requirements and the consortium's strategic vision for international accreditation. The Curriculum Developer will conduct all on-site work at the consortium's primary office on Nevsky Prospekt, with remote collaboration available for distributed teams across the Saint Petersburg metropolitan area.

## 4. Payment Terms and Schedule

This Quotation Estimate stipulates the following payment structure, payable in Russian Rubles via bank transfer to the account of PetroEdu Consulting LLC, registered in Saint Petersburg, Russia:

- 30% advance payment (2,818,800 RUB) upon signed acceptance of this Quotation Estimate and execution of the service agreement.

- 40% milestone payment (3,758,400 RUB) upon delivery and client approval of the completed curriculum architecture and all 24 course syllabi.

- 30% final payment (2,818,800 RUB) upon completion of faculty training, regulatory compliance certification, and handover of all digital learning resources.

All payments are due within fifteen (15) business days of invoice issuance. Late payments shall incur a penalty of 0.1% per calendar day, in accordance with the Civil Code of the Russian Federation.

## 5. Terms and Conditions

- This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Beyond this period, pricing may be subject to revision based on market conditions in the Russia Saint Petersburg educational services sector.

- All intellectual property rights to the curriculum materials, syllabi, and digital content developed by the Curriculum Developer shall transfer to the client upon full and final payment.

- The Curriculum Developer shall maintain strict confidentiality regarding the client's proprietary academic data, student records, and internal strategic documents throughout the engagement.

- Any changes to the scope of work beyond the items listed in Section 2 shall require a written change order and a revised Quotation Estimate approved by both parties.

- This engagement is governed by the laws of the Russian Federation. Any disputes arising from this Quotation Estimate or the resulting service agreement shall be resolved through arbitration in Saint Petersburg, Russia.

- The Curriculum Developer reserves the right to subcontract specialized sub-components (e.g., graphic design for digital modules) provided prior written consent is obtained from the client.

- Force majeure events, including but not limited to government-mandated closures of educational institutions in Saint Petersburg, shall suspend project timelines without penalty to either party.

## 6. Acceptance and Authorization

By signing below, both parties acknowledge that this Quotation Estimate accurately represents the agreed-upon scope, cost, and terms for the Curriculum Developer engagement in Russia Saint Petersburg. This document, once countersigned, constitutes a binding proposal and shall form the financial annex to the master service agreement.

For PetroEdu Consulting LLC (Provider)

Name: Dr. Elena V. Sokolova

Title: Lead Curriculum Developer / Managing Director

Signature & Date

For Northwestern Federal Educational Consortium (Client)

Name: Mr. Dmitry A. Volkov

Title: Director of Academic Affairs

Signature & Date

This Quotation Estimate was prepared exclusively for the Northwestern Federal Educational Consortium, Saint Petersburg, Russia. It is not transferable and does not constitute a final contract until countersigned by both parties. Document Reference: QTE-RSP-2025-0472 | PetroEdu Consulting LLC | INN 7805432198 | OGRN 1157847001234