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1. Purpose of This Quotation Estimate
This Quotation Estimate is formally issued by PetroEdu Consulting LLC to the Northwestern Federal Educational Consortium, located in Russia Saint Petersburg, to provide a comprehensive and transparent breakdown of costs associated with the engagement of a senior Curriculum Developer for the redesign and modernization of the consortium's academic programmes. This document serves as a binding financial proposal and outlines the full scope of deliverables, timelines, and associated fees for the proposed engagement. All pricing in this Quotation Estimate reflects current market rates applicable to the Russia Saint Petersburg educational sector as of the date of issue.
2. Scope of Work — Curriculum Developer Services
The Curriculum Developer engaged under this Quotation Estimate will be responsible for the following deliverables, tailored specifically to the academic requirements and regulatory standards of institutions operating in Russia Saint Petersburg:
	#
	Deliverable / Service Item
	Duration
	Unit Cost (RUB)
	Total Cost (RUB)

	1
	Comprehensive needs assessment and audit of existing curriculum frameworks across all three consortium campuses in Saint Petersburg
	3 weeks
	185,000
	555,000

	2
	Design and development of a new integrated curriculum architecture aligned with the Federal State Educational Standards (FSES) of the Russian Federation
	8 weeks
	220,000
	1,760,000

	3
	Authoring of detailed course syllabi, learning outcomes, and assessment rubrics for 24 undergraduate modules
	10 weeks
	195,000
	1,950,000

	4
	Development of digital learning resources, interactive modules, and e-learning content compatible with the consortium's LMS platform
	6 weeks
	210,000
	1,260,000

	5
	Faculty training workshops (4 sessions) to onboard teaching staff on the new curriculum framework and pedagogical methodologies
	4 weeks
	160,000
	640,000

	6
	Quality assurance review, peer validation, and regulatory compliance check with the Ministry of Education and Science of the Russian Federation
	3 weeks
	175,000
	525,000

	7
	Post-implementation support, curriculum iteration, and annual review cycle (12-month period)
	12 months
	95,000
	1,140,000

	Subtotal:
	7,830,000

	VAT (20%):
	1,566,000

	Grand Total:
	9,396,000 RUB


3. Curriculum Developer Qualifications and Methodology
The Curriculum Developer assigned to this project holds a Doctorate in Educational Sciences from Saint Petersburg State University and possesses over fifteen years of experience in academic programme design within the Russia Saint Petersburg higher education landscape. The methodology employed will follow a constructivist, competency-based approach, ensuring that all developed curricula meet both the national FSES requirements and the consortium's strategic vision for international accreditation. The Curriculum Developer will conduct all on-site work at the consortium's primary office on Nevsky Prospekt, with remote collaboration available for distributed teams across the Saint Petersburg metropolitan area.
4. Payment Terms and Schedule
This Quotation Estimate stipulates the following payment structure, payable in Russian Rubles via bank transfer to the account of PetroEdu Consulting LLC, registered in Saint Petersburg, Russia:
· 30% advance payment (2,818,800 RUB) upon signed acceptance of this Quotation Estimate and execution of the service agreement.
· 40% milestone payment (3,758,400 RUB) upon delivery and client approval of the completed curriculum architecture and all 24 course syllabi.
· 30% final payment (2,818,800 RUB) upon completion of faculty training, regulatory compliance certification, and handover of all digital learning resources.
All payments are due within fifteen (15) business days of invoice issuance. Late payments shall incur a penalty of 0.1% per calendar day, in accordance with the Civil Code of the Russian Federation.
5. Terms and Conditions
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Beyond this period, pricing may be subject to revision based on market conditions in the Russia Saint Petersburg educational services sector.
1. All intellectual property rights to the curriculum materials, syllabi, and digital content developed by the Curriculum Developer shall transfer to the client upon full and final payment.
1. The Curriculum Developer shall maintain strict confidentiality regarding the client's proprietary academic data, student records, and internal strategic documents throughout the engagement.
1. Any changes to the scope of work beyond the items listed in Section 2 shall require a written change order and a revised Quotation Estimate approved by both parties.
1. This engagement is governed by the laws of the Russian Federation. Any disputes arising from this Quotation Estimate or the resulting service agreement shall be resolved through arbitration in Saint Petersburg, Russia.
1. The Curriculum Developer reserves the right to subcontract specialized sub-components (e.g., graphic design for digital modules) provided prior written consent is obtained from the client.
1. Force majeure events, including but not limited to government-mandated closures of educational institutions in Saint Petersburg, shall suspend project timelines without penalty to either party.
6. Acceptance and Authorization
By signing below, both parties acknowledge that this Quotation Estimate accurately represents the agreed-upon scope, cost, and terms for the Curriculum Developer engagement in Russia Saint Petersburg. This document, once countersigned, constitutes a binding proposal and shall form the financial annex to the master service agreement.
For PetroEdu Consulting LLC (Provider)
Name: Dr. Elena V. Sokolova
Title: Lead Curriculum Developer / Managing Director
Signature & Date
For Northwestern Federal Educational Consortium (Client)
Name: Mr. Dmitry A. Volkov
Title: Director of Academic Affairs
Signature & Date
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