Quotation Estimate - Curriculum Developer - Saudi Arabia Riyadh
QUOTATION ESTIMATE
Professional Curriculum Developer Services
Prepared for Clients in Saudi Arabia Riyadh
Quotation No.: QTE-2025-RYD-0472
Date Issued: 15 June 2025
Valid Until: 15 July 2025
1. Provider Information
This Quotation Estimate is issued by EduVision Learning Solutions LLC, a specialized educational consultancy firm headquartered in Riyadh, Kingdom of Saudi Arabia. Our team of certified Curriculum Developer professionals is dedicated to delivering world-class instructional design and curriculum architecture services tailored to the educational landscape of Saudi Arabia Riyadh and the broader Kingdom.
Address: King Fahd Road, Al Olaya District, Riyadh 12211, Saudi Arabia
Contact: +966 11 456 7890 | info@eduvision-sa.com
CR Number: 1010XXXXXX | VAT: 3100XXXXXX
2. Client Information
Client Name: [Institution / Organization Name]
Location: Riyadh, Saudi Arabia
Point of Contact: [Name & Title]
Reference / RFP No.: [As applicable]
3. Scope of Work – Curriculum Developer Services
The following Quotation Estimate outlines the comprehensive services to be delivered by our senior Curriculum Developer team. All work will be conducted in alignment with the Saudi Ministry of Education (MoE) standards, the National Curriculum Framework, and the Vision 2030 educational transformation goals applicable to institutions operating in Saudi Arabia Riyadh.
	Item No.
	Service Description
	Deliverables
	Duration
	Unit Price (SAR)
	Amount (SAR)

	01
	Needs Assessment & Stakeholder Analysis for the target institution in Riyadh
	Assessment Report, Gap Analysis Document
	3 weeks
	18,000
	18,000

	02
	Curriculum Framework Design (K-12 or Higher Education, as specified)
	Master Curriculum Blueprint, Learning Outcome Matrices
	6 weeks
	52,000
	52,000

	03
	Subject-Specific Curriculum Development (up to 8 subject areas)
	Detailed Unit Plans, Lesson Plans, Assessment Rubrics
	10 weeks
	96,000
	96,000

	04
	Digital Learning Integration & E-Learning Module Design
	Interactive Modules, LMS Content Packages, Multimedia Assets
	8 weeks
	74,000
	74,000

	05
	Teacher Training & Professional Development Workshops (4 sessions)
	Training Manuals, Session Recordings, Certification
	4 weeks
	32,000
	32,000

	06
	Quality Assurance, Peer Review & MoE Compliance Validation
	QA Report, Compliance Checklist, Final Sign-Off
	3 weeks
	22,000
	22,000

	07
	Ongoing Support & Curriculum Revision (12-month retainer)
	Quarterly Review Meetings, Revision Packages
	12 months
	48,000
	48,000

	Subtotal
	342,000

	VAT (15%)
	51,300

	TOTAL AMOUNT (SAR)
	393,300


4. Project Timeline
The total estimated project duration for the Curriculum Developer engagement is approximately 34 weeks (excluding the 12-month retainer period). The project will be executed in phases with milestone-based deliverables. All timelines are subject to client feedback cycles and approval gates. Given the operational context of Saudi Arabia Riyadh, our team will coordinate scheduling around the local academic calendar, national holidays, and the Islamic lunar calendar as applicable.
5. Payment Terms
Payment shall be structured as follows: 30% advance upon contract signing, 40% upon completion of the Curriculum Framework Design and Subject-Specific Development phases, and 30% upon final delivery and acceptance. The 12-month retainer will be billed quarterly in advance. All payments are due within 14 calendar days of invoice issuance. Late payments will incur a 2% monthly surcharge as per Saudi commercial law.
6. Terms and Conditions
1. This Quotation Estimate is valid for 30 calendar days from the date of issue. Beyond this period, pricing may be subject to revision based on market conditions in Saudi Arabia Riyadh.
1. All intellectual property rights in the developed curriculum materials shall transfer to the client upon full payment. The Curriculum Developer team retains the right to reference the project in portfolio materials with client written consent.
1. The scope of work is limited to the deliverables explicitly stated in Section 3. Any additional subject areas, grade levels, or modifications beyond the agreed scope will be quoted separately as a change order.
1. All curriculum content will be developed in compliance with Saudi Arabian educational regulations, cultural norms, and the directives of the Ministry of Education and the Supreme Council for Educational Quality (SCEQ).
1. Confidentiality: Both parties agree to maintain strict confidentiality regarding institutional data, student information, and proprietary educational content shared during the engagement.
1. Force Majeure: Neither party shall be liable for delays caused by events beyond reasonable control, including but not limited to government directives, natural disasters, or public health emergencies affecting operations in Riyadh.
1. Dispute Resolution: Any disputes arising from this agreement shall be resolved through amicable negotiation. Failing resolution within 30 days, the matter shall be referred to the competent courts in Riyadh, Kingdom of Saudi Arabia.
1. This Quotation Estimate does not constitute a binding contract until a formal Service Agreement is executed by both parties.
7. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, scope, and pricing outlined herein for the Curriculum Developer services to be delivered in Saudi Arabia Riyadh.
For EduVision Learning Solutions LLC
Authorized Signatory
Name: _________________________
Title: Managing Director
Date: _________________________
For the Client
Authorized Signatory
Name: _________________________
Title: _________________________
Date: _________________________
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