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QUOTATION ESTIMATE
Curriculum Developer Professional Services
Location of Service Delivery: Sri Lanka Colombo
Reference No: QTE-CLM-2025-0472 | Valid Until: 30 June 2025
	Prepared By
	EduCraft Solutions (Pvt) Ltd, 142 Galle Road, Colombo 03, Sri Lanka

	Prepared For
	Client Name / Institution (To be confirmed upon acceptance)

	Date of Issue
	15 May 2025

	Service Category
	Curriculum Developer – Full Engagement (Design, Development, Implementation Support)

	Currency
	Sri Lankan Rupees (LKR) / US Dollars (USD) – as applicable

	Validity Period
	45 calendar days from the date of issue


1. Introduction and Purpose of This Quotation Estimate
This Quotation Estimate document is issued by EduCraft Solutions (Pvt) Ltd to formally outline the scope, deliverables, timeline, and associated costs for engaging a qualified Curriculum Developer to design, develop, and implement a comprehensive educational curriculum tailored to the specific needs of the client institution. All services described herein will be delivered in and around Sri Lanka Colombo, leveraging the rich educational ecosystem, local regulatory frameworks, and cultural context unique to the Colombo metropolitan area and the broader Western Province of Sri Lanka.
This Quotation Estimate is prepared in accordance with the standards set by the Sri Lanka National Institute of Education (NIE) and aligns with the requirements of the Ministry of Education, Sri Lanka. The Curriculum Developer engaged under this proposal will possess a minimum of ten (10) years of experience in educational design, a Master's degree in Curriculum Studies or a related field, and demonstrated expertise in both national and international curriculum frameworks.
2. Scope of Work – Curriculum Developer Services
The Curriculum Developer will undertake the following key responsibilities as part of this engagement in Sri Lanka Colombo:
· Needs Assessment & Stakeholder Consultation: Conduct a thorough analysis of the institution's educational goals, learner demographics, and existing curriculum gaps. This phase includes on-site visits to the client's premises in Colombo and virtual consultations with faculty, administrators, and student representatives.
· Curriculum Framework Design: Develop a structured curriculum framework encompassing learning objectives, competency standards, assessment strategies, and pedagogical approaches aligned with Sri Lankan national education standards and, where applicable, Cambridge, IB, or other international frameworks.
· Content Development & Material Creation: Author detailed lesson plans, unit guides, teaching resources, and supplementary materials. All content will be culturally sensitive and contextually relevant to the Sri Lankan educational environment in Colombo.
· Assessment & Evaluation Design: Design formative and summative assessment instruments, rubrics, and evaluation protocols that meet both local regulatory requirements and the institution's quality benchmarks.
· Teacher Training & Capacity Building: Deliver a minimum of five (5) full-day training workshops for the client's teaching staff in Colombo, covering curriculum implementation strategies, differentiated instruction, and assessment literacy.
· Implementation Support & Review: Provide on-site and remote support during the first academic term of curriculum rollout, including bi-weekly review meetings, feedback collection, and iterative refinement of curriculum components.
3. Project Timeline
	Phase
	Description
	Duration
	Location

	Phase 1
	Needs Assessment & Stakeholder Consultation
	Weeks 1 – 3
	Colombo, Sri Lanka (On-site)

	Phase 2
	Curriculum Framework Design & Drafting
	Weeks 4 – 8
	Colombo, Sri Lanka (Hybrid)

	Phase 3
	Content Development & Material Creation
	Weeks 9 – 14
	Colombo, Sri Lanka (Hybrid)

	Phase 4
	Assessment Design & Validation
	Weeks 15 – 17
	Colombo, Sri Lanka (On-site)

	Phase 5
	Teacher Training Workshops
	Weeks 18 – 20
	Colombo, Sri Lanka (On-site)

	Phase 6
	Implementation Support & Final Review
	Weeks 21 – 26
	Colombo, Sri Lanka (Hybrid)


4. Financial Breakdown – Quotation Estimate
The following Quotation Estimate provides a detailed cost breakdown for the full engagement of the Curriculum Developer in Sri Lanka Colombo:
	Item / Service Component
	Unit
	Rate (LKR)
	Amount (LKR)

	Curriculum Developer – Professional Fee (Phase 1–6)
	26 weeks
	185,000 / week
	4,810,000

	Needs Assessment & Stakeholder Consultation (Travel, Materials)
	Lump Sum
	—
	250,000

	Curriculum Framework Design & Documentation
	Lump Sum
	—
	1,200,000

	Content Development & Teaching Material Creation
	Lump Sum
	—
	1,850,000

	Assessment & Evaluation Instrument Design
	Lump Sum
	—
	650,000

	Teacher Training Workshops (5 days, up to 40 participants)
	5 days
	120,000 / day
	600,000

	Implementation Support & Bi-weekly Reviews
	6 weeks
	95,000 / week
	570,000

	Travel & Local Transportation within Colombo
	Lump Sum
	—
	180,000

	Printing, Binding & Digital Distribution of Final Curriculum
	Lump Sum
	—
	120,000

	Subtotal (LKR)
	10,230,000

	VAT @ 18% (Sri Lanka)
	1,841,400

	TOTAL ESTIMATED COST (LKR)
	12,071,400

	TOTAL ESTIMATED COST (USD – Approx. @ 300 LKR/USD)
	~40,238


5. Terms and Conditions
1. This Quotation Estimate is valid for forty-five (45) calendar days from the date of issue. Beyond this period, rates and availability of the Curriculum Developer are subject to revision.
1. Payment terms: 30% advance upon signing the service agreement, 40% upon completion of Phase 3 (Content Development), and 30% upon final delivery and acceptance of all curriculum materials in Sri Lanka Colombo.
1. All intellectual property rights to the developed curriculum, materials, and assessment instruments shall transfer to the client upon full and final payment.
1. The Curriculum Developer shall adhere to all applicable Sri Lankan data protection and educational regulatory standards during the engagement.
1. Any changes to the scope of work beyond the originally agreed deliverables will be subject to a revised Quotation Estimate and mutual written consent.
1. Force majeure events, including but not limited to natural disasters, government-imposed restrictions, or public health emergencies affecting Colombo, Sri Lanka, may result in timeline adjustments without penalty to either party.
1. This Quotation Estimate does not constitute a binding contract until a formal Service Agreement is executed by both parties.
1. All communications, revisions, and approvals related to this engagement will be conducted in English, the primary working language for educational development in Sri Lanka Colombo.
6. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms outlined for the engagement of the Curriculum Developer in Sri Lanka Colombo.
	Client Signature
	_____________________________    Date: ____________

	Authorized Representative (EduCraft Solutions)
	_____________________________    Date: ____________
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