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1. Purpose and Scope of This Quotation Estimate
This Quotation Estimate is formally issued by EdVista Learning Solutions Co., Ltd. to provide Saigon International Academy with a comprehensive, itemized cost breakdown for the engagement of a senior Curriculum Developer to design, structure, and deliver a complete K-12 academic curriculum framework. All services described herein will be executed on-site and remotely within Vietnam Ho Chi Minh City, adhering to the Ministry of Education and Training (MOET) standards as well as international accreditation requirements (IB, Cambridge, and AP frameworks). This Quotation Estimate reflects current market rates for specialized Curriculum Developer expertise in the Vietnam Ho Chi Minh City educational sector as of June 2025.
2. Detailed Line Items – Curriculum Developer Services
	No.
	Service Description
	Duration
	Unit Rate (VND)
	Total (VND)

	1
	Curriculum Developer – Needs Assessment & Stakeholder Consultation in Vietnam Ho Chi Minh City (school visits, teacher interviews, parent surveys)
	2 weeks
	18,000,000
	36,000,000

	2
	Curriculum Developer – Design of Learning Objectives, Competency Frameworks & Assessment Strategies (Grades K-12)
	6 weeks
	22,000,000
	132,000,000

	3
	Curriculum Developer – Development of Subject-Specific Syllabi, Unit Plans & Lesson Sequences (Math, Science, Language Arts, Social Studies)
	8 weeks
	25,000,000
	200,000,000

	4
	Curriculum Developer – Creation of Teaching & Learning Materials, Workbooks, and Digital Resource Packages
	6 weeks
	20,000,000
	120,000,000

	5
	Curriculum Developer – Teacher Training Workshops & Professional Development Sessions (on-site in Vietnam Ho Chi Minh City)
	4 weeks
	15,000,000
	60,000,000

	6
	Curriculum Developer – Pilot Implementation Support, Feedback Collection & Iterative Refinement
	4 weeks
	18,000,000
	72,000,000

	7
	Curriculum Developer – Final Documentation, MOET Compliance Review & Handover Package
	2 weeks
	16,000,000
	32,000,000

	8
	Ongoing Curriculum Developer – Annual Review & Update Retainer (12 months post-delivery)
	12 months
	8,000,000
	96,000,000

	Subtotal
	748,000,000

	VAT (10%)
	74,800,000

	Grand Total (VND)
	822,800,000

	Grand Total (USD approx.)
	~$32,912


3. Terms and Conditions of This Quotation Estimate
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiry date, pricing for the Curriculum Developer engagement may be subject to revision based on market conditions in Vietnam Ho Chi Minh City.
1. Payment shall be made in Vietnamese Dong (VND) via bank transfer to the account specified by EdVista Learning Solutions Co., Ltd. A 30% advance payment is required upon acceptance of this Quotation Estimate to secure the Curriculum Developer's schedule.
1. Remaining payments will be disbursed in three equal milestones: 30% upon completion of the design phase, 30% upon delivery of all teaching materials, and 10% upon final handover and acceptance in Vietnam Ho Chi Minh City.
1. All intellectual property rights to the curriculum materials developed by the Curriculum Developer shall transfer to the client upon full and final payment.
1. The Curriculum Developer will work a minimum of five (5) days per week, with on-site presence at the client's facility in Vietnam Ho Chi Minh City for at least three (3) days per week. Remote work is permitted for the remaining days.
1. Any scope changes or additional requests beyond the items listed in this Quotation Estimate will be subject to a separate change-order agreement and additional cost assessment.
1. EdVista Learning Solutions Co., Ltd. reserves the right to substitute the assigned Curriculum Developer with a professional of equivalent or superior qualifications, subject to client approval.
1. This Quotation Estimate does not include costs for printing, licensing of third-party educational software, or travel expenses for the client's staff attending training sessions.
1. Confidentiality: All data, student information, and proprietary materials shared during the engagement in Vietnam Ho Chi Minh City shall be treated as strictly confidential and protected under Vietnamese data protection regulations.
4. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and pricing outlined for the Curriculum Developer services to be delivered in Vietnam Ho Chi Minh City.
For EdVista Learning Solutions Co., Ltd.:
Name: _________________________
Position: Project Director
Signature: _________________________
Date: _________________________
For Saigon International Academy:
Name: _________________________
Position: Director of Academic Affairs
Signature: _________________________
Date: _________________________
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