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1. Scope of Work — Editor Services in Bangladesh Dhaka
This Quotation Estimate is issued by Creative Edge Media Solutions, a registered editorial and post-production firm headquartered in Bangladesh Dhaka, to provide comprehensive Editor services for the client's multimedia content production requirements. The Editor engagement described herein encompasses video editing, content editing, graphic layout editing, and final post-production deliverables tailored specifically for the Bangladeshi market and broadcast standards applicable in Bangladesh Dhaka.
Our Editor team, based in the Banani commercial district of Bangladesh Dhaka, will be responsible for all stages of editorial processing from raw footage ingestion through to final export. The Editor will work in coordination with the client's creative director located in Dhaka and will ensure all deliverables comply with the Bangladesh Telecommunications Regulatory Commission (BTRC) content guidelines and local broadcasting standards.
2. Itemized Quotation Estimate Breakdown
	#
	Editor Service Description
	Duration / Qty
	Unit Rate (BDT)
	Amount (BDT)
	Remarks

	1
	Senior Video Editor — Raw footage assembly, timeline construction, and rough cut for corporate promotional video (4K resolution)
	10 working days
	8,500 / day
	85,000
	Based in Dhaka studio

	2
	Content Editor — Script refinement, subtitle localization (Bangla & English), and narrative restructuring for a 12-minute documentary
	8 working days
	6,200 / day
	49,600
	Bilingual Editor

	3
	Post-Production Editor — Color grading, audio mixing, sound design, and visual effects integration for broadcast delivery in Dhaka
	7 working days
	9,000 / day
	63,000
	DaVinci Resolve suite

	4
	Graphic & Layout Editor — Motion graphics, lower thirds, title sequences, and end-credit animation for the final package
	5 working days
	7,500 / day
	37,500
	After Effects / Premiere

	5
	Quality Assurance & Final Export — Multi-format rendering (MP4, MOV, ProRes), platform-specific edits for YouTube, Facebook, and local TV channels in Bangladesh Dhaka
	3 working days
	5,800 / day
	17,400
	3 revision rounds

	6
	Project Management & Client Coordination — Dedicated Editor liaison for weekly progress meetings at client office in Gulshan, Dhaka
	33 working days
	3,000 / day
	99,000
	On-site in Dhaka

	Subtotal (BDT)
	351,500
	

	VAT @ 15% (Bangladesh)
	52,725
	

	Grand Total (BDT)
	404,225
	


3. Quotation Estimate Terms & Conditions
1. This Quotation Estimate is valid for a period of thirty (30) calendar days from the date of issue. Beyond this period, rates for Editor services in Bangladesh Dhaka are subject to revision based on market conditions and resource availability.
1. Payment terms: 40% advance upon acceptance of this Quotation Estimate, 35% upon delivery of the rough cut by the Editor, and 25% upon final approval and handover of all deliverables. All payments shall be made in Bangladeshi Taka (BDT) via bank transfer to our account at BRAC Bank, Dhaka branch.
1. The Editor team will operate from our studio premises in Banani, Bangladesh Dhaka, with on-site client meetings scheduled at the client's Gulshan office as per the project timeline. Travel within Dhaka city limits is included in this Quotation Estimate.
1. All raw footage, project files, and intermediate renders remain the intellectual property of the client. The Editor retains no rights to the content beyond the scope of this engagement. A non-disclosure agreement (NDA) will be executed prior to the commencement of editorial work.
1. Three (3) rounds of revisions are included per deliverable. Additional revision requests beyond the included rounds will be charged at 50% of the applicable daily Editor rate as itemized in this Quotation Estimate.
1. Any scope change, additional deliverable, or extension of the Editor engagement beyond the 33 working days specified herein will require a written amendment to this Quotation Estimate, signed by both parties, before work commences on the additional scope.
1. Force majeure events, including but not limited to natural disasters, government-mandated lockdowns, or infrastructure failures in Bangladesh Dhaka, shall extend the project timeline proportionally without penalty to either party.
1. This Quotation Estimate is governed by the laws of the People's Republic of Bangladesh. Any disputes arising from this Editor services agreement shall be resolved through arbitration in Dhaka in accordance with the Bangladesh Arbitration Act, 2001.
4. Project Timeline Summary
	Milestone
	Editor Phase
	Estimated Completion

	Kick-off & Briefing
	Editor onboarding, asset handover
	Week 1

	Rough Cut Delivery
	Video Editor & Content Editor
	Week 3

	Fine Cut & Color Grade
	Post-Production Editor
	Week 5

	Final Delivery & Export
	QA Editor & Project Manager
	Week 6


5. Acceptance
By signing below, the client acknowledges and accepts this Quotation Estimate for Editor services to be delivered in Bangladesh Dhaka as described herein. This document, once countersigned, constitutes a binding service agreement between both parties.
For Creative Edge Media Solutions
Authorized Signatory — Editor Services Division
Dhaka, Bangladesh
For the Client
Authorized Signatory
Dhaka, Bangladesh
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