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Quotation Estimate
Quotation Details
Quotation No: QTE-LAG-2025-0472
Date Issued: 15 June 2025
Valid Until: 15 July 2025 (30 days)
Prepared For: [Client Name / Organization]
Client Address: [Client Address], Lagos, Nigeria
Project Reference
Service Type: Professional Editor
Location of Service: Lagos, Nigeria
Estimated Duration: 6 Weeks
Project Code: ED-LAG-2025-089
Currency: Nigerian Naira (NGN)
Dear Valued Client,
Thank you for considering Lagos Editorial Excellence Ltd. for your professional editing requirements. This Quotation Estimate has been carefully prepared to outline the full scope, deliverables, and associated costs for engaging our certified Editor team to deliver premium editorial services within the Lagos, Nigeria market. We are committed to providing world-class Editor services that meet the highest international standards while remaining fully attuned to the linguistic, cultural, and professional context of Nigeria Lagos.
Our Editor team comprises seasoned professionals with over a combined 25 years of experience in editorial work across publishing, corporate communications, academic research, and digital media. All services described in this Quotation Estimate will be executed by a dedicated Editor assigned exclusively to your project, ensuring continuity, consistency, and deep familiarity with your specific content requirements throughout the engagement in Nigeria Lagos.
Scope of Editor Services
The following Editor services are included in this Quotation Estimate and will be delivered by our lead Editor and supporting editorial staff based in our Lagos, Nigeria office:
	#
	Editor Service Description
	Deliverable / Output
	Duration
	Cost (NGN)

	1
	Comprehensive copyediting and proofreading of manuscript (up to 80,000 words) by senior Editor
	Edited manuscript with tracked changes and editorial notes
	2 Weeks
	₦ 480,000

	2
	Structural and developmental editing for content reorganization, flow, and argumentation
	Revised outline and restructured draft
	1.5 Weeks
	₦ 350,000

	3
	Style guide compliance review (APA 7th / Chicago / House Style) by dedicated Editor
	Style compliance report and corrected text
	1 Week
	₦ 220,000

	4
	Fact-checking, reference verification, and citation auditing performed by Editor team
	Verification log and corrected references
	1 Week
	₦ 180,000

	5
	Final proofread and pre-publication quality assurance by lead Editor
	Clean final manuscript and QA certificate
	0.5 Weeks
	₦ 120,000

	6
	Client consultation meetings (up to 4 sessions) with assigned Editor in Lagos, Nigeria office or via video call
	Meeting minutes and action items
	Ongoing
	₦ 90,000

	7
	Editorial project management, scheduling, and progress reporting
	Weekly progress reports
	6 Weeks
	₦ 110,000

	TOTAL ESTIMATED COST (Before VAT)
	₦ 1,550,000

	VAT (7.5% – Nigeria Lagos applicable rate)
	₦ 116,250

	GRAND TOTAL (Incl. VAT)
	₦ 1,666,250


Terms and Conditions of This Quotation Estimate
1. Validity: This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiry date, pricing for the Editor services may be subject to revision based on market conditions in Nigeria Lagos.
2. Payment Terms: A non-refundable deposit of 40% (₦ 666,500) is due upon acceptance of this Quotation Estimate to secure the Editor's schedule. The remaining 60% (₦ 999,750) is payable upon delivery of the final edited manuscript. All payments shall be made in Nigerian Naira (NGN) via bank transfer to our Lagos, Nigeria account.
3. Revisions: The Editor services include one (1) round of revisions per deliverable. Additional revision rounds beyond the included scope will be billed at ₦ 85,000 per round and are not covered under this Quotation Estimate.
4. Confidentiality: Our Editor and all editorial staff bound by this engagement in Nigeria Lagos shall maintain strict confidentiality regarding all client materials. A Non-Disclosure Agreement (NDA) will be executed prior to the commencement of work.
5. Intellectual Property: Upon full payment, all rights to the final edited work transfer to the client. The Editor retains no claim over the content. Our firm retains the right to reference the engagement in portfolio materials, subject to client approval.
6. Cancellation: Should the client cancel this Quotation Estimate after the deposit has been paid, the deposit shall be non-refundable. Cancellation after work has commenced will incur a pro-rata charge for Editor hours already expended.
7. Force Majeure: Neither party shall be liable for delays caused by events beyond reasonable control, including but not limited to power outages, internet disruptions, or government-mandated closures affecting operations in Lagos, Nigeria.
8. Governing Law: This Quotation Estimate and the resulting engagement shall be governed by the laws of the Federal Republic of Nigeria. Any disputes shall be resolved through arbitration in Lagos, Nigeria.
Acceptance of Quotation Estimate
By signing below, the client acknowledges receipt of this Quotation Estimate for Editor services and agrees to the terms, conditions, and pricing outlined herein. The Editor engagement in Nigeria Lagos shall commence upon receipt of the initial deposit.
For Lagos Editorial Excellence Ltd. (Editor Provider)
Name: ___________________________
Title: Lead Editor / Managing Director
Signature: _________________________
Date: ___________________________
Company Stamp
For the Client
Name: ___________________________
Title: ___________________________
Signature: _________________________
Date: ___________________________
Company Stamp (if applicable)
Lagos Editorial Excellence Ltd. | 14 Adeola Odeku Street, Victoria Island, Lagos, Nigeria
This Quotation Estimate is a commercial document issued by our Editor services division. It does not constitute a binding contract until both parties have executed the acceptance section above.
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